## Dashboard
[19 empty] | Residential |  | 3635.145
[19 empty] | C&I |  | 3718.01
| System Capacity |  |  |  |  | Project Value (RM) |  |  |  |  | Revenue (RM) |  |  |  |  | Collection (RM) |  |  |  |  | No of Sites
| Total | 2023 | 2024 | 2025 | 2026 | Total | 2023 | 2024 | 2025 | 2026 | Total | 2023 | 2024 | 2025 | 2026 | Total | 2023 | 2024 | 2025 | 2026 | Total | 2023 | 2024 | 2025 | 2026
Residential (PV System) | 3635.145 | 313.3 | 1637.165 | 1684.68 | 0 | 10314867.6 | 782725 | 5036797.2 | 4495345.4 | 0 | 8802124.6 | 379240 | 3897315.2 | 4525569.4 | 0 | 8586827.6 | 301640 | 3691311.2 | 4593876.4 | 0 | 313 | 23 | 143 | 147 | 0
C&I (PV System) | 3718.01 | 428.695 | 2088.345 | 1200.97 | 0 | 7185553.58 | 521800 | 4266680 | 2397073.58 | 0 | 6946746.41 | 278820 | 2643170 | 4024756.41 | 0 | 5420201.41 | 278820 | 2422890 | 2718491.41 | 0 | 33 | 3 | 18 | 12 | 0
Residential BESS | 287.4 | 287.4 | 0 | 0 | 0 | 720000 | 720000 | 0 | 0 | 0 | 720000 | 432000 | 288000 | 0 | 0 | 720000 | 432000 | 288000 | 0 | 0 | 1 | 1 | 0 | 0 | 0
C&I BESS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EV Chargers | 1786 | 100 | 789 | 897 | 0 | 1430963 | 93380 | 355363 | 982220 | 0 | 957823 | 46690 | 342903 | 568230 | 0 | 735522.5 | 46690 | 321025 | 367807.5 | 0 | 18 | 1 | 7 | 10 | 0
Total | [5 empty] | 19651384.18 | 2117905 | 9658840.2 | 7874638.98 | 0 | 17426694.01 | 1136750 | 7171388.2 | 9118555.81 | 0 | 15462551.51 | 1059150 | 6723226.2 | 7680175.31 | 0 | 365 | 28 | 168 | 169 | 0
| System Capacity (kWp) |  |  |  |  | System Capacity (kWp) |  |  |  |  | Project Value (RM) |  |  |  |  | Project Value (RM)
| Residential |  |  |  |  | C&I |  |  |  |  | Residential |  |  |  |  | C&I
| Total | 2023 | 2024 | 2025 | 2026 | Total | 2023 | 2024 | 2025 | 2026 | Total | 2023 | 2024 | 2025 | 2026 | Total | 2023 | 2024 | 2025 | 2026
NEM | 3417.375 | 220.15 | 1637.165 | 1560.06 | 0 | 3286.685 | 428.695 | 1675 | 1182.99 | 0 | 9838567.6 | 751725 | 5036797.2 | 4050045.4 | 0 | 6721700 | 521800 | 3866600 | 2333300 | 0
SELCO | 217.77 | 93.15 | 0 | 124.62 | 0 | 431.325 | 0 | 413.345 | 17.98 | 0 | 1196300 | 751000 | 0 | 445300 | 0 | 463853.58 | 0 | 400080 | 63773.58 | 0
ATAP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| System Capacity (kWp) |  |  |  |  | Project Value (RM)
| Total |  |  |  |  | Total
| Total | 2023 | 2024 | 2025 | 2026 | Total | 2023 | 2024 | 2025 | 2026
Tham | 4469.92 | 5.75 | 2808.42 | 1648.73 | - | 11010153.2 | 22000 | 7289133.2 | 3673920 | -
Chean Bang | 686.555 | 128.85 | 333.785 | 223.92 | 0 | 2335898 | 461700 | 1094898 | 779300 | 0
Simon | 1185.055 | 607.395 | 429.69 | 147.97 | 0 | 3516528 | 1634205 | 783603 | 1098720 | 0
Ong | 71.53 | 0 | 13.8 | 57.73 | 0 | 273958 | 0 | 54930 | 219028 | 0
Patricia | 934.89 | 0 | 120.51 | 807.3 | 0 | 2493346.98 | 0 | 368176 | 2103670.98 | 0
Reeve | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 7347.95 | 741.995 | 3706.205 | 2885.65 | 0 | 19629884.18 | 2117905 | 9590740.2 | 7874638.98 | 0
| System Capacity (kWp) |  |  |  |  | System Capacity (kWp) |  |  |  |  | Project Value (RM) |  |  |  |  | Project Value (RM)
| Residential |  |  |  |  | C&I |  |  |  |  | Residential |  |  |  |  | C&I
| Total | 2023 | 2024 | 2025 | 2026 | Total | 2023 | 2024 | 2025 | 2026 | Total | 2023 | 2024 | 2025 | 2026 | Total | 2023 | 2024 | 2025 | 2026
Tham | 1805.1 | 5.75 | 1131.85 | 667.5 | - | 2657.8 | 0 | 1676.57 | 981.23 | - | 5183153.2 | 22000 | 3434533.2 | 1726620 | - | 5801900 | 0 | 3854600 | 1947300 | -
Chean Bang | 622.845 | 128.85 | 310.785 | 183.21 | 0 | 63.71 | 0 | 23 | 40.71 | 0 | 2164898 | 461700 | 1014898 | 688300 | 0 | 171000 | 0 | 80000 | 91000 | 0
Simon | 293.135 | 178.7 | 59.635 | 54.8 | 0 | 891.92 | 428.695 | 370.055 | 93.17 | 0 | 2559648 | 1112405 | 503523 | 943720 | 0 | 956880 | 521800 | 280080 | 155000 | 0
Ong | 71.53 | 0 | 13.8 | 57.73 | 0 | 0 | 0 | 0 | 0 | 0 | 273958 | 0 | 54930 | 219028 | 0 | 0 | 0 | 0 | 0 | 0
Patricia | 823.23 | 0 | 101.79 | 721.44 | 0 | 104.58 | 0 | 18.72 | 85.86 | 0 | 2216073.4 | 0 | 316176 | 1899897.4 | 0 | 255773.58 | 0 | 52000 | 203773.58 | 0
Reeve | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Malaysia | Total
#VALUE! | 0
#VALUE! | 1
#VALUE! | 3
#VALUE! | 10
#VALUE! | 138
#VALUE! | 4
#VALUE! | 3
#VALUE! | 27
#VALUE! | 0
#VALUE! | 7
#VALUE! | 140
#VALUE! | 31
#VALUE! | 0
#VALUE! | 0
Authority Submission Summary Data
|  | NEM Rakyat |  | NOVA (C&I)
Max No. of Days for SEDA Approval |  | 109 |  | 132
Min No. of Days for SEDA Approval |  | 3 |  | 10
Ave No. of Days for SEDA Approval |  | 21.5577 |  | 41.7143
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Pivot (hidden)
Business | Metric | Year | Value | Year | (All) |  |  |  | Year | (All)
Residential (PV System) | System Capacity | 2023 | 313.3
Residential (PV System) | System Capacity | 2024 | 1637.165 | Sum of Value | Column Labels |  |  |  | Sum of Value | Column Labels
Residential (PV System) | System Capacity | 2025 | 1684.68 | Row Labels | Project Value | Revenue | Collection | Grand Total | Row Labels | System Capacity | Grand Total
Residential (PV System) | System Capacity | 2026 | 0 | Residential (PV System) | 10314867.6 | 8802124.6 | 8586827.6 | 27703819.8 | Residential (PV System) | 3635.145 | 3635.145
C&I (PV System) | System Capacity | 2023 | 428.695 | C&I (PV System) | 7185553.58 | 6946746.41 | 5420201.41 | 19552501.4 | C&I (PV System) | 3718.01 | 3718.01
C&I (PV System) | System Capacity | 2024 | 2088.345 | Residential BESS | 720000 | 720000 | 720000 | 2160000 | Residential BESS | 287.4 | 287.4
C&I (PV System) | System Capacity | 2025 | 1200.97 | C&I BESS | 0 | 0 | 0 | 0 | C&I BESS | 0 | 0
C&I (PV System) | System Capacity | 2026 | 0 | EV Chargers | 1430963 | 957823 | 735522.5 | 3124308.5 | EV Chargers | 1786 | 1786
Residential BESS | System Capacity | 2023 | 287.4 | Grand Total | 19651384.18 | 17426694.01 | 15462551.51 | 52540629.7 | Grand Total | 9426.555 | 9426.555
Residential BESS | System Capacity | 2024 | 0
Residential BESS | System Capacity | 2025 | 0
Residential BESS | System Capacity | 2026 | 0
C&I BESS | System Capacity | 2023 | 0
C&I BESS | System Capacity | 2024 | 0
C&I BESS | System Capacity | 2025 | 0
C&I BESS | System Capacity | 2026 | 0
EV Chargers | System Capacity | 2023 | 100
EV Chargers | System Capacity | 2024 | 789
EV Chargers | System Capacity | 2025 | 897
EV Chargers | System Capacity | 2026 | 0
Residential (PV System) | Project Value | 2023 | 782725
Residential (PV System) | Project Value | 2024 | 5036797.2
Residential (PV System) | Project Value | 2025 | 4495345.4
Residential (PV System) | Project Value | 2026 | 0
C&I (PV System) | Project Value | 2023 | 521800
C&I (PV System) | Project Value | 2024 | 4266680
C&I (PV System) | Project Value | 2025 | 2397073.58
C&I (PV System) | Project Value | 2026 | 0
Residential BESS | Project Value | 2023 | 720000
Residential BESS | Project Value | 2024 | 0
Residential BESS | Project Value | 2025 | 0
Residential BESS | Project Value | 2026 | 0
C&I BESS | Project Value | 2023 | 0
C&I BESS | Project Value | 2024 | 0
C&I BESS | Project Value | 2025 | 0
C&I BESS | Project Value | 2026 | 0
EV Chargers | Project Value | 2023 | 93380
EV Chargers | Project Value | 2024 | 355363
EV Chargers | Project Value | 2025 | 982220
EV Chargers | Project Value | 2026 | 0
Residential (PV System) | Revenue | 2023 | 379240
Residential (PV System) | Revenue | 2024 | 3897315.2
Residential (PV System) | Revenue | 2025 | 4525569.4
Residential (PV System) | Revenue | 2026 | 0
C&I (PV System) | Revenue | 2023 | 278820
C&I (PV System) | Revenue | 2024 | 2643170
C&I (PV System) | Revenue | 2025 | 4024756.41
C&I (PV System) | Revenue | 2026 | 0
Residential BESS | Revenue | 2023 | 432000
Residential BESS | Revenue | 2024 | 288000
Residential BESS | Revenue | 2025 | 0
Residential BESS | Revenue | 2026 | 0
C&I BESS | Revenue | 2023 | 0
C&I BESS | Revenue | 2024 | 0
C&I BESS | Revenue | 2025 | 0
C&I BESS | Revenue | 2026 | 0
EV Chargers | Revenue | 2023 | 46690
EV Chargers | Revenue | 2024 | 342903
EV Chargers | Revenue | 2025 | 568230
EV Chargers | Revenue | 2026 | 0
Residential (PV System) | Collection | 2023 | 301640
Residential (PV System) | Collection | 2024 | 3691311.2
Residential (PV System) | Collection | 2025 | 4593876.4
Residential (PV System) | Collection | 2026 | 0
C&I (PV System) | Collection | 2023 | 278820
C&I (PV System) | Collection | 2024 | 2422890
C&I (PV System) | Collection | 2025 | 2718491.41
C&I (PV System) | Collection | 2026 | 0
Residential BESS | Collection | 2023 | 432000
Residential BESS | Collection | 2024 | 288000
Residential BESS | Collection | 2025 | 0
Residential BESS | Collection | 2026 | 0
C&I BESS | Collection | 2023 | 0
C&I BESS | Collection | 2024 | 0
C&I BESS | Collection | 2025 | 0
C&I BESS | Collection | 2026 | 0
EV Chargers | Collection | 2023 | 46690
EV Chargers | Collection | 2024 | 321025
EV Chargers | Collection | 2025 | 367807.5
EV Chargers | Collection | 2026 | 0

## Master Data
Project No | Client Name | Closed Date | Sales PIC | Category | Scheme | Location | PV System Capacity (kWp) | EV Charger Capacity | BESS Capacity | Project Value (RM) | VO (RM) | Payment Method | Outright/PPA | Module | Module Quantity | Inverter | Inverter Warranty | I/C Number | Installation Address | Phone Number | Email Address | Insurance Warranty | DLP Period | O&M | Partner | Services Exclusion | Additional Remark
2303005 | Wong Kim Mei | 2023-04-05 | Simon | R-PV | NEM | #VALUE! | 8.05 | - |  | 32000 |  | Self finance | Outright | Astronergy 575Wp | 14 | Solinteg MHT-8K-25 hybrid |  | 731013-10-5784 | No. 24, Jalan Seri Muka 36/27A, Taman Menegun Indah, 41000 Klang, Selangor. | 016-335 4884 | wongkimmei73@gmail.com | 5 years | 1 year
2303006 | Ang Ching Ming | 2023-04-13 | Simon | R-PV | NEM | #VALUE! | 12.65 | - |  | 40000 |  | Self finance | Outright | Astronergy 575Wp | 22 | Solinteg MHT-10K-25 hybrid |  | 931003-10-6105 | 1, Jalan Ulek Mayang 2C/KU5, Bandar Bukit Raja, 41050 Klang, Selangpr | 017-9666099 | cmang_02@outlook.com | 1 year | 1 year
2304016 | Tan Sei Choon | 2023-05-02 | Chean Bang | R-PV | SELCO | #VALUE! | 8.05 | - |  | 31000 |  | Self finance | Outright | Astronergy 575Wp | 14 | Solinteg MHT-8K-25 hybrid |  | 650818-06-5287 | 2, Lorong Bukit Setongkol Perdana 52, Taman Fairmont Jaya, 25200 Kuantan, Pahang. | 016-922 3868 | tesoon12@gmail.com | 5 years | 1 year
2305021 | Ho Hon Kit | 2023-05-12 | Simon | R-PV | NEM | #VALUE! | 4.65 | - |  | 20000 |  | Self finance | Outright | Astronergy 575Wp | 8 | Solinteg MHS-3.6K-30 hybrid |  | 670422-10-5607 | No 32, Jalan Puteri 12/7, Bandar Puteri, 47100 Puchong, Selangor. | 012-3979968 | hkho@trident-x.com | 5 years | 1 year
2305026 | Stanley Ang Leng Chuan | 2023-07-07 | Simon | R-PV | NEM | #VALUE! | 12.65 | - |  | 40000 |  | Self finance | Outright | Astronergy 575Wp | 22 | Solinteg MHT-10K-25 hybrid |  | 751007-10-5671 | 5, Jalan Bidara 9, Bandar Botanic, 41200 Klang, Selangor. | 016-6767999 | stanleyang9@gmail.com | 1 year | 1 year
2306033 | Foo Tuang Lee | 2023-06-06 | Chean Bang | R-PV | NEM | #VALUE! | 4.65 | - |  | 16000 |  | Self finance | Outright | Astronergy 575Wp | 8 | Solinteg MHS-3.6K-30 hybrid |  | 741128-01-5075 | No 20, Jln Pelangi 15, Tmn Pelangi, 86000 Kluang, Johor | 016-2368221 | ericfoo8888@gmail.com | N/A | 1 year
2306037 | Tan Hong Guan | 2023-09-26 | Simon | R-PV | NEM | #VALUE! | 10.925 | - |  | 36575 |  | Self finance | Outright | Astronergy 575Wp | 19 | Huawei SUN2000-10KTL |  | 680512-07-5359 | No 6, Pinggir Bukit Segar 2, Tmn Bkt Segar, 56100 Cheras, Kuala Lumpur | 012-4380246 | hongguan.tan@gmail.com | N/A | 1 year |  | EDCA
2307040 | Law Soo Chin | 2023-07-11 | Chean Bang | R-PV | NEM | #VALUE! | 12.65 | - |  | 40000 |  | Self finance | Outright | Astronergy 575Wp | 22 | Solinteg MHT-10K-25 hybrid |  | 640407-07-5713 | 6, Jalan BS 3/8, Taman Bukit Serdang, 43300 Seri Kembangan, Selangor. | 016-2013221 | lawsc123@hotmail.com | 3 years | 1 year
2305011 | Kossan FRP Marketing (M) Sdn Bhd | 2023-06-01 | Simon | C&I-PV | NEM | #VALUE! | 283.945 | - |  | 242000 |  | Cash | Outright | - | - | - |  | - | PT 2019, Jln Keretapi Lama Off, Jln Kapar, BT 4 3/4, Kg Rantau Panjang, 42100 Klang, Selangor | - | - | N/A | 1 year | N/A | EDCA
2304007 | MTJ Development Sdn Bhd (Intercontinental KL) | 2023-06-28 | Simon | C&I-PV | NEM | #VALUE! | 51.75 |  |  | 188800 |  | Cash | Outright | Astronergy 575Wp | 90 | Goodwe 50kW |  | - | No 165, Jln Ampang, 50450 Kuala Lumpur, WP Kuala Lumpur | - | - | 3 years | 1 year | N/A
2307042 | Dato' Sri Ng Chong Keong | 2023-06-09 | Chean Bang | R-PV | NEM | #VALUE! | 16.1 | - |  | 50000 |  | Self finance | Outright | Astronergy 575Wp | 28 | Solinteg MHT-12K-25 hybrid |  | 650309-08-5407 | 9, Lorong Tok Sira 4, Taman Melor, 25050 Kuantan, Pahang. | 016-9907409 | ng_xinnee@hotmail.com | 5 years | 1 year
2308058 | Cheong Yik Yin | 2023-08-06 | Simon | R-PV | NEM | #VALUE! | 6.9 | - |  | 30000 |  | Self finance | Outright | Astronergy 575Wp | 12 | Solinteg MHT-5K-25 hybrid |  | 950710-14-6004 | No. 18, Jalan Setia Utama U13/39D, Setia Alam, Seksyen U13, 40170 Shah Alam, Selangor. | 016-6530107 | yikyin_cheong@hotmail.com | 3 years | 1 year
2308062 | Lim Chin Joo | 2023-11-17 | Simon | R-PV | NEM | #VALUE! | 12.65 | - |  | 42300 |  | Self finance | Outright | Astronergy 575Wp | 22 | Huawei SUN2000-12KTL |  | 6905020-02-5211 | 8, Jln BK 6A/2A, Bandar Kinrara, 47100 Puchong, Selangor Darul Ehsan | 012-6151020 | chinjoolim@gmail.com | 3 years | 1 year
2309068 | Kee Siew Chuan (Ngo Woon Wah) | 2023-10-20 | Chean Bang | R-PV | NEM | #VALUE! | 6.9 | - |  | 28500 |  | Self finance | Outright | Astronergy 575Wp | 12 | Solinteg MHT-5K-25 hybrid |  | 730119-08-5342 | No 12-A, Lrg Bukit Setongkol Jaya 32, Bkt Setongkol, 25200, Kuantan, Pahang Darul Makmur | 019-9631028 | siewchuan639@gmail.com | 5 years | 1 year
2310078 | Lee Nyok Cheng | 2023-10-10 | Chean Bang | R-PV | NEM | #VALUE! | 16.1 | - |  | 52000 |  | Self finance | Outright | Astronergy 575Wp | 28 | Solinteg MHT-12K-25 hybrid |  | 581227-05-5427 | No. 1, Lorong IM 1/62, Perumahan Indera Mahkota 1, 25200 Kuantan, Pahang. | 016-9221189 | songlee1188@gmail.com | 5 years | 1 year
2310083 | Ong Eng Guan | 2023-10-30 | Chean Bang | R-PV | NEM | #VALUE! | 8.05 | - |  | 31000 |  | Self finance | Outright | Astronergy 575Wp | 14 | Solinteg MHT-8K-25 hybrid |  | 451011-02-5493 | No. 9 Lorong Im 11/12, Mahkota Heights, 25200 Kuantan, Pahang Darul Makmur | 012-9853289 | daniel_8632@yahoo.com | 5 years | 1 year
2310084 | Chia Le Chin | 2023-11-01 | Chean Bang | R-PV | NEM | #VALUE! | 8.05 | - |  | 34000 |  | Cash + instalment | Outright | Astronergy 575Wp | 14 | Solinteg MHT-8K-25 hybrid |  | 730219-06-5090 | No 11, Lorong Im 11/12, Mahkota Heights, 25200 Kuantan, Pahang Darul Makmur | 013-9318778 | health_trading@yahoo | 5 years | 1 year
2305024 | Beh Poh Loh | 2023-06-26 | Chean Bang | R-PV | NEM | #VALUE! | 12.65 | - |  | 42500 | 6000 | Self finance | Outright | Astronergy 575Wp | 22 | GoodWe GW10KN-ET |  | 890620-06-5065 | No 10, Lorong Peramu Jaya 1/3, Perumahan Peramu Jaya 1, 26060 Kuantan, Pahang Darul Makmur | 016-9862270 | graybackboy@hotmail.com | 5 years | 1 year
2307052 | Ngoh Win Nee | 2023-08-16 | Chean Bang | R-PV | NEM | #VALUE! | 4.6 | - |  | 22100 |  | Credit Card Instalment | Outright | Astronergy 575Wp | 8 | Solinteg MHS-3.6K-30 hybrid |  | 851017-06-5456 | No 49, Lrg Tiram Jaya 5, Perumahan Tiram Jaya, 25200 Kuantan, Pahang | 012-9860700 | winneengoh@gmail.com | 5 years | 1 year
2304010 | Tung Seng Chang | 2023-05-15 | Simon | R-PV | NEM | #VALUE! | 13.625 | - |  | 20650 |  | Cash | Outright | - | - | Goodwe GW10K-SDT-20 |  | 720703-10-5665 | 18, Jalan Setia Perdana U13/29C, Setia Alam, 40170 Shah Alam, Selangor | 019-2933333 | tungsc6@gmail.com | N/A | 1 year |  | EDCA
2308065 | Pua Hock Meng | 2023-09-07 | Chean Bang | R-PV | NEM | #VALUE! | 8.625 | - |  | 33000 | 2500 | Self finance | Outright | Astronergy 575Wp | 15 | Solinteg MHT-8K-25 hybrid |  | 830524-06-5271 | No. 18, Lorong Peramu Jaya 1/2, Perumahan Peramu Jaya 1, 26060 Kuantan, Pahang Darul Makmur | 019-9956536 | prinze.pua@gmail.com | 5 years | 1 year
2306009 | Dato Arif Stephen bin Abdullah | 2023-09-24 | Simon | R-BESS | SELCO | #VALUE! | 85.1 | 44 | 287.4 | 720000 |  | Cash | Outright | Astronergy 575Wp | 148 | Solax X3-Ultra 20kW x 3 |  |  | Lot 12193, Jalan Felcra Semungkis, Batu 14 Hulu Langat, 43100 Hulu Langat, Selangor Darul Ehsan |  |  |  | 1 year
2303003 | Greenlast Housing Development Sdn Bhd | 2024-01-18 | Chean Bang | C&I-PV | NEM | #VALUE! | 23 | - |  | 80000 |  | Self finance | Outright | Astronergy 575Wp | 40 | Goodwe GW20K-SDT-20 |  | - | Lot 1-5, Jalan Semambu,Kawasan Perindustrian Semambu, Kuantan Pahang 25350 Malaysia | - | - | N/A | 1 year | Others |  |  | Panel Cleaning 3 years (Once per year)
2311040 | DBTS Industries Sdn Bhd | 2023-11-14 | SImon | C&I-PV | NEM | #VALUE! | 93 | - |  | 91000 |  | Cash | Outright | - | - | - |  | - | Lot 2199, Jalan Nuri, Kampung Batu 9 Kebun Baru, 42500 Telok Panglima Garang, Selangor | - | - | N/A | 1 year | Full O&M - 1 year | EDCA
2308007 | EV Connection Sdn Bhd (The Pines Melaka) | 2023-11-15 | Simon | EV Charger | - | #VALUE! | 0 | 100 |  | 93380 |  | Cash | Outright | - | - | - |  |  | 33, Jalan Tun Sri Lanang, 75100 Melaka |  |  | N/A | 1 year
2311094 | Ching Kok Keong | 2023-11-30 | Chean Bang | R-PV | NEM | #VALUE! | 9.775 | - |  | 37000 |  | Self finance | Outright | Astronergy 575Wp | 17 | Solinteg MHT-8K-25 hybrid |  | 670428-11-5021 | Lot 10997, Jln Kenanga, Kg Sura Jeti, 23000 Dungun, Terengganu Darul Iman | 017-9767388 | ckkcsk6666@gmail.com | 3 years | 1 year
2311095 | Chu Yin Siong | 2023-11-25 | Chean Bang | R-PV | NEM | #VALUE! | 12.65 | - |  | 44600 |  | Self finance | Outright | Astronergy 575Wp | 22 | Solinteg MHT-10K-25 hybrid |  | 620818-11-5371 | No 11, Jln Paka, Tmn Bunga Raya, 23000 Dungun, Terengganu Darul Iman | 019-9836811 | cca6668@gmail.com | 3 years | 1 year
2311039 | DC Handal EV Charging Hub | 2024-01-06 | Simon | C&I-PV | SELCO | #VALUE! | 370.055 | - |  | 280080 | 46945 | Self finance | Outright | - | - | - |  | - | - | - | - | N/A | 1 year | N/A
2311012 | EV Connection Sdn Bhd (IOI Citymall, Putrajaya) | 2024-01-10 | Simon | EV Charger | - | #VALUE! | 0 | 240 |  | 109000 |  | Cash | Outright | - | - | - |  | - | - | - | - | N/A | 1 year
2311089 | Susan Lau Shiew Hung | 2023-11-30 | Simon | R-PV | NEM | #VALUE! | 11.5 | - |  | 37500 |  | Self finance | Outright | Astronergy 575Wp | 20 | GoodWe GW10K-SDT-20 |  | 821226-13-5150 | 27, Jalan SS 22A/8, Damansara Jaya, 47400 Petaling Jaya, Selangor Darul Ehsan | 012-2777019 | san99lau@gmail.com | 3 years | 1 year
2312118 | Dr Suntheresan A/L Ganapathy | 2024-01-05 | Ong | R-PV | NEM | #VALUE! | 13.8 | - |  | 54930 |  | Self finance | Outright | Astronergy 575Wp | 24 | Solinteg MHT-12K-25 hybrid |  | 680926-02-5351 | No 27, Jalan Aman Elemen 3, Bandar Tropicana Aman, 42500 Telok Panglima Garang, Selangor Darul Ehsan | 019-2262119 | sunthe26@gmail.com | 3 years | 1 year
2309070 | Saiful Lizan Bin Ibrahim | 2024-01-12 | Simon | R-PV | NEM | #VALUE! | 13.8 | - |  | 48902 |  | Credit Card Instalment | Outright | Astronergy 575Wp | 24 | Solinteg MHT-12K-25 hybrid |  | 731112-06-5749 | 16, Jalan Suadamai 6/2, Bandar Tun Hussein Onn, 43200 Cheras, Selangor Darul Ehsan | 019-2611759 | gunner2490@yahoo.com | 3 years | 1 year
2310075 | Chong Fong Chin(Jessie) | 2024-03-15 | Chean Bang | R-PV | NEM | #VALUE! | 14.625 | - |  | 45600 |  | Self finance | Outright | Astronergy 585Wp | 25 | Solinteg MHT-12K-25 hybrid |  | 861207-33-5276 | No 11, Lrg Bkt Setongkol Perdana 29, Perkpgn Bkt Setongkol, Tmn Bukit Setongkol, 25200 Kuantan, Pahang Darul Makmur | 019-9351188 | jessie.cfc@gmail.com |  | 1 year
2310076 | Loo Thiam Seng | 2025-02-19 | Tham | R-PV | NEM | #VALUE! | 8.26 | - |  | 24000 |  | Cash | Outright | Astronergy 590Wp | 14 | Huawei SUN2000-6KTL |  | 560426-07-5479 | 61, Jln Tasik Indah 2, Tmn Tasik Indah, 51200 WP Kuala Lumpur | 019-2263229 | tsloo1956@gmail.com | 3 years | 1 year
2310085 | Chew Mei May | 2024-04-21 | Simon | R-PV | NEM | #VALUE! | 12.075 | - |  | 47786 |  | Credit Card Instalment | Outright | Astronergy 575Wp | 21 | Solinteg MHT-10K-25 hybrid |  | 721025-10-5598 | 67, Jln BK 5B/5A, Bdr Kinrara, 47180 Puchong, Selangor Darul Ehsan | 012-2203402 | meimaychew@gmail.com | 3 years | 1 year
2312113 | Razman Bin Samsudin | 2024-01-22 | Simon | R-PV | NEM | #VALUE! | 13.8 | - |  | 44000 |  | Self finance | Outright | Astronergy 575Wp | 24 | Huawei SUN2000-12KTL |  | 760713-71-5025 | No.8, Jalan SS20/25, Damansara Utama, 47400 Petaling Jaya, Selangor | 019-3371313 | razmanbinsamsudin@gmailcom | 3 years | 1 year
2401121 | Chen Ah Hin | 2024-04-01 | Tham | R-PV | NEM | #VALUE! | 11.7 | - |  | 40000 |  | Self finance | Outright | Astronergy 585Wp | 20 | Solinteg MHT-10K-25 hybrid |  | 480824-10-5119 | Lot 1325-79B, Jalan Jinjang Damai 7, JinJang Utara, 52000 Kuala Lumpur | 019-3281707 | chen2.luma@gmail.com | 3 years | 1 year
2401124 | Lim Kok Teong | 2024-04-02 | Tham | R-PV | NEM | #VALUE! | 17.55 | - |  | 53708 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL |  | 790418-07-5747 | 3 Jalan Kenyalang 11/4E, PJU 5, Kota Damansara, 47810 Petaling Jaya, Selangor Darul Ehsan | 019-4134865 | cmjasonlim311@gmail.com | 3 years | 1 year |  | Unitrade
2401131 | Chan Po Kok (JC Chan KEB) | 2024-04-12 | Tham | R-PV | NEM | #VALUE! | 8.19 | - |  | 29500 |  | Self finance | Outright | Astronergy 585Wp | 14 | Huawei SUN2000-6KTL |  | 830506-14-6019 | 16, Jalan Sunville 4, Taman Sunville, 43000 Kajang, Selangor Darul Ehsan | 017-8786050 | cpokok0506@hotmail.com | 3 years | 1 year
2401137 | Lim Kok Liang | 2024-04-02 | Tham | R-PV | NEM | #VALUE! | 11.7 | - |  | 40900 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL |  | 830112-02-5169 | 1, Jalan Metafasa, U16/160. Elmina West, Seksyen U16, 40160, Shah Alam , Selangor Darul Ehsan | 016-2173777 | steelmerchantssb@gmail.com | 3 years | 1 year
2401147 | Susan Sung Fong Thieng | 2024-04-02 | Tham | R-PV | NEM | #VALUE! | 11.7 | - |  | 40440 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL |  | 691205-12-5030 | 37, Southlake Terraces, Jalan Denai Selatan 5, Desa Parkcity. 52200 Kuala Lumpur | 012-2393003 | susansung37@gmail.com | 3 years | 1 year |  | Unitrade
2403165 | Lee Boon Huet | 2024-04-01 | Tham | R-PV | NEM | #VALUE! | 7.02 | - |  | 24600 |  | Cash | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 720825-05-5109 | 31, Jln Cassia 4, Bdr Botanic, 41200 Klang, Selangor Darul Ehsan | 012-2045618 | blee@fp-group.com | 3 years | 1 year
2403167 | Ng Yunn Chong | 2024-03-24 | Tham | R-PV | NEM | #VALUE! | 17.55 | - |  | 47500 |  | Self finance | Outright | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL |  | 620205-08-6037 | 97, Jalan Selasar Rokam 11, Kampung Sri Ampang, 31350 Ipoh, Perak Darul Ridzuan | 012-5127295 | ngyunnchong123@gmail.com | 3 years | 1 year
2403170 | Wong Hoon Sang | 2024-03-16 | Tham | R-PV | NEM | #VALUE! | 10.53 | - |  | 35600 |  | Self finance | Outright | Astronergy 585Wp | 18 | Solinteg MHT-8K-25 hybrid |  | 630220-10-7149 | 75, Jalan Uranus U5/122B, Seksyen U5, 40150 Shah Alam. Selangor Darul Ehsan | 014-9159789 | wonghoonsang@gmail.com | 3 years | 1 year
2403177 | Nor Aini binti Mohd Ashari | 2024-03-25 | Tham | R-PV | NEM | #VALUE! | 4.68 | - |  | 20000 |  | Self finance | Outright | Astronergy 585Wp | 8 | Huawei SUN2000-4KTL-L1 |  | 731105-08-6402 | No 61, Jln Sigma U6/16A, Sek U6 (Taman Subang Permata), 40150 Subang, Selangor Darul Ehsan | 011-28584486 | norazam4446@yahoo.com.sg | 3 years | 1 year |  | Bioserasi
2403189 | Lai Kim Soon (Stella) | 2024-03-29 | Chean Bang | R-PV | NEM | #VALUE! | 7.02 | - |  | 27500 |  | Self finance | Outright | Astronergy 585Wp | 12 | Solinteg MHS-5K-30 hybrid |  | 910301-06-5675 | No 36, Lrg Seri Teruntum 13, Tmn Sri Teru, Tanah Putih, 25200 Kuantan. Pahang Darul Makmur | 011-55090155 | miiao_maomao520@hotmail.com | 3 years | 1 year
2403190 | Tan Poh Poh | 2024-03-27 | Chean Bang | R-PV | NEM | #VALUE! | 7.02 | - |  | 21000 |  | Self finance | Outright | Astronergy 585Wp | 12 | Solinteg MHS-5K-30 hybrid |  | 710625-08-5224 | 6, Lrg Seri Setali, 115 Off Jln Air Putih, Air Putih, 25300 Kuantan, Pahang Darul Makmur | 012-9831939 | may014215@gmail.com | 3 years | 1 year
2403197 | Leau Koo Sien (Eric) | 2024-03-29 | Chean Bang | R-PV | NEM | #VALUE! | 16.38 | - |  | 48600 |  | Self finance | Outright | Astronergy 585Wp | 28 | Solinteg MHT-12K-25 hybrid |  | 740722-06-5097 | No 12A, Lorong Pelindung 95, Perumahan Pelindung, 25050 Kuantan, Pahang Darul makmur | 019-9270778 | Leaueric@gmail.com | 3 years | 1 year
2403197-1 | Koon Kok Leong | 2024-04-01 | Tham | R-PV | NEM | #VALUE! | 7.02 | - |  | 27237.2 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 741008-01-5759 | No 80, Lrg Delima 5/KS6, Bdr Parklands, Pandamar, 42000 Klang, Selangor Darul Ehsan | 012-3988909 | klkoon8882@gmail.com | 3 years | 1 year
2404206 | Wong Wai Kwong | 2024-04-04 | Chean Bang | R-PV | NEM | #VALUE! | 8.19 | - |  | 31000 |  | Cash + instalment | Outright | Astronergy 585Wp | 14 | Huawei SUN2000-6KTL |  | 790114-06-5467 | No 55, Lrg Im 1/41, Tmn Putra Aman, 25200 Bandar Indera Mahkota, Pahang Darul Makmur | 016-9233066 | ww_kwong@yahoo.com.sg | 3 years | 1 year
2404226 | Jimmy Kok Aik Lim | 2024-04-14 | Tham | R-PV | NEM | #VALUE! | 7.02 | - |  | 25100 |  | Self finance | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 621013-11-5109 | 3 Jalan Telawi 7, Bangsar Baru, Bangsar,59100 Kuala Lumpur, WP Kuala Lumpur | 012-3709905 | lytan63@hotmail.com | 3 years | 1 year
2401063 | Weller Air-Cond Parts Enterprise Sdn Bhd | 2024-03-12 | Tham | C&I-PV | NEM | #VALUE! | 26.91 | - |  | 82000 |  | Self finance | Outright | Astronergy 585Wp | 46 | Huawei SUN2000-20KTL |  |  | Lot 8324, Kg Makau Bt 1, 43100 Hulu Langat, Selangor |  |  | 3 years | 1 year
2401069 | Enviri Industries Sdn Bhd | 2024-03-29 | Tham | C&I-PV | NEM | #VALUE! | 290.4 | - |  | 668000 | 2610 | Self finance | Outright | Jinko Solar 575Wp | 505 | Huawei SUN2000-100KTL x 2 Huawei SUN2000-36KTL x 1 |  |  | PT71179, Jalan Lapis 2, 42100 Klang, Selangor |  |  | 3 years | 1 year
2402079 | Intergreen Holdings Sdn Bhd | 2024-04-12 | Tham | C&I-PV | NEM | #VALUE! | 46.8 | - |  | 194600 |  | Self finance | Outright | Astronergy 585Wp | 80 | Huawei SUN2000-12KTL-M5 x 2 Huawei SUN2000-12KTL-MB0 x 1 |  |  | Pusat Perdagangan Amcorp, 3, Jalan Timur, Seksyen 9, 46000 Petaling Jaya, Selangor |  |  | 3 years | 1 year
2402080 | CK Fresh Sdn Bhd | 2024-03-06 | Tham | C&I-PV | SELCO | #VALUE! | 43.29 | - |  | 120000 | 1500 | Self finance | Outright | Astronergy 585Wp | 74 | Huawei SUN2000-30KTL |  |  | Lot 8393, Jln Air Hitam, Kelapa Sawit, 81000 Kulai, Johor |  |  | 3 years | 1 year
2312120 | Ling Duon Kwan | 2024-04-08 | Tham | R-PV | NEM | #VALUE! | 7.605 | - |  | 27500 |  | Self finance | Outright | Astronergy 585Wp | 13 | Huawei SUN2000-6KTL |  | 780817-13--5437 | No 58, Jln TP 1/3, Tiara Putra, 47000 Sungai Buloh, Selangor Darul Ehsan | 012-3799638 | duncanling@yahoo.com | 3 years | 1 year
2311092 | Tham Chee Man | 2023-11-23 | Tham | R-PV | NEM | #VALUE! | 5.75 | - |  | 22000 |  | Self finance | Outright | Astronergy 575Wp | 10 | Solinteg MHS-5K-30 hybrid |  | 590601-06-5153 | 33, Jalan Flora 3, Saujana Utama, 47000 Sungai Buloh, Selangor Darul Ehsan | 017-9034540 | thamcheongsheng@gmail.com | 3 years | 1 year
2404230 | Yap Bee Im Marianne | 2024-04-20 | Tham | R-PV | NEM | #VALUE! | 8.775 | - |  | 32500 | -2000 | Self finance | Outright | Astronergy 585Wp | 15 | Huawei SUN2000-8KTL |  | 831021-14-6242 | No 8, Jln Hijau Alam U9/14C, Cahaya SPK, Sek U9, 40150 Shah Alam, Selangor Darul Ehsan | 012-3050288 | marianneyap21@gmail.com | 3 years | 1 year
2401133 | Cheong Sau Ling | 2024-04-22 | Tham | R-PV | NEM | #VALUE! | 8.775 | - |  | 34460 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 15 | Huawei SUN2000-8KTL |  | 740823-02-5825 | 15, Jalan Kemuning Bayu 33/32L, Kemuning Utama,40400 Shah Alam, Selangor Darul Ehsan | 013-7274135 | lingling822@hotmail.my | 3 years | 1 year
2403171 | Sim Keng Chor | 2024-04-22 | Tham | R-PV | NEM | #VALUE! | 17.55 | - |  | 52400 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL |  | 470725-01-5629 | 8, Lorong Kemaris 6, Bangsar Baru, 59100 Kuala Lumpur, WP Kuala Lumpur | 012-2789488 | simson@unitrade.com.my | 3 years | 1 year |  | Unitrade
2403176 | Nor Hana binti Supiran @ Soviran | 2024-04-24 | Tham | R-PV | NEM | #VALUE! | 6.435 | - |  | 30500 |  | Self finance | Outright | Astronergy 585Wp | 11 | Huawei SUN2000-5KTL-M1 |  | 801003-08-5944 | Lot 84327, Lorong Merbau 1, Kampung Melayu, 68000 Ampang, Selangor Darul Ehsan | 019-3170725 | hanatrading78@yahoo.com | 3 years | 1 year |  | Bioserasi
2404229 | Ng Lay Ping | 2024-04-25 | Tham | R-PV | NEM | #VALUE! | 14.625 | - |  | 41600 | -1600 | Self finance | Outright | Astronergy 585Wp | 25 | Huawei SUN2000-12KTL | 15 years | 700919-10-5236 | Lot 27838, Jln BRP 2/2C, Bkt Rahman Putra, 40160 Sungai Buloh, Selangor Darul Ehsan | 012-3999903 | lpng_lew@yahoo.com | 3 years | 1 year |  |  |  | Inverter Warranty Extend to 15 years
2404211 | Nor Fadillah | 2024-04-26 | Tham | R-PV | NEM | #VALUE! | 17.55 | - |  | 49600 |  | Self finance | Outright | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL |  | 630327-04-5398 | 17, Jalan Laman Jasmin 5A, Laman Jasmin, 71800 Nilai Negeri Sembilan Darul Khusus | 016-2477797 | drnorfadillah@gmail.com | 3 years | 1 year
2404111 | Budi Jelas Sdn Bhd | 2024-04-25 | Tham | C&I-PV | NEM | #VALUE! | 26.91 | - |  | 81000 |  | Self finance | Outright | Astronergy 585Wp | 46 | Huawei SUN2000-20KTL |  |  | PT 12887, Kaw Asan Perindustrian LKNP Benus, 28700 Bentong, Pahang |  |  | 3 years | 1 year
2404219 | Billy Teoh Wee Wei | 2024-04-30 | Tham | R-PV | NEM | #VALUE! | 17.55 | - |  | 52000 |  | Cash + instalment | Outright | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL |  | 830811-07-5405 | No 5082, Lrg Bagan Vista, Jln Telaga Air, 12200 Butterworth Pulau Pinang | 012-4215656 | billyteoh19@hotmail.com | 3 years | 1 year |  | Unitrade
2404214 | Teo En Chie | 2024-05-02 | Tham | R-PV | NEM | #VALUE! | 15.795 | - |  | 48200 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 27 | Huawei SUN2000-12KTL |  | 910530-01-6505 | 18, Jalan Senibong 1, Teluk Senibong, 81750 Masai, Johor Darul Takzim | 010-8820636 | enchie@live.com.my | 3 years | 1 year |  | Unitrade
2403102 | Sleep Matics (Asia) Sdn Bhd | 2024-05-03 | Tham | C&I-PV | NEM | #VALUE! | 374.4 | - |  | 744800 |  | Self finance | Outright | Astronergy 585Wp | 640 | Huawei SUN2000-115KTL x 2 Huawei SUN2000-50KTL x 1 |  |  | Lot 37133, Kg Baru Sg Buloh, 47000 Sungai Buloh, Selangor |  |  | N/A | 1 year |  | Unitrade
2312059 | CHL Foam Industries Sdn Bhd | 2024-05-03 | Tham | C&I-PV | NEM | #VALUE! | 345.15 | - |  | 690300 | 130000 | Self finance | Outright | Astronergy 585Wp | 590 | Huawei SUN2000-115KTL x 2 Huawei SUN2000-30KTL x 1 |  |  | Lot 37174, Kg Baru Sg Buloh, 47000 Sungai Buloh, Selangor |  |  | N/A | 1 year |  | Unitrade
2404255 | Ong Pui Fen | 2024-05-12 | Tham | R-PV | NEM | #VALUE! | 7.605 | - |  | 30260 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 13 | Huawei SUN2000-6KTL |  | 760801-04-5180 | 51, Jalan USJ 2/5H, USJ 2, 47600 Subang Jaya, Selangor Darul Ehsan | 016-2100039 | tattmun@gmail.com | 3 years | 1 year
2404242 | Chua Boon Seng | 2024-04-26 | Azra | R-PV | NEM | #VALUE! | 10.53 | - |  | 35000 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 21 | Huawei SUN2000-8KTL |  | 750927-06-5137 | No 1B, Lrg Seri Kuantan 28/1, Kuantan Garden, 25300 Kuantan, Pahang Darul Makmur | 018-9094538 | cboonhuang@gmail.com | 3 years | 1 year
2405272 | Chan Hui Li | 2024-05-15 | Tham | R-PV | NEM | #VALUE! | 9.36 | - |  | 32180 |  | Self finance | Outright | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL |  | 700521-06--5318 | No 111, Lrg Air Putih 21, Jln Air Putih, Tmn Dahlia Astana, 25350 Kuantan, Pahang Darul Makmur | 012-2392000 | conniechan2105@yahoo.com | 3 years | 1 year |  | Unitrade
2405266 | Goh Wee Bang (Goh Swee Teng) | 2024-05-20 | Tham | R-PV | NEM | #VALUE! | 13.455 | - |  | 41000 |  | Self finance | Outright | Astronergy 585Wp | 23 | Huawei SUN2000-10KTL |  | 750605-10-5255 | No 12A, Jln Cokmar 2 K, Tmn Mutiara Bkt Raja, 41050 Klang, Selangor Darul Ehsan | 012-2313922 | vbangoh1975@gmail.com | 3 years | 1 year
2405280 | Teoh Kah Ming | 2024-05-10 | Tham | R-PV | NEM | #VALUE! | 9.36 | - |  | 34600 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL |  | 880326-14-5807 | No 5, Jln Kemuning Indah 32/141J, Kemuning Utama, 40460 Shah Alam, Selangor Darul Ehsan | 012-6777309 | kahming.teoh@gmail.com | 3 years | 1 year
2405294 | Gan Wei Kuan | Cancelled | Tham |  |  |  | 7.02 | - |  | 25100 |  | Self finance | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | [5 empty] | 3 years | 1 year
2405296 | Haiu Chan Lai | 2024-05-02 | Tham | R-PV | NEM | #VALUE! | 8.775 | - |  | 32000 |  | Self finance | Outright | Astronergy 585Wp | 15 | Huawei SUN2000-8KTL |  | 670120-11-5324 | 41, Jln Daun Inai 7, Sunway SPK Damansara, 52200 Kuala Lumpur, WP Kuala Lumpur | 012-3760333 | jacquelinehaiu@gmail.com | 3 years | 1 year |  | Unitrade
2405307 | Shreeram Nadarajah | 2024-05-22 | Tham | R-PV | NEM | #VALUE! | 8.19 | - |  | 28000 | 4600 | Self finance | Outright | Astronergy 585Wp | 14 | Huawei SUN2000-6KTL |  | 760726-14-5391 | 123, Jalan Terasek 1, Bangsar Baru, Bangsar, 59100 Kuala Lumpur, WP Kuala Lumpur | 019-2619729 | shreeram.nadarajah@gmail.com | 1 year | 1 year |  | Unitrade
2404227 | Datin Tai Bee Choon | 2024-05-30 | Tham | R-PV | NEM | #VALUE! | 17.55 | - |  | 52400 |  | Self finance | Outright | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL |  | 760817-01-5584 | No 16, Jln Setia Tropika 15/1, Tmn Setia Tropika, 81200 Johor Bahru. Johor Darul Takzim | 013-8222255 | datoivan@ungguhgroup.com | 3 years | 1 year |  | Unitrade
2405315 | Yeap Say Woei | 2024-06-03 | Tham | R-PV | NEM | #VALUE! | 13.455 | - |  | 40000 |  | Self finance | Outright | Astronergy 585Wp | 23 | Huawei SUN2000-10KTL |  | 800117-02-5697 | 10, Bukit Dumbar Residences, Lorong Batu Gajah, 11600 Jelutong, Pulau Pinang | 012-4776246 | saywoei@yahoo.com | 3 years | 1 year |  | Unitrade
2405319 | Tan Zhi Cheng | 2024-06-02 | Tham | R-PV | NEM | #VALUE! | 7.02 | - |  | 26240 |  | Self finance | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 840518-09-5203 | 15, Jalan BK 2/7, Bandar Kinrara, 47180 Puchong, Selangor Darul Ehsan | 016-4010372 | tzcheng07@gmail.com | 3 years | 1 year |  | Unitrade
2405288 | Teh Siew Eng | 2024-05-28 | Tham | R-PV | NEM | #VALUE! | 12.285 | - |  | 41840 |  | Self finance | Outright | Astronergy 585Wp | 21 | Huawei SUN2000-10KTL |  | 531030-08-5440 | No 49, Jln Kasipillay, 51200 Kuala Lumpur, WP Kuala Lumpur | 012-2290951 | fattychuah@gmail.com | 3 years | 1 year |  | Unitrade
2404256 | Lai Chun Wai | 2024-06-21 | Azra | R-PV | NEM | #VALUE! | 8.775 | - |  | 33100 |  | Self finance | Outright | Astronergy 585Wp | 14 | Solinteg MHT-8K-25 hybrid |  | 711015-14-5159 | No 31, Lrg Sri Kuantan 55, Tmn Timur, 25150 Kuantan, Pahang Darul Makmur | 012-3879932 | chunwai103@gmail.com | 3 years | 1 year
2406323 | Tay Poh Chai | 2024-06-14 | Tham | R-PV | NEM | #VALUE! | 14.04 | - |  | 40000 |  | Self finance | Outright | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL |  | 730209-04-5037 | 53, Jalan Saujana Duta 7, Saujana Duta, Seremban 2 Heights, 70300 Seremban, Negeri Sembilan Darul Khusus | 019-6616826 | alextaypohchai@hotmail.com | 3 years | 1 year
2406336 | Alex How Chee Keong | 2024-06-19 | Tham | R-PV | NEM | #VALUE! | 11.7 | - |  | 31000 |  | Self finance | Outright | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL |  | 770202-14-5437 | Unit 16, Zenia Jalan Residen 2, Desa Parkcity, 52200 Kuala Lumpur, WP Kuala Lumpur | 012-3453457 | keongko@hotmail.com | 1 year | 1 year |  | Unitrade
2406340 | How Mei Cheng | 2024-06-21 | Tham | R-PV | NEM | #VALUE! | 7.02 | - |  | 24100 |  | Self finance | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 811203-14-5656 | 2-134, Jalan Udang Ketak, Taman Sri Segambut, 52000 Kuala Lumpur, WP Kuala Lumpur | 012-2012123 | joe_hmc@hotmail.com | 3 years | 1 year |  | Unitrade
2406355 | Windy Ng | 2024-06-28 | Tham | R-PV | NEM | #VALUE! | 9.36 | - |  | 27000 | -1872 | Self finance | Outright | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL |  | 820717-01-5204 | 13, Jalan U13/53H, Eco Ardence, Seksyen U13, 40170 Shah Alam, Selangor Darul Ehsan | 017-7753119 | yellowwindy@hotmail.com | N/A | 1 year
2406357 | Zainuddin Zin | 2024-06-28 | Patricia | R-PV | NEM | #VALUE! | 12.285 | - |  | 38000 |  | Self finance | Outright | Astronergy 585Wp | 21 | Huawei SUN2000-10KTL |  | 590911-06-5319 | 8, Lrg Kg Panching 10, Kg Panching, 26090 Kuantan, Pahang Darul Makmur | 019-9774850 | zainudinzin@gmail.com | 5 years | 1 year
2405019 | Handal Green Mobility Sdn Bhd (Encore Melaka) | 2024-06-20 | Simon | EV Charger | - | #VALUE! | 0 | 240 |  | 90800 |  | Cash | Outright | - | - | - |  | - | No 3, Jalan KSB - Impression 8, Impression City @ Kota Syahbandar, 75200 Melaka | - | - | N/A | 1 year
2406358 | Kwan Li Shan | 2024-07-01 | Tham | R-PV | NEM | #VALUE! | 9.36 | - |  | 30000 |  | Self finance | Outright | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL |  | 800718-08-5978 | Lot 387509, Laluan Sri Ampang 2, Kampung Sri Ampang, 31350 Ipoh, Perak Darul Ridzuan | 012-5142483 | lishankwan@gmail.com | 3 years | 1 year
2407360 | Liau Hui Kiem | 2024-07-18 | Tham | R-PV | NEM | #VALUE! | 14.04 | - |  | 45020 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL |  | 780419-10-5734 | 20, Jalan Setia Damai U13/15F, Setia Alam 40170 Shah Alam, Selangor Darul Ehsan | 019-2338688 | hkliau8688@gmail.com | 3 years | 1 year
2407364 | Mohd Nasir Man | 2024-07-08 | Patricia | R-PV | NEM | #VALUE! | 8.19 | - |  | 25000 |  | Self finance | Outright | Astronergy 585Wp | 14 | Huawei SUN2000-6KTL |  | 640103-09-5029 | No B3075, Jln Beserah, Tmn Multiply, 25300 Kuantan, Pahang Darul Makmur | 012-9003767 | mnasirman17@gmail.com | N/A | 1 year
2407375 | Tan Ger Ber | 2024-07-12 | Tham | R-PV | NEM | #VALUE! | 14.04 | - |  | 39980 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL |  | 560608-01-6090 | 10, Jalan Kenyalang 11/15G, Seksyen 11, Kota Damansara, 47810, Petaling Jaya, Selangor Darul Ehsan | 012-5273664 | tangerber@gmail.com | 3 years | 1 year |  | Unitrade
2407379 | Ng Boon Kiat (Daniel) | 2024-07-11 | Chean Bang | R-PV | NEM | #VALUE! | 5.265 | - |  | 22860 |  | Cash + Credit Card Instalment | Outright | Astronergy 585Wp | 9 | Solinteg MHS-5K-30 hybrid |  | 840903-01-5679 | No 4, Jalan KS 14/12, Kota Sultan Ahmad Shah, 25200 Kuantan, Pahang | 012-6121112 | danielngbk84@gmail.com | N/A | 1 year
2407380 | How Yee Seun | 2024-07-13 | Tham | R-PV | NEM | #VALUE! | 12.87 | - |  | 38000 |  | Self finance | Outright | Astronergy 585Wp | 22 | Huawei SUN2000-10KTL |  | 840202-06-5008 | 32A, Jalan Aman Arahsia 7, Bandar Tropicana Aman, 42500 Telok Panglima Garang, Selangor Darul Ehsan | 012-9370766 | yeesuen02@yahoo.com | 3 years | 1 year |  | Unitrade
2407381 | Lau Ah Leng | 2024-07-13 | Tham | R-PV | NEM | #VALUE! | 12.285 | - |  | 36680 |  | Self finance | Outright | Astronergy 585Wp | 21 | Huawei SUN2000-10KTL |  | 550425-02-5403 | 19, Jln Kenyalang 11/15I, Seksyen 11, Kota Damansara, 47810 Petaling Jaya, Selangor Darul Ehsan | 019-3128863 | allan@gmail.com | 3 years | 1 year |  | Unitrade
2407382 | Leong Tack Ming | 2024-07-15 | Tham | R-PV | NEM | #VALUE! | 8.775 | - |  | 29840 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 15 | Huawei SUN2000-8KTL |  | 530501-05-5607 | 3, Jalan SS 22/24, Damansara jaya. 47400 Petaling Jaya, Selangor | 012-2011132 |  | 3 years | 1 year |  | Unitrade
2407383 | Charles Lew Chow Leng | 2024-07-15 | Tham | R-PV | NEM | #VALUE! | 14.04 | - |  | 39980 |  | Self finance | Outright | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL |  | 620529-07-5406 | 6, Jalan Kenyalang 11/15A, Seksyen 11, Kota Damansara, 47810 Petaling Jaya, Selangor Darul Ehsan | 012-3999189 | clew62@gmail.com | 3 years | 1 year |  | Unitrade
2407384 | Loh Fook Khew | 2024-07-15 | Tham | R-PV | NEM | #VALUE! | 12.285 | - |  | 36800 |  | Self finance | Outright | Astronergy 585Wp | 21 | Huawei SUN2000-10KTL |  | 560512-08-5307 | 8, Jalan Kenyalang 11/15A, Seksyen 11, Kota Damansara, 47810 Petaling Jaya, Selangor Darul Ehsan | 012-3351801 | chinmei_fashion@hotmail.com | 3 years | 1 year |  | Unitrade
2407385 | Cheong Chin Meng | 2024-07-15 | Chean Bang | R-PV | NEM | #VALUE! | 15.21 | - |  | 45600 |  | Self finance | Outright | Astronergy 585Wp | 26 | Solinteg MHT-12K-25 hybrid |  | 730422-06-5301 | 145, Jln Bkt Setongkol 3, Tmn Muhibah FAS, Bukit Setongkol, 25200 Kuantan, Pahang Darul Makmur | 012-9103893 | ioienterprisektn@gmail.com | 3 years | 1 year
2310035 | Advantic Nutraceuticals | 2025-05-16 | Tham | C&I-PV | NEM | #VALUE! | 87.84 | - |  | 188000 |  | Self finance | Outright | Astronergy 610Wp | 144 | Huawei SUN2000-30KTL + Huawei SUN2000-36KTL | [5 empty] | 3 years | 1 year | Full O&M - 3 years
2403088 | Chua Tong Hin Hardware Sdn Bhd | 2024-07-17 | Tham | C&I-PV | NEM | #VALUE! | 37.44 | - |  | 98000 |  | Self finance | Outright | Astronergy 585Wp | 64 | Huawei SUN2000-30KTL |  |  | Lot 37679, Jln 3/37A, Tmn Bukit Maluri Kepong, 52100 Kuala Lumpur |  |  | 3 years | 1 year
2407157 | NMSY Capital Sdn Bhd (Mohd Nasir) | 2024-07-08 | Patricia | C&I-PV | NEM | #VALUE! | 18.72 | - |  | 52000 |  | Self finance | Outright | Astronergy 585Wp | 32 | Huawei SUN2000-17KTL |  |  | N-1332, G Floor, Jln Tg Lumpur, 26060 Kuantan, Pahang |  |  | N/A | 1 year
2312116 | Chua Ling Ling | 2024-06-18 | Tham | R-PV | NEM | #VALUE! | 11.7 | - |  | 32540 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL |  | 760115-14-5448 | 132A, Jln Desa Residen, Desa Parkcity, 52200 Kuala Lumpur, WP Kuala Lumpur | 011-11428999 | llchua00@hotmail.com | 1 year | 1 year |  | Unitrade
2407388 | Yeo Chen Kok | 2024-07-19 | Tham | R-PV | NEM | #VALUE! | 12.285 | - |  | 34600 |  | Cash | Outright | Astronergy 585Wp | 21 | Huawei SUN2000-10KTL |  | 830625-07-5049 | 10, Jln Hujan Emas 11, Overseas Union Garden, 58200 Kuala Lumpur, WP Kuala Lumpur | 012-9283828 | yeochenkok@gmail.com | 3 years | 1 year |  | Unitrade
2407386 | Amirluddin bin Awang | 2024-07-21 | Chean Bang | R-PV | NEM | #VALUE! | 12.285 | - |  | 38000 |  | Self finance | Outright | Astronergy 585Wp | 21 | Solinteg MHT-10K-25 hybrid |  | 671111-11-5079 | No 8, Lorong Im 11/10, Mahkota Heights, 25200 Kuantan, Pahang Darul Makmur | 012-7992686 | tidzariah@gmail.com | N/A | 1 year
2403158 | Ong Gin Chin | 2024-07-22 | Tham | R-PV | NEM | #VALUE! | 7.02 | - |  | 23500 | -1404 | Self finance | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 600218-01-5432 | 9, Jalan Anggerik Liparis 31/152, Kota Kemuning, 40460 Shah Alam, Selangor Darul Ehsan | 016-2792625 | cyschin@hotmail.com | 3 years | 1 year |  | Unitrade
2404220 | Ng Seow Fong | 2024-07-18 | Tham | R-PV | NEM | #VALUE! | 7.02 | - |  | 23500 | -1404 | Self finance | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 790812-14-5854 | 21, Jalan Suria 6, Taman Suria, 43000 Kajang, Selangor Darul Ehsan | 012-2624548 | esther@unitrade.com.my | 3 years | 1 year |  | Unitrade
2403202 | Chuah Teah Soo | 2024-07-24 | Tham | R-PV | NEM | #VALUE! | 10.53 | - |  | 31000 |  | Self finance | Outright | Astronergy 585Wp | 18 | Huawei SUN2000-8KTL |  | 500224-08-5017 | No 11, PT 28561, Jalan Bukit Indah, Taman Bukit Indah, 27600 Raub, Pahang Darul Makmur | 019-9867505 | sykt_pern_chuah@yahoo.com.my | 3 years | 1 year
2407392 | Ecila Sim Ju-Inn | 2024-07-24 | Tham | R-PV | NEM | #VALUE! | 11.7 | - |  | 36680 | -2340 | Self finance | Outright | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL |  | 781228-14-5762 | 49, Jalan Duta Villa 1, Setia Alam, 40170 Shah Alam, Selangor Darul Ehsan | 019-6668520 | juinn@unitrade.com.my | 3 years | 1 year |  | Unitrade
2404232 | Wong Yoke Chon | 2024-06-25 | Tham | R-PV | NEM | #VALUE! | 7.02 | - |  | 25000 |  | Self finance | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 740422-08-5002 | 368, Jalan Tasek Permai, Kampung Tasek Permai, 68000 Ampang, Selangor Darul Ehsan | 016-2081788 | traceywong92@gmail.com | 3 years | 1 year |  | Unitrade
2407397 | Foo Su Hoong | 2024-07-25 | Tham | R-PV | NEM | #VALUE! | 15.21 | - |  | 39600 |  | Self finance | Outright | Astronergy 585Wp | 26 | Huawei SUN2000-12KTL |  | 640115-10-5474 | 3, Jln Kenyalang 11/15D, Seksyen 11, Kota Damansara, 47810 Petaling Jaya, Selangor Darul Ehsan | 012-3739780 | suhoongfoo@gmail.com | 3 years | 1 year |  | Unitrade
2404250 | Wan Johan Bin Rahim | 2024-07-29 | Tham | R-PV | NEM | #VALUE! | 17.55 | - |  | 50320 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL |  | 860724-43-6847 | 12A, Jalan Setia Tropika U13/20B, Setia Alam, 40170 Shah Alam, Selangor Darul Ehsan | 012-3906522 | aminrahim@msn.com | 3 years | 1 year
2407399 | Koo Woon Kee | 2024-07-26 | Tham | R-PV | NEM | #VALUE! | 10.53 | - |  | 31000 |  | Cash | Outright | Astronergy 585Wp | 18 | Huawei SUN2000-8KTL |  | 540804-10-6087 | 50B, Jln Merah Mawar Tujuh U9/6G, Cahaya SPK, Sek U9, 40150 Shah Alam, Selangor Darul Ehsan | 012-2426698 | koowoonkee@gmail.com | 3 years | 1 year |  |  | Exc Smart Meter
2407394 | Nor Aini binti Mat Saman (Nazrul Latif) | 2024-07-31 | Patricia | R-PV | NEM | #VALUE! | 7.02 | - |  | 24100 |  | Self finance | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 760923-08-6124 | No 49, Lorong Pinggiran Putra 3/122, Pinggiran Putra 3, 26060 Kuantan, Pahang | 019-9598431 |  | 3 years | 1 year
2407397-1 | Teo Kai Yun | 2024-08-02 | Tham | R-PV | NEM | #VALUE! | 15.21 | - |  | 39600 |  | Self finance | Outright | Astronergy 585Wp | 26 | Huawei SUN2000-12KTL |  | 950515-05-5334 | 138, Lorong Warisan Villa 2/3, Taman Warisan Villa, 71800 Nilai, Negeri Sembilan Darul Khusus | 012-2531773 | allyssa_pinky@hotmail.com | 3 years | 1 year |  | Unitrade
2312114 | Chua Teng Teng | 2024-06-18 | Tham | R-PV | NEM | #VALUE! | 11.7 | - |  | 31000 |  | Self finance | Outright | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL |  | 771115-14-5820 | 130, Jln Desa Residen, Desa Parkcity, 52200 Kuala Lumpur, WP Kuala Lumpur | 012-3354488 | ttchua77@hotmail.com | 1 year | 1 year |  | Unitrade
2401123 | Lee Yoon Huat | 2024-07-05 | Tham | R-PV | NEM | #VALUE! | 12.285 | - |  | 36500 |  | Cash | Outright | Astronergy 585Wp | 21 | Huawei SUN2000-10KTL |  | 780620-05-5273 | No 18, Jln Jalil Perkasa 19, Tmn Esplanad, 57100 Bukit Jalil, WP Kuala Lumpur | 016-2226469 | thomas119@hotmail.com | 3 years | 1 year |  | Unitrade
2404207 | Tan Boon Siang (Han Father) | 2024-05-20 | Tham | R-PV | NEM | #VALUE! | 7.02 | - |  | 26240 | -1404 | Cash | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 610216-02-5417 | 360, Tmn Saga Jln Alor Mengkudu, 05400 Alor Setar, Kedah Darul Aman | 017-4732831 | boon.siang@hotmail.com | 3 years | 1 year |  | Unitrade
2408402 | Tee Cheong Tuan | 2024-08-05 | Tham | R-PV | NEM | #VALUE! | 12.87 | - |  | 43000 |  | Cash | Outright | Astronergy 585Wp | 22 | Huawei SUN2000-10KTL |  | 621029-06-5273 | No 3, Jln BK 6A/2A, Bandar Kinrara, 47100 Puchong, Selangor | 012-3290810 | tuantee2010@gmail.com | 3 years | 1 year
2407372 | Dato Tay Tong Ben | 2024-08-06 | Tham | R-PV | NEM | #VALUE! | 14.04 | - |  | 37600 |  | Cash | Outright | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL |  | 900522-01-5829 | 15, PTD207737, Jalan Danga Sutera 12/3, Taman Danga Sutera, 81300 Johor Bahru, Johor Darul Takzim | 016-7132622 | legendtay@hotmail.com | 3 years | 1 year |  | Unitrade
2405298 | Lim Choon Huat | 2024-07-26 | Tham | R-PV | NEM | #VALUE! | 11.7 | - |  | 35960 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL |  | 820818-01-6265 | 64, Jalan Eko Botani 1/9, Taman Eko Botani, 79100 Iskandar Puteri, Johor Darul Takzim | 012-7731700 | otakibc@gmail.com | 3 years | 1 year |  | Unitrade
2408404 | Ong Ling Gee | 2024-08-11 | Tham | R-PV | NEM | #VALUE! | 7.02 | - |  | 24680 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 690508-01-5643 | 57, Jln Melawati Tmn Melawati, 83700 Yong Peng, Johor Darul Takzim | 013-7448833 | onglinggee@yahoo.com | 3 years | 1 year |  | Unitrade
2408401 | Kuek Soon Yeam | 2024-08-08 | Tham | R-PV | NEM | #VALUE! | 7.02 | - |  | 22500 |  | Cash | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 560722-10-6137 | No 95, Jln Hujan Bubuk, Overseas Union Garden, 58200 Kuala Lumpur, WP Kuala Lumpur | 012-3107766 | danielkuek56@hotmail.com | 3 years | 1 year
2408398 | Yap Siok Ching | 2024-08-15 | Tham | R-PV | NEM | #VALUE! | 11.7 | - |  | 36680 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL |  | 620404-10-6408 | No 33, Lrg Burhanuddin Helmi 1, Tmn Tun Dr Ismail, 60000 Kuala Lumpur, WP Kuala Lumpur | 017-2783248 | ginayap@gmail.com | 3 years | 1 year |  | Unitrade
2408415 | Shahrin Merican | 2024-08-21 | Tham | R-PV | NEM | #VALUE! | 17.55 | - |  | 45600 |  | Cash | Outright | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL |  | 610228-71-5001 | 36, Jalan Lanai Kiara, Taman Sri Hartamas, 50480 Kuala Lumpur | 012-2967681 | sitiomar19@yahoo.com | 3 years | 1 year |  | Unitrade
2408425 | Chua Shen Huat | 2024-08-27 | Tham | R-PV | NEM | #VALUE! | 14.04 | - |  | 43100 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL |  | 600508-11-5247 | PT PT 26137, Jln USJ 3D/6, USJ Avenue, 47500 Subang Jaya, Selangor | 013-2767764 | shchua60@hotmail.com | 3 years | 1 year
2406334 | Yap Kee Leong | 2024-08-27 | Tham | R-PV | NEM | #VALUE! | 14.04 | - |  | 37600 |  | Cash | Outright | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL |  | 640318-10-6143 | Jalan Klang Batu 16, Kampung Tambak Jawa, 45800 Jeram, Selangor | 019-6642542 | klyap1964@hotmail.com | 3 years | 1 year
2407371 | Tiong Nguong Kiong | 2024-08-28 | Chean Bang | R-PV | NEM | #VALUE! | 10.53 | - |  | 32800 |  | Cash | Outright | Astronergy 585Wp | 18 | Huawei SUN2000-8KTL |  | 560304-01-5435 | No 8, Jln Mawar 6, Tmn Mawar, 28300 Triang, Pahang | 012-6628908 | meeting1210@gmail.com | 5 years | 1 year
2408409 | Lua Peck Lay | 2024-08-30 | Patricia | R-PV | NEM | #VALUE! | 9.945 | - |  | 27700 |  | Cash | Outright | Astronergy 585Wp | 17 | Huawei SUN2000-8KTL |  | 680419-11-5184 | No 25, Lrg Kubang Buaya 78, 25050 Kuantan, Pahang | 012-9218033 | luapecklay@yahoo.com | N/A | 1 year
2408411 | Akhman Aidi Putra | 2024-08-15 | Patricia | R-PV | NEM | #VALUE! | 7.02 | - |  | 24100 |  | Cash | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 850804-06-5063 | No 7, Lrg Seberang Balok Aman 22, Kg Seberang Balok, 26100 Kuantan, Pahang | 017-3054551 | mr_akhman85@yahoo.com | 3 years | 1 year
2408408 | Chiang Yoke Har | 2024-08-15 | Patricia | R-PV | NEM | #VALUE! | 17.55 | - |  | 50600 |  | Cash + Credit Card Instalment | Outright | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL |  | 620610-06-5002 | 2, Lrg Bukit Setongkol 45, Tmn Cenderawasih Indah, 25200 Kuantan, Pahang | 019-9896028 | yhchiang62@gmail.com | 3 years | 1 year
2408025 | Handal Green Mobility Sdn Bhd (ICE Gallery @ Pantai Sentral) | 2024-08-29 | Simon | EV Charger | - | #VALUE! | 0 |  |  | 55300 |  | Cash | Outright | - | - | - |  | - | No 2, Jalan Pantai Sentral 1, Pantai Sentral, 59200 Kuala Lumpur | - | - | N/A | 1 year
2408431 | Lor Yean Yean | 2024-09-09 | Tham | R-PV | NEM | #VALUE! | 9.36 | - |  | 30000 |  |  | Outright | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL |  | 600919-03-5372 | Lot 2206, Jln Bkt Losong Kg Losong Atap Zin, 21000 Kuala Terengganu | 012-9873293 | keemajujaya@gmail.com | 3 years | 1 year
2408432 | Lin Mok Kwai Yin | 2024-08-30 | Chean Bang | R-PV | NEM | #VALUE! | 8.19 | - |  | 23800 |  |  | Outright | Astronergy 585Wp | 14 | Huawei SUN2000-6KTL |  | 521023-06-5194 | 24, Lrg Seri Setali 17, Taman Tunas Baru, 25300 Kuantan, Pahang | 013-9310848 | datoedd@gmail.com | N/A | 1 year
2408407 | Kwong Wui Ee | 2024-09-05 | Patricia | R-PV | NEM | #VALUE! | 9.36 | - |  | 29700 |  | Cash | Outright | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL |  | 760907-06-5366 | No. 8, Lorong Bukit Setongkol Perdana 10, Perumahan Bukit Setongkol Perdana, 25200 Kuantan, Pahang | 012-9500330 | wuiee@hotmail.com | N/A | 1 year |  |  | Exc Smart Meter
2409441 | Cheu Chow Sew @ Chew Chow Sew | 2024-09-05 | Chean Bang | R-PV | NEM | #VALUE! | 12.87 | - |  | 38000 |  | Cash | Outright | Astronergy 585Wp | 22 | Huawei SUN2000-10KTL |  | 550726-06-5257 | Lot 690-B PPRT, Jln Paka, Kg Batu 50, 23000 Dungun Terengganu | 019-982 4668 | pnhuphin@gmail.com | 3 years | 1 year |  |  |  | Invoice to Perniagaan Hup Hin
2408433 | Ng Ek Hoo | 2024-09-02 | Chean Bang | R-PV | NEM | #VALUE! | 5.85 | - |  | 24000 |  | Cash | Outright | Astronergy 585Wp | 10 | Huawei SUN2000-5KTL-M1 |  | 500712-06-5197 | 41, Lrg Sekilau 64, Jalan Hj Ahmad, 25300 Kuantan | 010-2198138 | sping26@hotmail.com | 3 years | 1 year
2409445 | Phang Kar Teck | 2024-09-09 | Patricia | R-PV | NEM | #VALUE! | 7.02 | - |  | 22500 |  | Cash | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 560510-01-6383 | B4308, Jln Hj Ahmad, Tmn Rasa Sayang, 25300 Kuantan, Pahang | 019-9862354 | centralphang@gmail.com | N/A | 1 year
2408434 | Lim Ye Soon | 2024-09-09 | Chean Bang | R-PV | NEM | #VALUE! | 14.04 | - |  | 38600 |  | Cash | Outright | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL |  | 870920-06-5675 | Lot 7822, Lrg SJ 6-3, Tmn Emas - Sri Jaya, 26500 Maran, Pahang | 017-2152133 | limyesoon@gmail.com | 3 years | 1 year
2409442 | Lee Chiou Horng | 2024-09-08 | Tham | R-PV | NEM | #VALUE! | 9.44 | - |  | 33000 |  | Credit Card Instalment | Outright | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL |  | 820611-07-5743 | 38, Jalan Udang Gantung, Taman Cuepacs, Segambut, 52000 Kuala Lumpur, | 016-2030140 | alch51@yahoo.com | 3 years | 1 year |  |  |  | On-site service system electrical checking (once a year) for 1 year
2409443 | Dato Lim Zhen Peng | 2024-09-09 | Tham | R-PV | NEM | #VALUE! | 17.55 | - |  | 47360 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL |  | 910607-01-5085 | 15, Jalan Sentral 23/2, Taman Nusa Sentral, 79100 Iskandar Puteri, Johor | 017-6885686 | lindasushen@gmail.com | 3 years | 1 year
2408417 | Mohmad Nazeri bin Abdul Wahab | 2024-09-08 | Tham | R-PV | NEM | #VALUE! | 17.55 | - |  | 36500 |  | Cash | Outright | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL |  | 670812-10-6015 | 2, Jalan Merbuk 7/23, Taman Bentara, 42500 Telok Panglima Garang, Selangor | 017-2051100 |  | 3 years | 1 year
2409440 | Tan Say Kheng | 2024-09-04 | Tham | R-PV | NEM | #VALUE! | 7.02 | - |  | 25520 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 810115-10-5115 | 22, Jalan Jelok Impian 4, Taman Jelok Impian, 43000 Kajang, Selangor | 012-3850884 | tansaykheng@hotmail.com | 3 years | 1 year |  | Unitrade
2405273 | Leong Ah Seng | 2024-08-29 | Tham | R-PV | NEM | #VALUE! | 17.55 | - |  | 44600 | 7500 | Cash | Outright | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL |  | 570405-71-5931 | 22A, Jln PJU 3/12, Tropicana Indah, 47410 Petaling Jaya, Selangor | 012-2809511 | alicia@rossi.com.my | 3 years | 1 year |  | Unitrade
2308064 | Low Yin Jun | 2024-08-28 | Simon | R-PV | NEM | #VALUE! | 11.7 |  |  | 35000 |  | Cash | Outright | Astronergy 585Wp | 20 | Solinteg MHT-10K-25 hybrid |  | 910313-07-5138 | 16, Jalan CV 4B/1, Selangor Cyber Valley, 63300 Cyberjaya. Selangor Darul Ehsan | 019-3797922 | yinjunlow@gmail.com | 3 years | 1 year
2409447 | Chan Chee Tuck | 2024-09-10 | Chean Bang | R-PV | NEM | #VALUE! | 7.02 | - |  | 22200 |  | Cash | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 830427-06-5499 | No 43, Lorong Sri Jaya 7/4, Taman Sri Jaya Indah, 26500 Maran, Pahang | 011-51393543 | xiaoying2501@gmail.com | N/A | 1 year
2409444 | Tuan Noraizan Bt Tuan Long | 2024-09-11 | Chean Bang | R-PV | NEM | #VALUE! | 9.36 | - |  | 28700 |  | Cash | Outright | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL |  | 750714-11-5284 | Lot 339, Kg Raja Baran, Chendering, 21080 Kuala Terengganu, Terengganu | 019-4705537 | tuan_noraizan@arb.com.my | N/A | 1 year
2407368 | Noor Izzah Akmal Bt Mohd Nordin | 2024-09-10 | Chean Bang | R-PV | NEM | #VALUE! | 12.87 | - |  | 38600 |  | Cash | Outright | Astronergy 585Wp | 22 | Huawei SUN2000-10KTL |  | 871023-06-5530 | Lot 104149, Lrg Pak Mahat, Kg Kempadang, 26060 Kuantan. Pahang | 010-7058844 | izzahnordeen87@gmail.com | 3 years | 1 year
2409446 | Guok Diong Chong | 2024-09-09 | Tham | R-PV | NEM | #VALUE! | 9.36 | - |  | 28500 |  | Cash | Outright | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL |  | 640715-08-5235 | 85, Jln BU 11/6, Bandar Utama, 47800 Petaling Jaya, Selangor | 012-2685691 | dc.guok@gmail.com | 3 years | 1 year |  | Unitrade
2404249 | Tan Kheng Guan | 2024-09-11 | Tham | R-PV | NEM | #VALUE! | 17.55 | - |  | 47600 |  |  | Outright | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL |  | 550603-11-5293 | PT 19441, Jln Jakar, 24000 Cukai, Terengganu | 017-9083355 | kianhui89@gmail.com | 3 years | 1 year
2408424-1 | Low Bok Tek | 2024-09-11 | Tham | R-PV | NEM | #VALUE! | 17.55 | - |  | 46100 |  | Cash | Outright | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL |  | 580321-08-5097 | 18, Lrg 20 Tmn Lake View, 34000 Taiping, Perak | 019-4799999 | btcap@hotmail.com | 3 years | 1 year
2408424-2 | Low Bok Tek | 2024-09-11 | Tham | R-PV | NEM | #VALUE! | 17.55 | - |  | 46100 |  | Cash | Outright | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL |  | 530321-08-5097 | 18, Lrg 20 Tmn Lake View, 34000 Taiping, Perak | 019-4799999 | btcap@hotmail.com | 3 years | 1 year
2405284 | Amirul Hakim bin Omar | 2024-09-11 | Tham | R-PV | NEM | #VALUE! | 7.02 | - |  | 23500 |  |  | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 940311-10-5273 | 1, Jalan Beting Dua 8/13B, Seksyen 8, 40000 Shah Alam, Selangor | 010-3825802 | akembsp5@gmail.com | 3 years | 1 year
2409448 | Pang Chong Han | 2024-09-10 | Simon | R-PV | NEM | #VALUE! | 8.26 | - |  | 31622 |  | Credit Card Instalment | Outright | Astronergy 590Wp | 14 | Solinteg MHS-8K-25 |  | 860301-43-5893 | 12, Jln Gamelan 1E, Bdr Bukit Raja, 41050 Klang, Selangor | 016-9704005 | chonghan1386@hotmail.com | 3 years | 1 year
2408400 | Oh Chai Ean | 2024-09-11 | Chean Bang | R-PV | NEM | #VALUE! | 17.55 | - |  | 43300 |  | Cash | Outright | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL |  | 830417-08-5066 | A7468, Jln Galing Kecil, 25250 Kuantan,Pahang | 019-9128777 | wcyyoong123@gmail.com | N/A | 1 year
2409449-1 | Nurul Ain Binti Yahaya | 2024-09-11 | Chean Bang | R-PV | NEM | #VALUE! | 9.36 | - |  | 30000 |  | Cash+Credit Card Instalment | Outright | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL |  | 861226-23-5908 | No 24, Jalan KS 5/18, 25200 Kuantan, Pahang | 011-19423302 | nurulainyahaya@gmail.com | 3 years | 1 year
2409452 | Yio Pee Ban | 2024-09-21 | Chean Bang | R-PV | NEM | #VALUE! | 10.53 | - |  | 29700 |  | Cash | Outright | Astronergy 585Wp | 18 | Huawei SUN2000-8KTL |  | 810215-06-5157 | 135, Jln Bkt Setongkol 3, Tmn Muhibah Fasa 2, Bukit Setongkol, 25200 Kuantan, Pahang | 019-9142311 | pee.banyio@yahoo.com | 3 years | 1 year
2409449 | Tan Hock Seng | 2024-09-26 | Tham | R-PV | NEM | #VALUE! | 7.02 | - |  | 24908 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 700111-13-5045 | 107, Jalan Udang Pasir 3, Taman Megah, Kepong, 52100 Kuala Lumpur | 012-2383954 | tan.hockseng111@gmail.com | 3 years | 1 year
2409448-1 | Claris Lim Jink Niee (Lim Chin Horng) | 2024-09-21 | Tham | R-PV | NEM | #VALUE! | 11.7 | - |  | 34600 |  |  | Outright | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL |  | 020529-10-1062 | No 16, Jln Setia Nusantara U13/22T, Bandar Eco Setia, Setia Alam, 40170 Shah Alam, Selangor | 016-2176116 | clarislim2002@hmail.com | 3 years | 1 year
2406343 | Dato Sim Keng Piao | 2024-09-27 | Tham | R-PV | NEM | #VALUE! | 9.36 | - |  | 30000 |  |  | Outright | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL |  | 810623-05-5361 | 632, Jalan Sri Pulai 34, Taman Sri Pulai 3, 70400 Seremban, Negeri Sembilan | 012-3599293 | piew831@gmail.com | 3 years | 1 year
2409455 | Muhamad Syamil bin Zulkafli | 2024-09-03 | Tham | R-PV | NEM | #VALUE! | 7.02 | - |  | 22800 |  | Cash | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 850401-11-5337 | 15, Lrg Im 6/6 Indera Kayangan, Indera Mahkota, 25200 Kuantan, Pahang | 013-7196919 | syamale1985@gmail.com | N/A | 1 year
2410064 | Zarita binti Saliman | 2024-10-08 | Tham | R-PV | NEM | #VALUE! | 7.605 | - |  | 23940 |  | Cash | Outright | Astronergy 585Wp | 13 | Solinteg MHS-5K-30 hybrid |  | 720113-01-5002 | Lot 1183, Jalan Felcra, Kampung Batu 14, 43100 Hulu Langat, Selangor | 012-8888661 | capt.arifstephen@yahoo.com | 3 years | 1 year
2405305 | Chan Woei Jye | 2024-10-18 | Tham | R-PV | NEM | #VALUE! | 10.53 | - |  | 32000 |  | Cash | Outright | Astronergy 585Wp | 18 | Huawei SUN2000-8KTL |  | 750414-01-6647 | No 7, Jln Anggerik Eria Tujuh 31/109G, Kota Kemuning, Seksyen 31, 40460 Shah Alam, Selangor | 016-2100036 | cwoei_jye@hotmail.com | 3 years | 1 year
2409456 | Low Hong Chin | 2024-10-21 | Tham | R-PV | NEM | #VALUE! | 11.115 | - |  | 30000 |  | Cash | Outright | Astronergy 585Wp | 19 | Huawei SUN2000-10KTL |  | 791203-01-5725 | 9, Jalan Panorama 2, Taman Kota Panorama, 83700 Yong Peng | 013-3533328 | aiping8113@gmail.com | 3 years | 1 year
2410461 | Low Hong Choon | 2024-10-21 | Tham | R-PV | NEM | #VALUE! | 7.02 | - |  | 23500 |  | Cash | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 830209-01-6269 | No 21, Jln Bayu 8, Tmn Sri Bayu, 83700 Yong Peng, Johor | 012-5103669 | aiping8113@gmail.com | 3 years | 1 year
2409029 | Handal Green Mobility Sdn Bhd (Mazda Kuantan Showroom) | 2024-10-15 | Simon | EV Charger | - | #VALUE! | 0 | 22 |  | 2643 |  | Cash | Outright | - | - | - |  | - | A557, Jalan Padang lalang, Padang Lalang Industrial Area, Kuantan, Pahang | - | - | N/A | 1 year
2410032 | Handal Green Mobility Sdn Bhd (United Point Mall, Kuala Lumpur) | 2024-10-24 | Simon | EV Charger | - | #VALUE! | 0 | 120 |  | 38470 |  | Cash | Outright | - | - | - |  | - | 10, Jalan Lang Emas, Segambut, 51200 Kuala Lumpur | - | - | N/A | 1 year
2407167-1 | Econframe Marketing Sdn Bhd (Kilang 1 & 3) | 2024-09-17 | Tham | C&I-PV | NEM | #VALUE! | 109.395 | - |  | 233000 |  | Cash | Outright | Yingli Solar 585Wp | 187 | Huawei SUN2000-50KTL + SUN2000-36KTL |  | - | No 1, Jln Sg Rasa 27 A Off, Jln Dato Mohd Sidin, 41300 Klang, Selangor |  |  | 3 years | 1 year
2407167-2 | Econframe Marketing Sdn Bhd (Kilang 4) | 2024-09-18 | Tham | C&I-PV | NEM | #VALUE! | 26.91 | - |  | 71000 |  | Cash | Outright | Yingli Solar 585Wp | 46 | Huawei SUN2000-20KTL |  | - | Lot 4, Jln Sg Rasa 27 A Off, Jln Dato Mohd Sidin, 41300 Klang,Selangor |  |  | 3 years | 1 year
2407167-3 | Econframe Marketing Sdn Bhd (Kilang 20) | 2024-09-19 | Tham | C&I-PV | NEM | #VALUE! | 67.275 | - |  | 136000 |  | Cash | Outright | Yingli Solar 585Wp | 115 | Huawei SUN2000-50KTL |  | - | Lot 63272, Lrg Sg Rasau 27A, 41300 Klang, Selangor |  |  | 3 years | 1 year
2408174 | Zimandy Construction Sdn Bhd (Bandar Tenggara) | 2024-10-18 | Tham | C&I-PV | NEM | #VALUE! | 120.95 | - |  | 269900 |  | Cash | Outright | Astronergy 590Wp | 205 | Huawei SUN2000-40KTL +SUN2000-30KTL + SUN2000-20KTL |  | - |  |  |  | 3 years | 1 year
2408179 | Pelita Hijrah Sdn Bhd | 2024-09-27 | Tham | C&I-PV | NEM | #VALUE! | 107.64 | - |  | 320000 |  | Cash | Outright | Astronergy 585Wp | 184 | Huawei SUN2000-20KTL x 4 |  | - | Lot 71104-A, Jln Teratai, Kg Paya Jaras Hilir, 40160 Sungai Buloh, Selangor |  |  | 3 years | 1 year |  | PX
2409185 | Kim Chong Mechanical Services Sdn Bhd | 2024-09-30 | Tham | C&I-PV | NEM | #VALUE! | 26.55 | - |  | 73000 |  | Cash | Outright | Astronergy 590Wp | 45 | Huawei SUN2000-20KTL |  | - | 3-KB 12, Jalan KPB 18. Kawasan Perindustrian Balakong, 43300 Seri Kembangan, Selangor |  |  | 3 years | 1 year |  | Unitrade
2410196 | Unilink Machinery Sdn Bhd | 2024-10-24 | Tham | C&I-PV | NEM | #VALUE! | 26.55 | - |  | 73000 |  | Cash | Outright | Astronergy 590Wp | 45 | Huawei SUN2000-20KTL |  |  | PT 85915, Jln KPG Tok Muda, Kapar, 42200 Klang. Selangor |  |  | 3 years | 1 year |  | Unitrade
2410474 | Koe Ban Seng | 2024-11-01 | Tham | R-PV | NEM | #VALUE! | 14.04 | - |  | 37600 |  | Cash | Outright | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL |  | 621130-12-5429 | 8, Jln Kenyalang 11/15C, Seksyen 11, Kota Damansara, 47810 Petaling Jaya, Selangor | 012-3983893 | koebanseng@yahoo.com | 3 years | 1 year |  | Unitrade
2410468 | Teo Boon Ling | 2024-10-25 | Tham | R-PV | NEM | #VALUE! | 11.7 | - |  | 36600 |  | Cash | Outright | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL |  | 760505-06-5312 | 1, Jalan Daun Imai 10, Sunway SPK Damansara, 52200 Kuala Lumpur | 019-2221381 | boonlingteo@yahoo.com | 3 years | 1 year |  | Unitrade
2409450 | David Hie Wen Jian | 2024-10-26 | Tham | R-PV | NEM | #VALUE! | 7.02 | - |  | 23500 |  | Cash | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 890928-10-5553 | 52, Jln BU 1/9, Bandar Utama, 47800 Petaling Jaya, Selangor | 012-3756770 | hiedavid89@gmail.com | 3 years | 1 year
2411488 | Tan Kong Ling | 2024-11-04 | Chean Bang | R-PV | NEM | #VALUE! | 10.53 | - |  | 32000 |  | Cash | Outright | Astronergy 585Wp | 18 | Huawei SUN2000-8KTL |  | 661024-08-5861 | No 2, Lrg SJ 6-3, Tmn Emas-Sri Jaya, 26500 Maran, Selangor | 013-9365933 | ysy0723@hotmail.com | 3 years | 1 year
2411487 | Lim Daw Woei | 2024-11-04 | Tham | R-PV | NEM | #VALUE! | 15.21 | - |  | 42200 |  | Cash | Outright | Astronergy 585Wp | 26 | Huawei SUN2000-12KTL |  | 660927-01-5907 | 6, Jalan Kenyalang 11/15H, Seksyen 11, Kota Damansara, 47810 Petaling Jaya, Selangor | 012-3321852 | jolimdw@gmail.com | 3 years | 1 year |  | Unitrade
2410476 | Choong Chin Fong | 2024-11-03 | Tham | R-PV | NEM | #VALUE! | 7.02 | - |  | 23500 |  | Cash | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 801219-01-5419 | 42, Jalan Setia 9/11, Taman Setia Indah, 81100 Johor Bahru | 013-7679113 | berny9113bc@gmail.com | 3 years | 1 year |  | Unitrade
2407376 | Teoh Eng Siong | 2024-07-27 | Chean Bang | R-PV | NEM | #VALUE! | 10.53 | - |  | 37768 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 18 | Huawei SUN2000-8KTL |  | 801211-08-5615 | No 46, Lorong Sri Jaya 7/4, Taman Sri Jaya Indah, 26500 Maran, Pahang | 019-9153886 | teoh114@gmail.com | 5 years | 1 year
2410482 | Teo Thian Keong | 2024-10-31 | Tham | R-PV | NEM | #VALUE! | 8.775 | - |  | 28500 |  | Cash | Outright | Astronergy 585Wp | 15 | Huawei SUN2000-8KTL |  | 870218-23-5523 | 31, Jalan SS 22/30, Petaling, 47400 Petaling Jaya, Selangor | 017-7584843 | tianqiang87@gmail.com | 3 years | 1 year
2410471 | Chua Lu Chuan | 2024-10-11 | Chean Bang | R-PV | NEM | #VALUE! | 17.55 | - |  | 47600 |  | Cash | Outright | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL |  | 420804-10-5133 | No 1, Lrg Seri Kuantan 28/1, Kuantan Garden, 25300 Kuantan, Pahang | 010-3959313 | cboonhuang@gmail.com | 3 years | 1 year |  | Referral
2411489 | Quah Ewe Lee | 2024-11-26 | Tham | R-PV | NEM | #VALUE! | 14.04 | - |  | 39980 |  |  | Outright | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL |  | 560319-07-5561 | 11, Jalan Kenyalang 11/15F, Seksyen 11, Kota Damansara, 47810 Petaling Jaya, Selangor | 019-3126618 | qel1888@hotmail.com | 3 years | 1 year |  | Unitrade
2411486 | Lim Chee Keong | 2024-12-02 | Tham | R-PV | NEM | #VALUE! | 13.455 | - |  | 36600 |  | Cash | Outright | Astronergy 585Wp | 23 | Huawei SUN2000-10KTL |  | 570825-10-5283 | 5, SD 10/1E, Jln Margosa, Bdr Sri Damansara PJU 9, 52200 Kuala Lumpur, WP Kuala Lumpur | 018-7636292 | lim.jianwen0@gmail.com | 3 years | 1 year
2411500 | Ho Maw Chun | 2024-12-02 | Tham | R-PV | NEM | #VALUE! | 14.16 | - |  | 37600 |  | Cash | Outright | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL |  | 691208-08-5361 | 16, Jalan Kantan 5/KS6, Bandar Botanic, 41200 Klang, Selangor | 012-3306639 | hmc8925@gmail.com | 3 years | 1 year
2410034 | Handal Green Mobility Sdn Bhd (Pulse Grande Hotel) | 2024-11-25 | Chean Bang | EV Charger | - | #VALUE! | 0 | 47 |  | 4150 |  | Cash | Outright | - | - | - |  | - | Taman Putra perdana, Jalan Putra Perdana, Presint 1, 62000 Putrajaya | - | - | N/A | 1 year
2411494 | Pang Kim Soon | 2024-11-26 | Chean Bang | R-PV | NEM | #VALUE! | 17.55 | - |  | 60000 |  | Cash | Outright | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL |  | 770123-06-5463 | 44, Jalan KS 5/5, Kota Sultan Ahmad Shah, 25200 Kuantan, Pahang | 012-9833998 | ks.kspang@gmail.com | N/A | 1 year
2411496 | Teong Lian Aik | 2024-11-26 | Tham | R-PV | NEM | #VALUE! | 9.36 | - |  | 29000 | 289 | Cash | Outright | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL |  | 550907-08-5791 | 9(5), Regat Tasik Tmn Tasik Permai Fasa, 34000 Taiping, Perak | 012-5381739 | la_teong@yahoo.com | 3 years | 1 year
2404224 | Vijayalakshmi a/p Krishnaswamy (Tan Sri Rama Iyer) | 2024-11-28 | Tham | R-PV | NEM | #VALUE! | 17.7 | - |  | 45600 |  | Cash | Outright | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | - | 450528-71-5062 | Lot 310, Jln 3, Tmn Ampang Utama, 68000 Ampang, Selangor | 012-3030154 | ramavijayam10@gmail.com | 3 years | 1 year |  | Unitrade | Exclude Smart Meter | Unitrade request FOC for installing SSO for EV Charger
2411491 | Low Kim Keong | 2024-12-05 | Chean Bang | R-PV | NEM | #VALUE! | 11.7 | - |  | 38420 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL |  | 821109-06-5309 | 13, Lrg Seri Setali 11 Off Jln Galing Kem, Tmn Sri Galing, 25300 Kuantan, Pahang | 016-9210888 | adwardlow.co@gmail.com | 3 years | 1 year
2411490 | Chear Eng Soon | 2024-12-05 | Chean Bang | R-PV | NEM | #VALUE! | 7.02 | - |  | 21500 |  | Cash | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 840409-01-5489 | PTD 144930, No 7, Jln Pinggiran 3/2, Horizon Hills, 79100 Nusajaya, Johor | 012-7840881 | nick.chear@gmail.com | 3 years | 1 year |  | BNI | Exclude Smart Meter
2412504 | Thiong Jeng Ell | 2024-12-07 | Patricia | R-PV | NEM | #VALUE! | 9.36 | - |  | 31616 |  | Cash | Outright | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL |  | 790424-06-5465 | Lot 7929, Jln Hock Bee Kg Sri Jaya, 26500 Sri Jaya, Pahang | 013-9355351 | jethiong@hotmail.com | 5 years | 1 year
2412503 | Lian Hock Seng | 2024-12-07 | Chean Bang | R-PV | NEM | #VALUE! | 14.04 | - |  | 38600 |  | Cash | Outright | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL |  | 781225-06-5185 | 70, Lrg SJ 4-4, Tmn Sri Jaya Indah, 26500 Maran, Pahang | 013-9933228 | hockseng8168@gmail.com | 5 years | 1 year
2410033 | Handal Green Mobility Sdn Bhd (Kuantan City Mall) | 2024-12-10 | Chean Bang | EV Charger | - | #VALUE! | 0 | 120 |  | 55000 |  | Cash | Outright | - | - | - |  | - | Jalan Putra Square 6, Putra Square, 25300 Kuantan, Pahang | - | - | N/A | 1 year
2412505 | Dong Mee Hong | 2024-12-13 | Patricia | R-PV | NEM | #VALUE! | 14.04 | - |  | 42860 |  | Credit Card Instalment | Outright | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL |  | 511231-08-5676 | Lot 7824, Lrg Sj 6-3, Tmn Emas-Sri Jaya, 26500 Maran, Pahang | 012-9371615 |  | 5 years | 1 year
2412509 | Muck Bei lee (Le Lodge Mansion) | 2024-12-31 | Chean Bang | R-PV | NEM | #VALUE! | 17.7 | - |  | 50000 |  | Credit Card Instalment | Outright | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL |  | 861105-33-5208 | No 2, Lrg Air Putih 97, Tmn Sri Air Putih, Air Putih, 25300 Kuantan, Pahang | 012-9533751 | beilee86@gmail.com | N/A | 1 year |  |  | Exclude smart meter and insurance
2412515 | Liew Mun Meng | 2024-12-21 | Tham | R-PV | NEM | #VALUE! | 17.55 | - |  | 44600 |  | Cash | Outright | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL |  | 641211-08-6159 | 77, Jalan Taming Indah 2, Taman Taming Indah 2, 43000 Kajang, Selangor | 010-5642088 | weinnyliew88@gmail.com | 3 years | 1 year |  | Unitrade
2410462 | Yee Mei Ling | 2024-12-23 | Tham | R-PV | NEM | #VALUE! | 7.02 | - |  | 23500 |  | Cash | Outright | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 680106-07-5302 | 19, Jalan Mas 3/2, Taman Mas 3, 43200 Cheras, Selangor | 019-2233298 | pmcoatings2010@gmail.com | 3 years | 1 year |  | Unitrade
2412516 | Chareon Phromsuwan | 2024-12-24 | Tham | R-PV | NEM | #VALUE! | 12.98 | - |  | 37160 |  | Credit Card Instalment | Outright | Astronergy 590Wp | 22 | Huawei SUN2000-10KTL |  | 680901-07-5379 | 7, Jln Kenyalang 11/15C, Seksyen 11, Kota Damansara, 47810, Petaling Jaya, Selangor | 019-3102054 | chareonp@gmail.com | 3 years | 1 year |  | Unitrade
2412521 | Christopher A De Souza | 2025-01-02 | Tham | R-PV | NEM | #VALUE! | 15.34 | - |  | 39560 |  | Credit Card Instalment | Outright | Astronergy 590Wp | 26 | Huawei SUN2000-12KTL |  | 600427-10-6373 | 24, Jalan Kenyalang 11/15G, Seksyen 11, Kota Damansara, 47810 Petaling Jaya, Selangor | 012-3328366 | christophera.desouza@gmail.com | 3 years | 1 year |  | Unitrade
2412524 | Teng Lee Xung | 2025-01-02 | Chean Bang | R-PV | NEM | #VALUE! | 14.16 | - |  | 34000 |  | Cash | Outright | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL |  | 850803-02-5617 | No 6, Lrg Seri Setali 119, Jln Air Putih, Tmn Semambu, 25350 Kuantan, Pahang | 012-8860611 | danileteng777@gmail.com | N/A | 1 year
2412513 | Ganapathy Srihari a/l Rama Iyer | 2025-01-09 | Tham | R-PV | NEM | #VALUE! | 10.03 | - | - | 29000 |  | Cash | Outright | Astronergy 590Wp | 17 | Huawei SUN2000-8KTL |  | 720101-10-7073 | 68, Jalan Athinahapan, Taman Tun Dr Ismail, 60000 Kuala Lumpur, WP Kuala Lumpur | 012-2000599 | srihari.iyer@gmail.com | 3 years | 1 year
2501038 | Florence Poon | 2025-01-21 | Simon | EV Charger | - | #VALUE! | 0 | 11 |  | 2000 |  | Cash | Outright |  | - | - |  | - | 8, Lorong PJU 3/28C, 28 Residency Sunway, Damansara, 47810 Petaling Jaya, Selangor | - | - | N/A | 1 year
2501532 | Prasert Phromsuwan | 2025-01-25 | Tham | R-PV | NEM | #VALUE! | 9.44 | - | - | 27000 |  | Cash | Outright | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL |  | 650114-07-5321 | No 37, Jln Setia Damai U13/14E, Seksyen U 13, 40170 Shah Alam, Selangor | 019-2867788 | pphromsuwan@gmail.com | 3 years | 1 year
2501544 | Gan Tek Chuan | 2025-02-06 | Patricia | R-PV | NEM | #VALUE! | 17.7 | - | - | 44000 |  | Cash | Outright | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL |  | 660508-10-5393 | Lot 11013, B26, Jln Hock Bee Kg Sri Jaya, 26500 Sri Jaya, Pahang | 011-53019513 | pekjin123@gmail.com | 3 years | 1 year |  |  |  | Add 1k for smart meter
2502548 | Wong Kok Wai | 2025-02-12 | Chean Bang | R-PV | NEM | #VALUE! | 17.7 | - | - | 42000 |  | Cash | Outright | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL |  | 910323-06-5427 | 11, Lrg Sekilau 38, Tmn Sekilau Perdana, 25200 Kuantan, Pahang | 011-16233292 | rambowongkokwai@gmail.com | 3 years | 1 year
2501545 | Lee Tian Look | 2025-02-13 | Chean Bang | R-PV | NEM | #VALUE! | 7.08 | - | - | 21800 |  | Cash | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 610115-06-5321 | 53A Lrg Sj 6-3, Tmn Emas-Sri Jaya, 26500 Maran, Pahang Darul Makmur | 010-2109882 | leeweisen@gmail.com | 3 years | 1 year
2311088 | Lee Chean Chung | 2025-02-12 | Chean Bang | R-PV | NEM | #VALUE! | 10.62 | - | - | 27000 |  | Cash | Outright | Astronergy 590Wp | 18 | Huawei SUN2000-10KTL |  | 810411-06-5277 | 5, Jalan 6/5, Seksyen 6. 46000 Petaling Jaya, Selangor | 012-9540498 | cheanchung@gmail.com | 3 years | 1 year
2502216 | Low Yi Chin | 2025-02-13 | Chean Bang | C&I-PV | NEM | #VALUE! | 14.16 | - | - | 37000 |  | Cash | Outright | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL |  | 730830-14-5255 | Lot 4358, Jln Kuantan Kg Sri Jaya, 26500 Sri Jaya, Pahang | 012-2529900 | chipseng.srijaya@yahoo.com.my | 3 years | 1 year
2502553 | Salim Majid Zain Bin Abdul Majid | 2025-02-14 | Tham | R-PV | NEM | #VALUE! | 17.7 | - | - | 42000 |  | Cash | Outright | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL |  | 690717-10-5637 | 48, Jalan Lanai Kiara, Taman Sri Haratamas, 50480 Kuala Lumpur, WP Kuala Lumpur | 019-2200333 | salimmaa@gmail.com | 3 years | 1 year
2502552 | Anandan a/l Balakrishnan | 2025-02-14 | Tham | R-PV | NEM | #VALUE! | 11.8 | - | - | 31000 |  | Cash | Outright | Astronergy 590Wp | 20 | Huawei SUN2000-10KTL |  | 670720-05-5097 | 79, Jalan SS 18/4, SS 18, 47500 Subang Jaya, Selangor | 012-2070181 | dan.anandan@yahoo.com | 3 years | 1 year
2412519 | Liew Swee Fah | 2025-02-12 | Tham | R-PV | NEM | #VALUE! | 7.08 | - | - | 21500 |  | Cash | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 700204-06-5293 | 203, Kg Baru, Sungai Lui, 27600 Raub, Pahang | 011-37587569 | liewsweefah5379@gmail.com | 3 years | 1 year
2502547 | Chong Chee Hoo | 2025-02-17 | Tham | R-PV | NEM | #VALUE! | 11.8 | - | - | 32840 |  | Credit Card Instalment | Outright | Astronergy 590Wp | 20 | Huawei SUN2000-10KTL |  | 860527-23-6635 | 9, Jalan Eko Botani 1/7, Taman Eko Botani, 79100 Iskandar Puteri, Johor | 012-2556708 | cheehoo1450@gmail.com | 3 years | 1 year |  | Unitrade
2502541 | Boo Kee Meng | 2025-02-17 | Tham | R-PV | NEM | #VALUE! | 7.08 | - | - | 21500 |  | Cash | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 690901-01-5903 | 6, Jalan Bertam 21, Taman Daya, 81100 Johor Bahru | 016-7255360 | lucasboo123@hotmail.com | 3 years | 1 year
2502556 | Gan Chong Sing | 2025-02-17 | Patricia | R-PV | NEM | #VALUE! | 7.08 | - | - | 22500 |  | Cash | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 900427-06-5131 | No A53, Jln Hock Bee Kg Sri Jaya, 26500 Sri Jaya, Pahang | 010-2399409 | chongsing90@hotmail.com | 3 years | 1 year
2502551 | Tan Seng Shen | 2025-02-17 | Tham | R-PV | NEM | #VALUE! | 14.16 | - | - | 35000 |  | Cash | Outright | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL |  | 680116-01-5493 | 20, Jalan BK 6A/2G, Bandar Kinrara, 47180 Puchong, Selangor | 012-2329310 | samtan@insutex.my | 3 years | 1 year
2502546 | Jordan Tan Heng Xiang | 2025-02-17 | Tham | R-PV | NEM | #VALUE! | 7.08 | - | - | 22500 |  | Cash | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-6KTL |  | 920619-10-5001 | 47, Jln Bungor 7, Bdr Botanic, 41200 Klang, Selangor | 016-3030529 | jordantan.1992@gmail.com | 3 years | 1 year
2502559 | Wong Peng Soon | 2025-02-18 | Chean Bang | R-PV | NEM | #VALUE! | 9.44 | - | - | 28000 |  | Cash | Outright | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL |  | 570816-10-5679 | 1, Lrg Im 13/7, Jln Sg Lembing (Astana Golf Resort), Indera Mahkota, 25200 Kuantan, Pahang | 012-9832681 | miaoshun@live.com.my | 3 years | 1 year
2501537 | Chan My Ling | 2025-02-17 | Tham | R-PV | NEM | #VALUE! | 12.39 | - | - | 33800 |  | Credit Card Instalment | Outright | Astronergy 590Wp | 21 | Huawei SUN2000-10KTL |  | 651015-06-5528 | No 2, Jln Mandarina 2, Bkt Manda'rina, 56000 Cheras, WP Kuala Lumpur | 011-16262901 | irenechan2708@gmail.com | 3 years | 1 year |  | Unitrade
2502550 | Ricky Goh Hoon Kan | 2025-02-18 | Chean Bang | R-PV | NEM | #VALUE! | 14.75 | - | - | 37500 |  | Cash | Outright | Astronergy 590Wp | 25 | Huawei SUN2000-12KTL |  | K2270382D | 5, Jln Pahang Tmn Canning, 31400 Ipoh, Perak | 017-4380711 | rickygohhk@yahoo.com | 5 years | 1 year
2502543 | Chow Leong Choon | 2025-02-13 | Ong | R-PV | NEM | #VALUE! | 7.08 |  |  | 22000 |  | Cash | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 790829-14-5017 | 41, Jln USJ 16/3, Mukim Damansara, 47630 Petaling Jaya, Selangor | 011-33111419 | lcchow2k@yahoo.com | N/A | 1 year
2502560 | Lim Sooi Poh | 2025-02-20 | Tham | R-PV | NEM | #VALUE! | 14.16 |  |  | 35000 |  | Cash | Outright | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL |  | 600828-01-5237 | 17, Double Storey Semi-Detached, Jln Panorama 2, Tmn Kota Panorama, 83700 Yong Peng, Johor | 019-7137352 | c2pxian92@hotmail.com | 3 years | 1 year |  | Unitrade
2408411-1 | Eng Khai Shu | 2025-02-25 | Tham | R-PV | NEM | #VALUE! | 17.7 |  |  | 43000 |  | Cash | Outright | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL |  | 880903-14-5138 | 72, WP Kuala Lumpur, Jalan Kasipillay, 51200 Kuala Lumpur, WP Kuala Lumpur | 012-5030513 | celinebellea0903@gmail.com | 3 years | 1 year
2502569 | Chew Beng Hock | 2025-02-24 | Ong | R-PV | NEM | #VALUE! | 8.85 |  |  | 29228 |  | Credit Card Instalment | Outright | Astronergy 590Wp | 15 | Huawei SUN2000-8KTL |  | 670201-04-5153 | 51, Jln USJ 11/1F, UEP Subang Jaya, 47600 Subang Jaya, Selangor | 017-8779033 | ameliachew76@yahoo.com | 3 years | 1 year
2502565 | Yeo Shu Jin | 2025-02-25 | Simon | R-PV | NEM | #VALUE! | 7.67 |  |  | 21500 |  | Cash | Outright | Astronergy 590Wp | 13 | Huawei SUN2000-6KTL |  | 820817-10-5821 | 8, Jalan Aman Perdana 8E/KU5, Taman Aman Perdana, 41050 Klang, Selangor | 012-2111891 | sjyeo82@yahoo.com | 3 years | 1 year
2502549 | Har Hock Lee | 2025-02-27 | Patricia | R-PV | NEM | #VALUE! | 14.16 |  |  | 35000 |  | Cash | Outright | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL |  | 650217-08-5143 | Lot 5361, Lrg SJ 6-3, Tmn Emas-Sri Jaya, 26500 Maran, Pahang | 013-9304377 | harwanhong99@gmail.com | 3 years | 1 year
2405286 | Wong Wai Hung | 2025-02-28 | Tham | R-PV | NEM | #VALUE! | 17.7 |  |  | 41000 |  | Cash | Outright | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL |  | 760329-14-5793 | 25, Jalan SS 3/86, Taman Universiti, 47300 Petaling Jaya, Selangor | 019-2266120 | w.waihung@gmail.com | 3 years | 1 year
2501527 | Kuan Guan Chong | 2025-03-02 | Tham | R-PV | NEM | #VALUE! | 11.8 |  |  | 31000 |  | Cash | Outright | Astronergy 590Wp | 20 | Huawei SUN2000-10KTL |  | 551212-03-5215 | 7, Jln Impian 1, Tmn Impian Villa, 27600 Raub, Pahang | 017-9331115 | kuankianyang@hotmail.com | 3 years | 1 year
2501529 | Kuan Kian Yang | 2025-03-02 | Tham | R-PV | NEM | #VALUE! | 10.62 |  |  | 29000 |  | Cash | Outright | Astronergy 590Wp | 18 | Huawei SUN2000-8KTL |  | 831207-03-5225 | No 93, Jalan Impian 4, Taman Impian Villa, 27600 Raub Pahang | 017-9331115 | kuankianyang@hotmail.com | 3 years | 1 year
2502581 | Loh Chee Kuan | 2025-03-01 | Tham | R-PV | NEM | #VALUE! | 7.08 |  |  | 22340 |  | Credit Card Instalment | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 810227-14-5381 | No 12, Jln Megah 11A, Tmn Megah, 43200 Batu 11 Cheras, Selangor | 012-6269463 | stanleyloh33@gmail.com | 3 years | 1 year
2501540 | Mohd Rushdi Bin Haji Abu Bakar | 2025-02-28 | Patricia | R-PV | NEM | #VALUE! | 7.08 |  |  | 23429 |  | Cash + CC Instalment | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 730408-06-5049 | No 59, Lrg Seri Damai Aman 52, Jln Gambang, Tmn Seri Damai Aman, 25150 Kuantan, Pahang | 010-5767058 | mohd.rushdi.abu.bakar@gmail.com | 3 years | 1 year
2502571 | Ting Kam Peng | 2025-03-02 | Tham | R-PV | NEM | #VALUE! | 11.8 |  |  | 32840 |  | Credit Card Instalment | Outright | Astronergy 590Wp | 20 | Huawei SUN2000-10KTL |  | 500414-08-5173 | 13, Jln 13 Jln Klang Lama Bt 5, Tmn Lee Yan Lian, 58200 WP Kuala Lumpur | 019-3211233 | tingkampeng@gmail.com | 3 years | 1 year
2502568 | Lim See Peng | 2025-02-28 | Tham | R-PV | NEM | #VALUE! | 7.08 |  |  | 25280 |  | Credit Card Instalment | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-6KTL-M1 |  | 300102-10-5815 | 16, Jln Kemuning Indah 32/142, Kemuning Utama, Seksyen 32, 40460 Shah Alam, Selangor | 012-3178932 | seepeng.lim@gmail.com | 3 years | 1 year |  |  |  | Completion of physical by Sept 2025
2404258 | Chan Yee Wan | 2025-03-06 | Tham | R-PV | NEM | #VALUE! | 9.44 |  |  | 27000 |  | Cash | Outright | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL |  | 801016-14-6283 | 52A, Jalan Aman Arahsia 2, Bandar Tropicana Aman, 42500 Telok Panglima Garang, Selangor | 012-2912577 | jason_dasb@hotmail.com | 3 years | 1 year
2503588 | Lee Xue Cheng | 2025-03-06 | Tham | R-PV | NEM | #VALUE! | 7.08 |  |  | 22500 |  | Cash | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 051028-01-1415 | No 70, Jln Bestari 3/1, Tmn Nusa Bestari, 79150 Johor Bahru, Johor | 017-7857783 | xuechenglee1028@gmail.com | 3 years | 1 year
2502561 | Dennis Lee Jia Seng | 2025-03-07 | Tham | R-PV | NEM | #VALUE! | 15.93 |  |  | 38000 |  | Cash | Outright | Astronergy 590Wp | 27 | Huawei SUN2000-12KTL |  | 970507-01-6675 | No 6, Jln Panorama 7, Tmn Kota Panorama, 83700 Yong Peng, Johor | 016-7139920 | leedennis507@gmail.com | 3 years | 1 year |  | Unitrade
2503590 | Teh Wee Loon | 2025-03-07 | Tham | R-PV | NEM | #VALUE! | 14.16 |  |  | 39680 |  | Credit Card Instalment | Outright | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL |  | 830510-10-5973 | 1, Jalan Aman Perdana 11K/KU5, Taman Aman Perdana, 41050 Klang, Selangor | 019-6483333 | tehweeloon@gmail.com | 3 years | 1 year |  | Unitrade
2502570 | Tang Wei Keong | 2025-03-07 | Tham | R-PV | NEM | #VALUE! | 9.44 |  |  | 27000 |  | Cash | Outright | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL |  | 780524-14-5949 | No 5, Jln Kemuning Damai 32/147D, Kemuning Utama, Seksyen 32, 40460 Shah Alam, Selangor | 012-2398993 | wktang@synteq.com.my | 3 years | 1 year
2502573 | Wong Jun Kit | 2025-03-06 | Simon | R-PV | NEM | #VALUE! | 6.49 |  |  | 26000 |  | Cash | Outright | Astronergy 590Wp | 11 | Huawei SUN2000-5KTL-M1 |  | 801127-10-2417 | No 1, Lrg Mohd Tahir 14A/KS2, Tmn Saujana, Kg Jawa, 41000 Klang, Selangor | 019-3840060 | junkit143@yahoo.com.sg | 3 years | 1 year
2503593 | Rashid Bin Darlan | 2025-03-10 | Patricia | R-PV | NEM | #VALUE! | 7.08 |  |  | 24548 |  | Credit Card Instalment | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 680415-01-5223 | No 6, Jalan Sungai Soi Jaya 3, Perumahan Sungai Soi Jaya 2, 26060 Kuantan Pahang | 012-4424191 | rash.darl@gmail.com | 3 years | 1 year
2501211 | Great Beauty Furniture Sdn Bhd | 2025-03-07 | Chean Bang | C&I-PV | NEM | #VALUE! | 26.55 |  |  | 54000 |  | Cash | Outright | Astronergy 590Wp | 45 | Huawei SUN2000-20KTL |  |  | A 483, Jalan Beserah, Taman Sri Pelindung Satu, 25300 Kuantan, Pahang |  |  | 3 years | 1 year |  |  |  | No GITA application
2502589 | Chin Kok Leng | 2025-03-07 | Patricia | R-PV | NEM | #VALUE! | 8.85 |  |  | 26000 |  | Cash | Outright | Astronergy 590Wp | 15 | Huawei SUN2000-8KTL |  | 761030-06-5371 | 11, Lrg Sekilau 42, Jln Hj Ahmad, Tmn Sekilau Perdana, 25200 Kuantan, Pahang | 016-9221033 | cherryq16@gmail.com | 3 years | 1 year
2403090 | Mei Shun Fang Manufacturing Sdn Bhd | 2025-02-27 | Tham | C&I-PV | NEM | #VALUE! | 476.13 | 44 |  | 898000 | 8500 | Cash | Outright | Astronergy 590Wp | 807 | [6 empty] | 3 years | 1 year | Full O&M - 3 years
2502557 | Chin Yee Fa | 2025-03-11 | Patricia | R-PV | NEM | #VALUE! | 9.44 |  |  | 28000 |  | Cash | Outright | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL |  | 570406-06-5491 | No 19, Lrg Im 11/6, Mahkota Heights, 25200 Kuantan, Pahang | 019-9160668 | cjhao8855@gmail.com | 3 years | 1 year
2503594 | Wong Teck Keng | 2025-03-11 | Patricia | R-PV | NEM | #VALUE! | 7.08 |  |  | 22500 |  | Cash | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 770530-14-5591 | 161, Jln USJ 9/1, UEP Subang Jaya, 47630 Subang Jaya, Selangor | 012-3153960 | teckkeng@gmail.com | 3 years | 1 year |  | Ken
2503597 | Bhajan Singh a/l S Bachan Singh | 2025-03-11 | Chean Bang | R-PV | NEM | #VALUE! | 10.62 |  |  | 31000 |  | Cash | Outright | Astronergy 590Wp | 18 | Huawei SUN2000-8KTL |  | 520529-01-5595 | 1, Lrg Kubang Buaya 7, 25250 Kuantan, Pahang | 013-9276292 | bhajan1952@gmail.com | 3 years | 1 year
2502588 | Khadillah binti Hassan | 2025-03-12 | Patricia | R-PV | NEM | #VALUE! | 8.85 |  |  | 26600 | 1000 | Cash | Outright | Astronergy 590Wp | 15 | Huawei SUN2000-8KTL |  | 680623-06-5006 | D367, Jln Bukit Setongkol, Pkg Cenderawasih, 25200 Kuantan, Pahang | 012-9222442 | fenthagrow@gmail.com | 3 years | 1 year
2502040 | ST Rosyam Mall (Plus Xnergy Services Sdn Bhd) | 2025-03-12 | Simon | EV Charger |  | #VALUE! |  | 62 |  | 92000 | 400 | Cash | Outright | - | - | - | [5 empty] | N/A | 1 year
2503595 | Lim Zhi Jie | 2025-03-14 | Tham | R-PV | NEM | #VALUE! | 14.16 |  |  | 35000 |  | Cash | Outright | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL |  | 991018-01-5615 | 19, Jalan Panoram 2, Taman Kota Panorama, 83700 Yong Peng, Johor | 011-33112738 | Jie_008@hotmail.com | 3 years | 1 year |  | Unitrade
2503586 | Safinaz Binti Mohd Sharif | 2025-03-14 | Patricia | R-PV | NEM | #VALUE! | 6.49 |  |  | 21500 |  | Cash | Outright | Astronergy 590Wp | 11 | Huawei SUN2000-5KTL-L1 |  | 670915-01-5984 | Lot 2298, Jalan Sg. Soi, Kg. Sepat, 25150 Penor, Pahang. | 012-9818637 | safinazsharif67@gmail.com | 3 years | 1 year |  | Ken
2503604 | Kong Chun Seng | 2025-03-17 | Tham | R-PV | NEM | #VALUE! | 9.44 |  |  | 27000 |  | Cash | Outright | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL |  | 950316-14-6321 | No 200, Jalan Colonial 6, Taman Colonial, 27600 Raub, Pahang | 019-9804663 | Chunseng950316@icloud.com | 3 years | 1 year
2503598 | Lew Yuen Tang | 2025-03-17 | Tham | R-PV | NEM | #VALUE! | 9.44 |  |  | 27000 |  | Cash | Outright | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL |  | 560915-10-5405 | 5, Jalan SS 22A/6, Damansara Jaya, 47400 Petaling Jaya, Selangor | 012-3309688 | pavirelew3@gmail.com | 3 years | 1 year |  | Unitrade
2503609 | Yau Hwee Tien | 2025-03-19 | Tham | R-PV | NEM | #VALUE! | 14.16 |  |  | 35000 |  | Cash | Outright | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL |  | 811024-01-5944 | 70, Jalan Kota Impian 2, Taman Kota Impian, 83700 Yong Peng, Johor | 016-7601468 | hweetien@hotmail.com | 3 years | 1 year |  | Unitrade
2503610 | Datuk Abdul Rani | 2025-03-24 | Tham | R-PV | NEM | #VALUE! | 17.7 |  |  | 43000 |  | Cash | Outright | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL |  | 730517-08-5321 | No 41, Jalan Frekuensi U16/118, Elmina East, 40160 Shah Alam, Selangor | 017-3777902 | iyadnifaelio@gmail.com | 3 years | 1 year
2503611 | Augustine Kok Hwai Nam | 2025-03-26 | Tham | R-PV | NEM | #VALUE! | 7.67 |  |  | 23500 |  | Cash | Outright | Astronergy 590Wp | 13 | Huawei SUN2000-6KTL |  | 640823-07-5309 | 68, Jln BU 12/6, Bandar Utama, 47800 Petaling Jaya, Selangor | 012-5017002 | augkok@gmail.com | 3 years | 1 year
2501524 | Jeremy Koo Wui Ken | 2025-03-28 | Tham | R-PV | NEM | #VALUE! | 9.44 |  |  | 27000 |  | Cash | Outright | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL |  | 810525-14-6833 | 17, Jln BU 11/6, Bandar Utama, 47800 Petaling Jaya, Selangor | 852-52392544 | jeremy6833@gmail.com | 3 years | 1 year
2503617 | Vinny Len Siew Meng | 2025-03-28 | Patricia | R-PV | NEM | #VALUE! | 17.7 |  |  | 41000 |  | Cash | Outright | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL |  | 870530-06-5450 | No 19, Jalan Rinba Jaya 3, Taman Rimba Jaya, 28400 Mentakab, Pahang | 012-2352813 | vinnylen@gmail.com | 3 years | 1 year
2503601 | William Song Jian Tat | 2025-03-28 | Tham | R-PV | NEM | #VALUE! | 9.44 |  |  | 29000 |  | Cash | Outright | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | [5 empty] | 3 years | 1 year
2503619 | Haslina binti Othman | Cancelled | Patricia |  |  |  | 7.08 |  |  | 21500 |  | Cash | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 670604-11-5048 | Lot 367, Jln Tg Lumpur, Kg Peramu, 26060 Kuantan, Pahang | 013-9480768 | ahbagency67@gmail.com | 3 years | 1 year
2504623 | Choy Poh Chu | 2025-04-03 | Patricia | R-PV | NEM | #VALUE! | 7.08 |  |  | 21500 |  | Cash | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 751103-06-5104 | No 42, Lrg Im 1/34, Bdr Indera Mahkota, 25200 Kuantan, Pahang | 017-8815769 | pohchuchoy@gmail.com | 3 years | 1 year
2503589 | Chong Shiuh Dyi | 2025-04-09 | Tham | R-PV | NEM | #VALUE! | 7.08 |  |  | 21500 |  | Cash | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 830419-14-5229 | No 143, Jln Bidara 1, Tmn Bidara, 68100 Batu Caves, Selangor | 010-4698765 | wanderingvirocana@gmail.com | 3 years | 1 year |  | Unitrade
2504633 | Yong Chee Seng | 2025-04-11 | Tham | R-PV | NEM | #VALUE! | 7.08 |  |  | 21500 |  | Cash | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 751025-04-5019 | 41, Jalan Aman Perdana 11K/KU5, Taman Aman Perdana, 41050 Klang, Selangor | 012-3888517 | hoongthyeengineering@gmail.com | 3 years | 1 year |  | Unitrade
2504636 | Nur Salinahany binti Hanafiah | 2025-04-11 | Patricia | R-PV | NEM | #VALUE! | 17.7 |  |  | 41000 |  | Cash | Outright | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL |  | 771124-02-6014 | 36645, Rumah Lot, Jln Lapangan Terbang, 26070 Kuantan | 010-4060484 | hanynajib7577@gmail.com | 3 years | 1 year
2406152 | Chara Sdn Bhd | 2025-04-07 | Simon | C&I-PV | NEM | #VALUE! | 93.17 |  |  | 155000 |  | Cash | PPA | Astronergy 605Wp | 154 | Huawei SN2000-40KTL + Huawei SUN2000-30KTL |  |  | 3, Jalan Majistret U1/26, Hicom Glenmarie Industrial Park, 40150 Shah Alam, Selangor |  |  | N/A | 1 year |  | Unitrade
2504640 | Ng Mong Ping | 2025-04-17 | Tham | R-PV | NEM | #VALUE! | 9.44 |  |  | 26000 |  | Cash | Outright | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL |  | 730122-01-5257 | 25, Jalan Panorama 7, Taman Kota Panorama, 83700 Yong Peng, Johor | 65-91388191 | mongping.ng@gmail.com | 3 years | 1 year
2504638 | Lai Boon Liong | 2025-04-17 | Tham | R-PV | NEM | #VALUE! | 9.44 |  |  | 27000 |  | Cash | Outright | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL |  | 791205-01-5083 | 1, Jalan Bayu 8, Taman Sri Bayu, 83700 Yong Peng, Johor | 012-4743089 | yap.sk@hotmail.com | 3 years | 1 year |  | Unitrade
2504652 | Khairul Hisham Bin Mohamed | 2025-04-19 | Patricia | R-PV | NEM | #VALUE! | 9.44 |  |  | 27500 |  | Cash | Outright | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL |  | 850301-06-5635 | 50, Taman PSJ, Lrg Sg Karang Darat 12, PKGN Sg Karang Darat, 26100 Kuantan, Pahang | 019-9709798 | khaimoha3720@gmail.com | 3 years | 1 year
2504647 | Tan Hock Cheng | 2025-04-20 | Patricia | R-PV | NEM | #VALUE! | 7.08 |  |  | 21500 |  | Cash | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 700325-01-5145 | No 20, Lrg Air Putih 102, Tmn Air Putih, Air Putih, 25300 Kuantan, Pahang | 019-9310567 | hvacrtan@gmail.com | 3 years | 1 year
2504658 | Phang Yeong Chin | 2025-04-22 | Ong | R-PV | NEM | #VALUE! | 7.08 |  |  | 22500 |  | Cash | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 780919-07-5404 | 62A, Jln USJ 12/1, UEP Subang Jaya, 47630 Subang Jaya, Selangor | 012-2965565 | phang_sk13@yahoo.com | 3 years | 1 year
2503614 | Yap Weoi Kee | Cancelled | Simon | [8 empty] | Cash | Outright | Astronergy 590Wp | 15 | Solax 8kW |  | 670103-10-6653 | 52, Jalan SL 4/2, Bandar Sungai Long, 43000 Kajang, Selangor | 019-3100965 | yapweoikee@gmail.com | N/A | 1 year
2504643 | Lee Sui Lian | 2025-04-25 | Patricia | R-PV | NEM | #VALUE! | 17.7 |  |  | 46700 |  | Credit Card Instalment | Outright | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL |  | 550331-04-5091 | E2010, Jln Mat Kilau, 25100 Kuantan, Pahang | 011-35339431 | kcwlcy0912@gmail.com | 3 years | 1 year
2504663 | Too Seng Eng | 2025-04-23 | Patricia | R-PV | NEM | #VALUE! | 7.08 |  |  | 22500 |  | Cash | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-6KTL-M1 |  | 690211-06-5017 | No 18, Lrg GE 2 Tmn Gemilang Emas-Sg Jan, 27000 Jeratut Pahang | 013-9816863 | kaixuantoo@gmail.com | 3 years | 1 year
2504671 | Anthony Phua Kin Loong | 2025-04-30 | Patricia | R-PV | NEM | #VALUE! | 17.7 |  |  | 41000 |  | Cash | Outright | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL |  | 860406-33-5573 | No 14, Jalan KS 12/8, Kota Sultan Ahmad Shah, 25200 Kuantan, Pahang | 016-9514838 | Anthony.phua.kl@gmail.com | 3 years | 1 year
2506644 | Chang Kok Sang (Chang Vun Yu) | 2025-05-05 | Tham | R-PV | NEM | #VALUE! | 7.08 |  |  | 21000 |  | Cash | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 510630-12-5175 | 43, Jln USJ 9/3P, UEP Subang Jaya, 47500 Subang Jaya, Selangor | 019-8606262 | clementchang@harrisons.com.my | 3 years | 1 year
2505675 | Tee Hup Soon | 2025-05-05 | Patricia | R-PV | NEM | #VALUE! | 15.34 |  |  | 42170 |  | Credit Card Instalment | Outright | Astronergy 590Wp | 26 | Huawei SUN2000-12KTL |  | 970830-56-5439 | No 2, Lorong Bukit Setongkol Baru 9, Perumahan Bukit Setongkol Baru, 25200 Kuantan, Pahang | 013-8040830 | thssoon@gmail.com | 3 years | 1 year |  |  |  | include smart meter
2502564 | Muhammad Arif Stephen bin Abddullah | 2025-05-06 | Simon | R-PV | NEM | #VALUE! | 17.7 |  |  | 43000 |  | Cash | Outright | Astronergy 590Wp | 30 | Solinteg MHT-12K-25 hybrid |  | 621102-10-7661 | Lot-1183A, Jalan Felcra, Kampung Batu 14, 43100 Hulu Langat, Selangor | 012-8888661 | capt.arifstephen@yahoo.com | 3 years | 1 year
2504664 | Law Meng Siong | 2025-05-09 | Patricia | R-PV | NEM | #VALUE! | 17.7 |  |  | 41000 |  | Cash | Outright | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL |  | 680623-06-5049 | Lot 13347, Bt 2 1-2 Jln Triang, 28200 Triang, Pahang | 019-9558682 | tskiansiong@gmail.com | 3 years | 1 year
2504651 | Teh Bat Kuan (Teh Eng Lim) | 2025-05-09 | Tham | R-PV | NEM | #VALUE! | 14.16 |  |  | 35000 |  | Cash | Outright | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL |  | 580406-08-5985 | PT 1467, Regat Th 2, Taman Taiping Harmoni, 34000 Taiping, Perak | 012-52211111 | office.tehtehdev@gmail.com | 3 years | 1 year |  | Unitrade
2504049 | Ayer Keroh R&R (Southbound) - Green EV Charge Sdn Bhd | 2025-05-09 | Simon | EV Charger |  | #VALUE! |  | 60 |  | 45015 |  | Cash | Outright | - | - | -
2505686 | Lai Kwee Far | 2025-05-13 | Patricia | R-PV | NEM | #VALUE! | 7.08 |  |  | 21500 |  | Cash | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 631106-05-5079 | 20, Lrg Kurnia Jaya 3, Pkg Kurnia Jaya 1, 25150 Kuantan, Pahang | 010-9831963 | liewbonnie67@gmail.com | 3 years | 1 year
2503603 | Dr Balbinder Singh a/l Gurbaksh Singh | 2025-05-14 | Tham | R-PV | NEM | #VALUE! | 17.7 |  |  | 43400 |  | Credit Card Instalment | Outright | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL |  | 680315-07-5317 | 41, Jalan Tempinis 1, Taman Lucky, Bangsar, 59100 Kuala Lumpur, WP Kuala Lumpur | 012-2134001 | kgbill15@yahoo.com | 3 years | 1 year
2302004 | Ong Ah Chai | 2025-05-14 | Chean Bang | R-PV | NEM | #VALUE! | 8.85 |  |  | 27500 |  | Credit Card Instalment | Outright | Astronergy 590Wp | 15 | Huawei SUN2000-8KTL |  |  | 1, Lrg Galing 18, 25300 Kuantan, Pahang |  |  | N/A | 1 year
2503225 | Weller Air-Cond Parts Enterprise Sdn Bhd | 2025-05-14 | Tham | C&I-PV | NEM | #VALUE! | 97.6 |  |  | 198800 |  | Cash | Outright | Astronergy 610Wp | 160 | Huawei SUN2000-50KTL + SUN2000-20KTL | [5 empty] | 3 years | 1 year
2403185 | Wan Kong Wing | 2025-05-15 | Tham | R-PV | NEM | #VALUE! | 7.08 |  |  | 21500 | -1416 | Cash | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 640707-08-5227 | 21, JLN UNGU U9/29A, CAHAYA SPK, SEK U9, 40150 SHAH ALAM, SELANGOR | 012-3788234 | kwwan07@yahoo.com | 3 years | 1 year |  | Unitrade
2410194 | Berjayapak Sdn Bhd | 2025-05-15 | Tham | C&I-PV | NEM | #VALUE! | 207.08 |  |  | 395000 |  | Cash | Outright | Yingli Solar 620Wp | 334 | Huawei SUN2000-50KTL + SUN2000-20KTL
2504669 | Zohairen Bin Mhamad Sori | 2025-05-16 | Tham | R-PV | NEM | #VALUE! | 10.62 |  |  | 29000 |  | Cash | Outright | Astronergy 590Wp | 18 | Huawei SUN2000-8KTL |  | 691107-04-5475 | 59, JLN KELAB UKAY, TMN KELAB UKAY, BKT ANTARABANGSA, 68000 AMPANG, SELANGOR | 014-6269711 | zohairen@gmail.com | 3 years | 1 year |  | Facebook
2504660 | Roshahni Binti Mhammad | 2025-05-16 | Chean Bang | R-PV | NEM | #VALUE! | 14.75 |  |  | 34000 |  | Cash | Outright | Astronergy 590Wp | 25 | Huawei SUN2000-12KTL |  | 670308-03-5318 | 6, Lrg Galing 28, 25300 Kuantan, Pahang | 011-55032998 | nanimuhammad67@gmail.com | N/A | 1 year
2410191 | Jowee Trading Sdn Bhd | 2025-05-16 | Tham | C&I-PV | NEM | #VALUE! | 53.68 |  |  | 150000 |  | Cash | Outright | Astronergy 620Wp | 88 | Huawei SUN2000-20KTL x 2 | [5 empty] | 3 years | 1 year |  | Unitrade
2505695 | Nur Salwahani Bt Muhammad | 2025-05-20 | Patricia | R-PV | NEM | #VALUE! | 9.44 |  |  | 27000 |  | Cash | Outright | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL |  | 780205-11-5670 | No 15, Lrg Im 15/7, Tmn Astana View, 25300 Kuantan, Pahang | 013-9082165 | norsalwahanimuhammad2003@gmail.com | 3 years | 1 year
2505672 | Tham Wai Hong | 2025-05-20 | Patricia | R-PV | NEM | #VALUE! | 8.85 |  |  | 27000 |  | Cash | Outright | Astronergy 590Wp | 15 | Huawei SUN2000-8KTL |  | 730725-06-5069 | 7, Lrg Air Putih 51, 25300 Kuantan, Pahang | 012-3666363 | mysamwht@gmail.com | 3 years | 1 year |  |  |  | include smart meter
2505684 | Ng Heng Hock | 2025-05-20 | Patricia | R-PV | NEM | #VALUE! | 11.21 |  |  | 30000 |  | Cash | Outright | Astronergy 590Wp | 19 | Huawei SUN2000-10KTL |  | 771118-02-5875 | 1884, Lrg Alor Akar 46, Tmn Impiana, 25300 Kuantan, Pahang | 019-9523822 | xingen150305@gmail.com | 3 years | 1 year
2505697 | Chong Yee Sam | 2025-05-20 | Patricia | R-PV | NEM | #VALUE! | 7.08 |  |  | 21500 |  | Cash | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 870913-38-5355 | B3394, Lrg Galing 143, Air Putih, 25020 Kuantan, Pahang | 010-4080727 | sam2chong@gmail.com | 3 years | 1 year
2505688 | Heng Mooi Sing | 2025-05-20 | Tham | R-PV | NEM | #VALUE! | 16.52 |  |  | 40000 |  | Cash | Outright | Astronergy 590Wp | 28 | Huawei SUN2000-12KTL |  | 771008-08-7020 | 33, Garden Manor, Sierramas, 47000 Sungai Buloh, Selangor | 012-6510878 | asam1008@hotmail.com | 3 years | 1 year
2505682 | Lee Soo Kean | 2025-05-20 | Patricia | R-PV | NEM | #VALUE! | 13.42 |  |  | 36620 |  | Credit Card Instalment | Outright | Astronergy 610Wp | 22 | Huawei SUN2000-10KTL |  | 650615-07-5151 | No 1, Lrg Im 1/61, Tmn Mahkota Ceria, 25200 Kuantan Pahang | 013-9377981 | sklee0665@gmail.com | 5 years | 1 year
2505699 | Kiren Kaur A/P Bhajan Singh | 2025-05-21 | Chean Bang | R-PV | NEM | #VALUE! | 11.8 |  |  | 33000 |  | Cash | Outright | Astronergy 590Wp | 20 | Huawei SUN2000-10KTL |  | 820207-08-5886 | No 11, Lrg Kubang Buaya 7, 25250 Kuantan, Pahang | 012-4056292 | kirenkaurbraich@gmail.com
2503612 | Low Bok Tek | 2025-05-21 | Tham | R-PV | NEM | #VALUE! | 17.7 | [5 empty] | Outright | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL |  | 580321-08-5097 | 39, Bayu Utara Seri Pilmoor, Jln PJU 1A/20, 43701 Petaling Jaya, Selangor | 019-4799999 | btcap@hotmail.com
2505680 | Chiang Hock Chiong | 2025-05-21 | Patricia | R-PV | NEM | #VALUE! | 17.7 |  |  | 41000 |  | Cash | Outright | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL |  | 680101-03-8297 | 15, Lorong Pelindung 3, Persisiran Residences Bukit Pelindung, 25050 Kuantan, {ahang | 012-9085551 | isaaczack@yahoo.com
2503607 | Goh Boon Leng | 2025-05-23 | Tham | R-PV | NEM | #VALUE! | 10.62 |  |  | 29000 |  | Cash | Outright | Astronergy 590Wp | 18 | Huawei SUN2000-8KTL |  | 791028-01-5655 | 116, Jalan 20/7, Taman Paramount, 46300 Petaling Jaya, Selangor | 016-6629044 | boonlg@gmail.com | 3 years | 1 year |  | Unitrade
2505711 | Lee Len Foong | 2025-05-27 | Chean Bang | R-PV | NEM | #VALUE! | 8.26 |  |  | 25500 |  | Cash | Outright | Astronergy 590Wp | 14 | Huawei SUN2000-6KTL |  | 631030-06-5122 | No 16, Lrg Bukit Setongkol 171, 25200 Kuantan, Pahang | 016-5299174 | EEKIENLOONG96@GMAIL.COM | 3 years | 1 year
2505713 | Yap Swee Piau | 2025-05-28 | Patricia | R-PV | NEM | #VALUE! | 17.7 |  |  | 41000 |  | Cash | Outright | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL |  | 890301-14-6351 | No. 9, Jalan KS 12/8, Kota Sultan Ahmad Shah, 25200 Kuantan, Pahang | 016-6905690 | darickyap@gmail.com | 3 years | 1 year
2505714 | Kong King Wai | 2025-05-29 | Tham | R-PV | NEM | #VALUE! | 7.08 |  |  | 22500 |  | Cash | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 811005-08-5461 | 22A, Jln Segar Perdana 4/7, Tmn Segar Perdana, 43200 Batu 11 Cheras, Selangor | 017-8775160 | kwkong555@gmail.com | 3 years | 1 year
2405306 | Leong Ah Seng | 2025-05-29 | Tham | R-PV | NEM | #VALUE! | 17.7 |  |  | 43000 | 7000 | Cash | Outright | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL |  | 570405-71-5931 | 22, Jln PJU 3/12, Tropicana Indah, 47410 Petaling Jaya, Selangor | 012-2809511 | alicia@rossi.com.my | 3 years | 1 year
2505705 | Lee Kee Chew | 2025-05-30 | Tham | R-PV | NEM | #VALUE! | 7.08 |  |  | 21500 |  | Cash | Outright | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 570906-08-6555 | 18, Jalan SS 22/28, Damansara Jaya, 47400 Petaling Jaya, Selangor | 019-3111662 | simonlee1@yahoo.com | 3 years | 1 year
2505717 | Sia Wee Leng | 2025-06-03 | Tham | R-PV | NEM | #VALUE! | 16.52 |  |  | 42000 |  | Credit Card Instalment | Outright | Astronergy 590Wp | 28 | Huawei SUN2000-12KTL |  | 700101-10-7323 | No 3, Jln Rimbunan Melor 9, Laman Rimbunan Kepong, 52100 Kuala Lumpur, WP Kuala Lumpur | 012-3862832 | lgfswl@gmail.com | 3 years | 1 year
2505699-1 | Leong Wai Wung | 2025-06-04 | Tham | R-PV | NEM | #VALUE! | 11.8 |  |  | 32000 |  | Cash | Outright | Astronergy 590Wp | 20 | Huawei SUN2000-10KTL
2505719 | Lim Jun Hong | 2025-06-04 | Tham | R-PV | NEM | #VALUE! | 11.78 |  |  | 27000 |  | Cash | Outright | Astronergy 620Wp | 19 | Huawei SUN2000-10KTL |  | 940611-08-5059 | No 7, Jln USJ 3A/8, 47680 Subang Jaya, Selangor | 016-6679002 | limjh.611@gmail.com | N/A | 2 years
2505687 | Thayananthan A/L Lokanatan | 2025-06-06 | Patricia | R-PV | NEM | #VALUE! | 10.03 |  |  | 30000 |  | Cash | Outright | Astronergy 590Wp | 17 | Huawei SUN2000-8KTL |  | 880603-06-5259 | No 3, Lrg Im 21/4, Perumahan Taman Indera Mahkota 21, 25200 Kuantan, Pahang | 016-7252108 | avith2309@gmail.com | N/A | 1 year
2505718 | Koh Kheat Kian | 2025-06-07 | Chean Bang | R-PV | NEM | #VALUE! | 7.44 |  |  | 23500 |  | Cash | Outright | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-M1 |  | 800626-06-5187 | 51, Jln Bkt Setongkol 3, Tmn Muhibah Fasa 2, Bukit Setongkol, 25200 Kuantan, Pahang | 012-9502255 | kk5k@yahoo.com | 3 years | 2 years
2506726 | Poh Pun Hong | 2025-06-08 | Ong | R-PV | NEM | #VALUE! | 7.44 |  |  | 22000 |  | Cash + CC Instalment | Outright | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 651214-10-6548 | 11, Jalan Sg 1/14, Taman Sri Gombak, 68100 Batu Caves. Selangor | 012-8856276 | briancmf940921@gmail.com | 3 years | 2 years
2506735 | Lee Meng Fui | 2025-06-09 | Patricia | R-PV | NEM | #VALUE! | 7.44 |  |  | 19000 |  | Cash | Outright | Astronergy 610Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 770221-06-5395 | 32, Lrg Tiram Aman 3, Perumahan Tiram Aman. 25200 Kuantan, Pahang | 012-9589956 | calvinleemf@gmail.com | N/A | 1 year
2506734 | Leow Siew Lian (Tee Hong Yee) | 2025-06-09 | Patricia | R-PV | NEM | #VALUE! | 11.16 |  |  | 25500 |  | Cash | Outright | Astronergy 610Wp | 18 | Huawei SUN2000-8KTL |  | 670130-06-5156 | No 7, Lrg Pelindung Pantai 11 Kg Pelindu, Tmn Pantai Pelindung 26100 Berserah, Pahang | 017-8911268 | zhixuanx23@gmail.com | N/A | 1 year
2505708 | Mohd Shariff | 2025-06-10 | Tham | R-PV | NEM | #VALUE! | 7.44 |  |  | 20500 |  | Cash | Outright | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1
2506744 | Gan Chin Sam | 2025-06-10 | Tham | R-PV | NEM | #VALUE! | 14.88 |  |  | 32500 |  | Cash | Outright | Astronergy 620Wp | 24 | Huawei SUN2000-12KTL |  | 580625-05-5241 | 67, Jalan PJU 1A/36, Ara Damansara, 47301 Petaling Jaya, Selangor | 019-3344789 | csamgan@gmail.com | 3 years | 2 years
2506727 | Tan Lee Khing | 2025-06-11 | Patricia | R-PV | NEM | #VALUE! | 12.4 |  |  | 28300 |  | Cash | Outright | Astronergy 620Wp | 20 | Huawei SUN2000-10KTL |  | 790523-10-5186 | 2, Lorong Bukit Setongkol Baru 10, Perumahan Bukit Setongkol Baru, 25200 Kuantan, Pahang | 012-2280130 | lee_khing@yahoo.com | N/A | 3 years
2505054 | DK Senza Residence | 2025-06-01 | Simon | EV Charger |  | #VALUE! |  | 44 |  | 59345 |  |  | Outright | - | - | - | [5 empty] | N/A
2506752 | Ng Cheng Hoe | 2025-06-13 | Tham | R-PV | NEM | #VALUE! | 7.44 |  |  | 22500 |  | Cash | Outright | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 881016-43-5205 | No. 5, Jalan Setia Utama U13/39D, Setia Alam, Seksyen U13, 40170 Shah Alam, Selangor | 013-7882286 | nevets8816@gmail.com | 3 years | 2 years
2501523 | Chen Kim Hock | 2025-06-13 | Tham | R-PV | NEM | #VALUE! | 17.7 |  |  | 44880 |  | Cash | Outright | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL |  | 601117-02-5513 | 37A, Jln Jingga 4, Tmn Pelangi, 80400 Johor Bahru, Johor | 014-7774333 | chenyeonhao@gmail.com | 3 years | 1 year |  | Unitrade
2506748 | Teh Foo Hock | 2025-06-16 | Patricia | R-PV | NEM | #VALUE! | 8.68 |  |  | 22500 |  | Cash | Outright | Astronergy 620Wp | 14 | Huawei SUN2000-8KTL |  | 650714-06-5055 | B3410, Lrg Galing 143, Air Putih, 25020 Kuantan, Pahang | 012-9839222 |  | N/A | 2 years
2505709 | Tan Heng Lian | 2025-06-16 | Patricia | R-PV | NEM | #VALUE! | 17.98 |  |  | 39000.4 |  | Credit Card Instalment | Outright | Astronergy 620Wp | 29 | Huawei SUN2000-12KTL |  | 780921-06-5117 | 31, Lrg Sri Kuantan 63, Taman Sri Kuantan, 25250 Kuantan, Pahang | 016-9619998 | Kuzo836@gmail | 3 years | 2 years
2501531 | Mohamad Hafizi Bin Abdul Rahman | 2025-06-17 | Patricia | R-PV | NEM | #VALUE! | 13.64 |  |  | 30500 |  | Cash | Outright | Astronergy 620Wp | 22 | Huawei SUN2000-10KTL |  | 741213-08-6337 | No 25, Lrg Bandar Damansara Kuantan 1/17, Bdr Damansara Kuantan, 26100 Kuantan, Pahang | 019-9569774 | datobulat@gmail.com | 5 years | 2 years
2506757 | Chai Cheong Sing | 2025-06-18 | Patricia | R-PV | NEM | #VALUE! | 7.44 |  |  | 21500 |  | Cash | Outright | Astronergy 620Wp | 12 | Huawei SUN2000-6KTL-M1 |  | 720125-01-5261 | 13, Lrg Seri Setali 10 Off, Jln Galing Ke, Tmn Sri Galing, 25300 Kuantan, Pahang | 012-7223686 | johnchai72@yahoo.com | 3 years | 2 years
2505259 | Liew Wen Qi | 2025-06-18 | Patricia | C&I-PV | NEM | #VALUE! | 19.52 |  |  | 45000 |  | Cash | Outright | Astronergy 610Wp | 32 | Huawei SUN2000-17KTL |  |  | A65 Bwh, Jln Seri Setali 2 Off Jln Air Putih, 25300 Kuantan, Pahang | 012-2691162 | wenqi_liew@hotmail.com | N/A | 1 year
2506758 | Goh Boon Meng | 2025-06-19 | Patricia | R-PV | NEM | #VALUE! | 17.98 |  |  | 39500 |  | Credit Card Instalment | Outright | Astronergy 620Wp | 29 | Huawei SUN2000-12KTL |  | 681204-06-5137 | No 6, Jln Mawar 6, Tmn Mawar, 28300 Triang, Pahang | 012-2429688 | gbm8869@gmail.com | 3 years | 2 years
2506762 | Megat Mohd Nashrul Bin Ahmad Zulkepli | 2025-06-20 | Patricia | R-PV | NEM | #VALUE! | 12.4 |  |  | 32500 |  | Cash | Outright | Astronergy 620Wp | 20 | Huawei SUN2000-10KTL |  | 851019-01-6703 | No 11, Lrg Im 8/24, Bandar Indera Mahkota, Indera Mahkota, 25200 Kuantan, Pahang | 013-6803366 | megat@nexgentechaus.com | 3 years | 2 years
2506753 | Lim Geok Suan | 2025-06-20 | Patricia | R-PV | NEM | #VALUE! | 11.78 |  |  | 27500 |  | Cash | Outright | Astronergy 620Wp | 19 | Huawei SUN2000-10KTL |  | 560421-07-5234 | No 65 A, Lrg Sekilau 22, Bkt Sekilau, 25200 Kuantan, Pahang | 012-9093055 | dinamikbudimas@gmail.com | 3 years | 2 years
2506768 | Yap Lee Yan | 2025-06-20 | Patricia | R-PV | NEM | #VALUE! | 11.16 |  |  | 27000 |  | Cash | Outright | Astronergy 620Wp | 18 | Huawei SUN2000-10KTL |  | 830913-06-5080 | No 12, Lrg Bukit Ubi 59, Perumahan Galing, 25200 Kuantan, Pahang | 017-9898860 | yenyen6513@gmail.com | 3 years | 2 years
2506761 | Lee Swee Li | 2025-06-23 | Patricia | R-PV | NEM | #VALUE! | 13.64 |  |  | 34000 |  | Credit Card Instalment | Outright | Astronergy 620Wp | 22 | Huawei SUN2000-12KTL |  | 730801-05-5074 | B913, Lrg Air Putih 25, Tmn Sentosa, 25350 Kuantan, Pahang | 012-9882982 | jennylee3668@gmail.com | 3 years | 2 years
2506779 | Koo Hing Yew | 2025-06-23 | Patricia | R-PV | NEM | #VALUE! | 7.44 |  |  | 20500 |  | Cash | Outright | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 600610-06-5215 | No. 9, Lorong Im 21/12, Perumahan Taman Indera Mahkota 21, 25200 Kuantan, Pahang | 017-3311266 | koojayaenterprise@gmail.com | 3 years | 2 years
2506781 | Teng Lily | 2025-06-23 | Patricia | R-PV | NEM | #VALUE! | 7.44 |  |  | 22000 |  | Credit Card Instalment | Outright | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 901117-06-5050 | 31, Jln Bkt Setongkol 3, Tmn Muhibah Fasa, Bukit Setongkol 25200 Kuantan,Pahang | 012 - 7887991 | lilyteng_5050@hotmail.com | 3 years | 2 years
2506782 | Tan Shu Huat | 2025-06-23 | Patricia | R-PV | NEM | #VALUE! | 14.88 |  |  | 36100 |  | Cash + CC Instalment | Outright | Astronergy 620Wp | 24 | Huawei SUN2000-12KTL |  | 760905-06-5397 | 137, Lrg Bkt Setongkol Perdana 52, Tmn Fairmont Jaya, 25200 Kuantan, Pahang | 016-9223663 | singhuatmotortrd@gmail.com | 3 years | 2 years
2506746 | Tan Wan Ngee | 2025-06-23 | Patricia | R-PV | NEM | #VALUE! | 9.92 |  |  | 24000 |  | Cash | Outright | Astronergy 620Wp | 16 | Huawei SUN2000-8KTL |  | 760607-06-5364 | No 6, Lorong Pelindung 2, Persisiran Residences Bukit Pelindung, 25050 Kuantan, Pahang | 016 - 9222888 |  | N/A | 2 years
2506780 | Yeo Khai Boon | 2025-06-23 | Patricia | R-PV | NEM | #VALUE! | 9.92 |  |  | 23800 |  | Cash | Outright | Astronergy 620Wp | 16 | Huawei SUN2000-8KTL |  | 000207-06-0319 | No 9, Jalan KS 5/14, Evergreen III @ Presint 5, Kotasas, 25200 Kuantan, Pahang | 019-7046189 | ahwen000207@hotmail.com | N/A | 2 years
2506778 | Teo Lun Wei | 2025-06-23 | Patricia | R-PV | NEM | #VALUE! | 7.44 |  |  | 20500 |  | Cash | Outright | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 940421-06-5073 | No 26, Lorong Tas Perdana 3, Perumahan Tas Perdana, 25150 Kuantan Pahang | 010 - 7696618 |  | 3 years | 2 years
2506745 | Lee Ban Hong | 2025-06-15 | Tham | R-PV | NEM | #VALUE! | 14.88 |  |  | 32500 |  | Cash | Outright | Astronergy 620Wp | 24 | Huawei SUN2000-12KTL |  | 860910-56-6071 | 67, Jalan 2/C, Taman Jati, 48000 Rawang, Selangor | 018-2526174 | hueiya-lee97@hotmail.com | 3 years | 2 years
2506789 | Wu Sio Yunn | 2025-06-25 | Patricia | R-PV | NEM | #VALUE! | 9.92 |  |  | 27130 |  | Credit Card Instalment | Outright | Astronergy 620Wp | 16 | Huawei SUN2000-8KTL |  | 680925-06-5044 | D-278, Lrg Bukit Setongkol 211, Tmn Bukit Setongkol, 25200 Kuantan, Pahang | 013-9848650 | irenewsy@hotmail.com | 3 years | 2 years
2404254 | Meor Farizal Bin Ramli | 2025-06-25 | Chean Bang | R-PV | SELCO | #VALUE! | 5.58 |  |  | 19500 |  | Cash | Outright | Astronergy 620Wp | 9 | Huawei SUN2000-5KTL-L1 |  | 810605-10-6153 | Lot 1433, Jln Merpati Kg Dato Ahmad Said, 30020 Ipoh, Perak | 012-5098235 | wan_8807@yahoo.com.my | 3 years | 2 years
2506732 | Chai Shwu Yi (Tan Lewin) | 2025-06-25 | Simon | R-PV | NEM | #VALUE! | 7.44 |  |  | 20500 |  | Cash | Outright | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 860913-43-6870 | 3, Jalan Mahligai 2A, Bandar Bukit Raja, 41050 Klang, Selangor | 012-2431712 | c.shwu.yi@gmail.com | 3 years | 2 years
2506767 | Lee Lee Tan @ Tan Lee Lee | 2025-06-25 | Tham | R-PV | NEM | #VALUE! | 7.44 |  |  | 20500 |  | Cash | Outright | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 681204-10-6242 | 32, Jalan SL 13/3, Bandar Sungai Long, 43000 Kajang Selangor | 012-2293778 | lilyt8793@gmail.com | 3 years | 2 years
2506759 | Yim Kai Mun | 2025-06-26 | Patricia | R-PV | NEM | #VALUE! | 10.54 |  |  | 27000 |  | Cash | Outright | Astronergy 620Wp | 17 | Huawei SUN2000-8KTL |  | 531231-05-5387 | 4, Lrg Pelindung 32, Tmn Pelindung, 25250 Kuantan, Pahang | 019 - 9518264 | johnnie.why@gmail.com | 3 years | 2 years
2506794 | Ahmad Fadhil Bin Alias | 2025-06-26 | Patricia | R-PV | NEM | #VALUE! | 9.92 |  |  | 25000 |  | Cash | Outright | Astronergy 620Wp | 16 | Huawei SUN2000-8KTL |  | 790130-11-5113 | No 16, Lrg Pelindung Damai 26 Villa, Pelindung Indah, Beserah, 26100 Kuantan, Pahang | 014-5301886 |  | 3 years | 2 years
2506798 | Lew Sieow Shih | 2025-06-26 | Patricia | R-PV | NEM | #VALUE! | 7.44 |  |  | 20500 |  | Cash | Outright | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 780528-06-5196 | D975, Jln Kg Jawa, Tmn Sri Berlian, 25200 Kuantan, Pahang | 012 - 9554526 |  | 3 years | 2 years
2506773 | Leiw Chew Choi | 2025-06-26 | Patricia | R-PV | NEM | #VALUE! | 14.88 |  |  | 32500 |  | Cash | Outright | Astronergy 620Wp | 24 | Huawei SUN2000-12KTL |  | 641010-06-5028 | No 18, Lorong Pelindung 2, Persisiran Residences Bukit Pelindung, 25050 Kuantan, Pahang | 012 - 9856616 |  | 3 years | 2 years
2506789-1 | Lim Kim Kiew | 2025-06-26 | Chean Bang | R-PV | NEM | #VALUE! | 7.44 |  |  | 20500 |  | Cash | Outright | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 |  | 620525-11-5212 | 48, Lrg Air Putih 3 Jln Air Puith, Tmn Seri Maju, 25300 Kuantan, Pahang | 019-9629183 | lucaslim930@gmail.com | 3 years | 2 years
2506786 | Lim Chee Seng | 2025-06-28 | Tham | R-PV | NEM | #VALUE! | 13.64 |  |  | 30500 |  | Cash | Outright | Astronergy 620Wp | 22 | Huawei SUN2000-12KTL |  | 721110-14-5287 | NO DST11, JLN JEREJAK, TMN SETAPAK, 53000 WP KUALA LUMPUR | 019-2235411 | vincent7283@gmail.com | 3 years
2505260 | Canning Garden Baptist Church | 2025-06-25 | Patricia | C&I-PV | NEM | #VALUE! | 48.36 |  |  | 95000 |  | Cash | Outright | Astronergy 620Wp | 78 | Huawei SUN2000-36KTL |  | - | 3, Lal Lee Kwee Foh, Tmn Canning, 31400 Ipoh, Perak | 05-5468480 | cgbc.ipoh@gmail.com | 3 years | 1 year
2506799 | Lee Cheow Ban | 2025-06-27 | Patricia | R-PV | NEM | #VALUE! | 13.64 |  |  | 30500 |  | Cash | Outright | Astronergy 620Wp | 22 | Huawei SUN2000-12KTL |  | 690614-06-5011 | No E 1111, Jln Darat Makbar, 25100 Kuantan | 017 - 9353338 |  | 3 years | 2 years
2506276 | Tew Ah Sing @ Teo Ah Sing | 2025-06-28 | Chean Bang | R-PV | NEM | #VALUE! | 19.84 |  |  | 40000 | -1000 | Cash | Outright | Astronergy 620Wp | 32 | Huawei SUN2000-17KTL
2506785 | Mohd Nurazuwan Bin Radzi | 2025-06-29 | Patricia | R-PV | NEM | #VALUE! | 13.64 |  |  | 34500 |  | Cash | Outright | Astronergy 620Wp | 22 | Huawei SUN2000-12KTL |  | 860517-23-6463 | No 3, Lrg Tmn Beserah 28, Tmn Beserah, 26100 Kuantan, Pahang | 016-7794494 | nurazuwan.petrofarm@gmail.com | 3 years | 2 years
2506801 | Lim Joo Eng | 2025-06-30 | Patricia | R-PV | NEM | #VALUE! | 17.98 |  |  | 39500 |  | Credit Card Instalment | Outright | Astronergy 620Wp | 29 | Huawei SUN2000-12KTL |  | 520920-10-5796 | 6, Lrg Seri Teruntum 134 Jln Wong Ah Jan, 25100 Kuantan, Pahang | 012-9392331 | gigityng85@yahoo.com | 3 years | 2 years
2503223 | Insultec Duragate Sdn Bhd | 2025-06-24 | Tham | C&I-PV | NEM | #VALUE! | 58.9 |  |  | 117500 |  | Cash | Outright | Yingli Solar 620Wp | 95 | Huawei SUN2000-50KTL | [5 empty] | 3 years
2506802 | Hung Wen Hao | 2025-06-30 | Patricia | R-PV | NEM | #VALUE! | 13.64 |  |  | 31500 |  | Cash | Outright | Astronergy 620Wp | 22 | Huawei SUN2000-12KTL |  | 980309-10-6169 | No 21, Lorong Sekilau 1/1, Perumahan Bukit Sekilau 1, 25200 Kuantan, Pahang | 011-1166669 |  | 3 years | 2 years
2412510 | How Toon Huah | 2025-07-05 | Chean Bang | R-PV | NEM | #VALUE! | 14.88 |  |  | 34000 |  | Credit Card Instalment | Outright | Astronergy 620Wp | 24 | Huawei SUN2000-12KTL |  | 560127-06-5094 | Lot 10991, Lrg Kubang Buaya 77, 25050 Kuantan, Pahang | 012-9883639 | hsmei30@yahoo.com | 3 years | 2 years
2504051 | G. Semanggol R&R (Northbound) - Green EV Charge Sdn Bhd | 2025-06-25 | Simon | EV Charger |  | #VALUE! |  | 240 |  | 250000 |  | Cash | Outright | [8 empty] | N/A
2505056 | TMG Mall Tanjung Lumpur (Handal Green Mobility) | 2025-07-21 | Chean Bang | EV Charger |  | #VALUE! |  | 60 |  | 43000 |  | Cash | Outright | [8 empty] | N/A
2507833 | Yee Main Way | 2025-08-05 | Patricia | R-PV | SELCO | #VALUE! | 12.4 |  | 15 | 46000 |  | Cash + CC Instalment | Outright | Astronergy 620Wp | 20 | Solax 10kW |  | 700220-05-5423 | No 19 B, Lrg Galing 23 Off, Jln Hj Ahmad,Tmn Hj Ahmad Mewah, 25300 Kuantan Town, Pahang | 017-9866683 |  | N/A | 2 years
2409030 | TMG Mall Bandar Indera Mahkota (Handal Green Mobility) | 2025-08-12 | Chean Bang | EV Charger |  | #VALUE! |  | 60 |  | 58000 |  | Cash | Outright | [8 empty] | N/A
2507059 | TMG Mall IM16 (Handal Green Mobility) | 2025-08-12 | Chean Bang | EV Charger |  | #VALUE! |  | 60 |  | 53000 |  | Cash | Outright | [8 empty] | N/A
2507060 | TMG Mall Temerloh (Handal Green Mobility) | 2025-08-12 | Chean Bang | EV Charger |  | #VALUE! |  | 60 |  | 55500 |  | Cash | Outright | [8 empty] | N/A
2508858 | Chan Weng Leong | 2025-08-26 | Patricia | R-PV | SELCO | #VALUE! | 16.12 |  | 15 | 49000 | 1593 | Cash | Outright | Astronergy 620Wp | 26 | Solax 12kW |  | 810123-10-6089 | 37, Jalan Mulia 9, Taman Mulia, 42700 Banting, Selangor | 016-9689365 |  | 3 years | 2 years
2507062 | Tapah R&R (Southbound) - Green EV Charge Sdn Bhd | 2025-08-09 | Simon | EV Charger |  | #VALUE! |  | 240 |  | 324360 |  | Cash | Outright | [8 empty] | N/A
2509863 | Goh Soon Teck | 2025-09-29 | Patricia | R-PV | SELCO | #VALUE! | 9.92 |  |  | 27000 |  | Cash | Outright | Astronergy 620Wp | 16 | Solax 7.5kW |  | 640915-06-5415 | No 51, Jln Bkt Setongkol 8, Tmn Sri Setongkol, 25200 Kuantan, Pahang | 016-9231811 |  | N/A | 2 years
2507840 | Chew Kok leong | 2025-09-19 | Patricia | R-PV | SELCO | #VALUE! | 15.5 |  | 30 | 63000 |  | Cash + CC Instalment | Outright | Astronergy 620Wp | 25 | Solax 12kW |  |  | 376, Jalan Kg. Kolong Pahat, Kg. Kolong Pahat, 26200 Sg. Lembing, Pahang |  |  | N/A | 2 years
2508857 | Chong Horng Tat | 2025-10-10 | Ong | R-PV | SELCO | #VALUE! | 8.68 |  | 15 | 49800 |  | Cash | Outright | Astronergy 620Wp | 14 | Solax 8kW |  | 851029-14-6341 | No 92, Mutiara Villa, Jalan Mutiara 6, Mutiara Heights, 43000 Kajang, Selangor | 016-2427853 |  | N/A | 2 years
2305008 | Yeap Chooi Hock | 2025-10-28 | Patricia | C&I-PV | SELCO | #VALUE! | 17.98 |  | 30 | 63773.58 |  | Cash + CC Instalment | Outright | Astronergy 620Wp | 29 | Solax 15kW |  | 621017-08-6085 | No 65, Jalan Sri Jaya 5-1, Taman Bukit SR, 26500 Maran, Pahang |  |  | N/A | 2 years
2508856 | Eddie Leong Kai Sheng | 2025-10-28 | Ong | R-PV | SELCO | #VALUE! | 18.6 |  | 29.95 | 73500 |  | Cash | Outright | Astronergy 620Wp | 30 | Fox ESS 12kW |  | K5404484K | No 22, Jalan KS 7/1, Kota Sultan Ahmad Shah 7, 25200 Kuantan, Pahang | +65 90629902 |  | N/A | 2 years
2510877 | Wang Pay Chen | 2025-11-03 | Patricia | R-PV | SELCO | #VALUE! | 9.92 |  |  | 28500 |  | Cash | Outright | Astronergy 620Wp | 16 | Solax 8kW |  | 790603-11-5042 | PT3665, Jalan Apps 1/5, Taman Alam Perdana, 24000 Kemaman, Terengganu | 017-9869863 |  | N/A | 2 years
2511887 | Lee Hang Meng | 2025-11-09 | Patricia | R-PV | SELCO | #VALUE! | 12.4 |  |  | 29000 |  | Cash | Outright | Astronergy 620Wp | 19 | Fox ESS 10kW |  | 700815-06-5057 | No 23, Lrg Galing 27, Tmn Sri Tahan, 25300 Kuantan, Pahang | 012-9873327 |  | N/A | 2 years
2305019 | Soe Yew Seng | 2025-10-30 | Simon | R-PV | SELCO | #VALUE! | 15.5 |  | 29.95 | 60000 |  | Cash | Outright | Astronergy 620Wp | 25 | Fox ESS 12kW |  | 680303-10-5531 | No 117, Lebuh Berangan, 42000 Klang, Selangor | 017-3035058 |  | N/A | 2 years
Note on L59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: RSA VO = RM 2,500 Lights Deduction = - RM 1,000
Note on B71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ST Login details: sleepmaticssdnbhd@gmail.com Abcd1234
Note on B72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ST Login: Username: chlfoamsdnbhd@gmail.com Password: Abcd1234
Note on B247: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ST Portal Login: Username: meishunfangmanufacturingsdnbhd@gmail.com Password: Abcd1234

## Data (hidden)
Sales PIC | Category | Scheme | Payment Method | Location | Finance | DLP | O&M | Insurance
Chean Bang | R-PV | NEM | Cash | #VALUE! | Outright | 1 year | N/A | N/A
Simon | C&I-PV | SELCO | Credit Card Instalment | #VALUE! | PPA | 2 years | On site checking - 1 year | 1 year
Tham | R-BESS | ATAP | Cash + CC Instalment | #VALUE! |  | 3 years | On site checking - 2 years | 2 years
Patricia | C&I-BESS |  |  | #VALUE! |  | 4 years | On site checking - 3 years | 3 years
Ong | EV Charger |  |  | #VALUE! |  | 5 years | Full O&M - 1 year | 4 years
Reeve |  |  |  | #VALUE! |  | 6 years | Full O&M - 2 years | 5 years
|  |  |  | #VALUE! |  | 7 years | Full O&M - 3 years | 6 years
|  |  |  | #VALUE! |  | 8 years | Full O&M - 4 years | 7 years
|  |  |  | #VALUE! |  | 9 years | Full O&M - 5 years | 8 years
|  |  |  | #VALUE! |  | 10 years | Full O&M - 6 years | 9 years
|  |  |  | #VALUE! |  |  | Full O&M - 7 years | 10 years
|  |  |  | #VALUE! |  |  | Full O&M - 8 years
|  |  |  | #VALUE! |  |  | Full O&M - 9 years
|  |  |  | #VALUE! |  |  | Full O&M - 10 years
Others
SEDA Status
Documents Provided
Waiting for Fee Payment
Waiting for Verification
Waiting for Verification (Update)
Waiting for TNB Confirmation
Approved - Waiting for Certificate
Certificate Generated
Application Withdrawal
Application Rejected
Completed Project Milestones
NEM Commencement Date

## ECN Project Tracker
[12 empty] | TNB-CAS |  | SEDA | [9 empty] | TNB (NEM Meter Change )
Project No | Client Name | Location | Sales PIC | Category | Scheme | System Capacity | Module | Module Quantity | Inverter | Project Status | Payment Status | CAS Application | CAS Approval | NEM Quota Submission | NEM Quota Approval | NEM Quota Status | NEMCD | Site Survey | Material Readiness | RSA Result | Engineering Design | Installer | Installation Date | NEM Meter Change/ Contract Submission | TNB Portal Status | Status Date | Meter Change Payment | NEM Meter Change | NEM Welcome Letter | NEM Term End Date | ST License Application | ST License Approval | GITA Application | GITA Approval |  | Close to Instaallation
2303005 | Wong Kim Mei | #VALUE! | Simon | R-PV | NEM | 8.05 | Astronergy 575Wp | 14 | Solinteg MHT-8K-25 hybrid | Completed | Invoice Completed | N/A | N/A | 2023-07-06 | 2023-08-05 | Completed Project Milestones | 2024-05-29 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2023-09-06 | 2023-09-06 | 2033-09-30 | N/A | N/A | N/A | N/A | 30 | #VALUE!
2303006 | Ang Ching Ming | #VALUE! | Simon | R-PV | NEM | 12.65 | Astronergy 575Wp | 22 | Solinteg MHT-10K-25 hybrid | Completed | Pending 1st Invoice | N/A | N/A | 2023-06-09 | 2023-06-27 | NEM Commencement Date | 2024-06-08 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2023-10-27 | 2023-10-27 | 2033-10-31 | N/A | N/A | N/A | N/A | 18 | #VALUE!
2304016 | Tan Sei Choon | #VALUE! | Chean Bang | R-PV | SELCO | 8.05 | Astronergy 575Wp | 14 | Solinteg MHT-8K-25 hybrid | Completed | Invoice Completed | N/A | N/A | N/A | N/A | N/A | N/A | Completed | Completed | N/A | Completed | Completed | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | #VALUE! | #VALUE!
2305021 | Ho Hon Kit | #VALUE! | Simon | R-PV | NEM | 4.65 | Astronergy 575Wp | 8 | Solinteg MHS-3.6K-30 hybrid | Completed | Pending 1st Invoice | N/A | N/A | 2023-06-06 | 2023-06-27 | NEM Commencement Date | 2024-06-08 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2023-09-13 | 2023-09-13 | 2033-09-30 | N/A | N/A | N/A | N/A | 21 | #VALUE!
2305026 | Stanley Ang Leng Chuan | #VALUE! | Simon | R-PV | NEM | 12.65 | Astronergy 575Wp | 22 | Solinteg MHT-10K-25 hybrid | Completed | Invoice Completed | N/A | N/A | 2023-07-08 | 2023-08-05 | NEM Commencement Date | 2025-04-23 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2023-11-02 | 2023-11-02 | 2033-11-30 | N/A | N/A | N/A | N/A | 28 | #VALUE!
2306033 | Foo Tuang Lee | #VALUE! | Chean Bang | R-PV | NEM | 4.65 | Astronergy 575Wp | 8 | Solinteg MHS-3.6K-30 hybrid | Completed | Invoice Completed | N/A | N/A | 2023-06-09 | 2023-06-27 | NEM Commencement Date | 2024-06-08 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2023-08-31 | 2023-08-31 | 2033-08-31 | N/A | N/A | N/A | N/A | 18 | #VALUE!
2306037 | Tan Hong Guan | #VALUE! | Simon | R-PV | NEM | 10.925 | Astronergy 575Wp | 19 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2023-08-08 | 2023-08-23 | NEM Commencement Date | 2025-05-16 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2023-10-09 | 2023-10-09 | 2033-10-31 | N/A | N/A | N/A | N/A | 15 | #VALUE!
2307040 | Law Soo Chin | #VALUE! | Chean Bang | R-PV | NEM | 12.65 | Astronergy 575Wp | 22 | Solinteg MHT-10K-25 hybrid | Completed | Invoice Completed | N/A | N/A | 2023-07-18 | 2023-08-05 | NEM Commencement Date | 2025-04-23 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2023-10-13 | 2023-10-13 | 2033-10-31 | N/A | N/A | N/A | N/A | 18 | #VALUE!
2305011 | Kossan FRP Marketing (M) Sdn Bhd | #VALUE! | Simon | C&I-PV | NEM | 283.945 | - | - | - | Completed | 2nd invoice | N/A | N/A | N/A | N/A | N/A | N/A | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | N/A | N/A | N/A | N/A | #VALUE! | #VALUE!
2304007 | MTJ Development Sdn Bhd (Intercontinental KL) | #VALUE! | Simon | C&I-PV | NEM | 51.75 | Astronergy 575Wp | 90 | Goodwe 50kW | Completed | 4th invoice | N/A | N/A | 2023-09-01 | 2023-11-08 | Certificate Generated | 2024-08-01 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | N/A | N/A | N/A | N/A | 68 | #VALUE!
2307042 | Dato' Sri Ng Chong Keong | #VALUE! | Chean Bang | R-PV | NEM | 16.1 | Astronergy 575Wp | 28 | Solinteg MHT-12K-25 hybrid | Completed | Invoice Completed | N/A | N/A | 2023-09-19 | 2023-10-06 | NEM Commencement Date | 2025-07-25 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2023-11-18 | 2023-11-18 | 2033-11-30 | N/A | N/A | N/A | N/A | 17 | #VALUE!
2308058 | Cheong Yik Yin | #VALUE! | Simon | R-PV | NEM | 6.9 | Astronergy 575Wp | 12 | Solinteg MHT-5K-25 hybrid | Completed | Pending 1st Invoice | N/A | N/A | 2023-08-29 | 2023-09-13 | NEM Commencement Date | 2025-06-05 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2023-11-21 | 2023-11-21 | 2033-11-30 | N/A | N/A | N/A | N/A | 15 | #VALUE!
2308062 | Lim Chin Joo | #VALUE! | Simon | R-PV | NEM | 12.65 | Astronergy 575Wp | 22 | Huawei SUN2000-12KTL | Completed | Pending 1st Invoice | N/A | N/A | 2023-11-29 | 2024-02-06 | NEM Commencement Date | 2025-09-10 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2024-04-14 | 2024-04-14 | 2034-04-30 | N/A | N/A | N/A | N/A | 69 | #VALUE!
2309068 | Kee Siew Chuan (Ngo Woon Wah) | #VALUE! | Chean Bang | R-PV | NEM | 6.9 | Astronergy 575Wp | 12 | Solinteg MHT-5K-25 hybrid | Completed | 1st invoice | N/A | N/A | 2023-12-12 | 2024-01-30 | Completed Project Milestones | 2025-10-09 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | 2024-02-09 | 2024-02-19 | 2024-02-19 | 2034-02-28 | N/A | N/A | N/A | N/A | 49 | #VALUE!
2310078 | Lee Nyok Cheng | #VALUE! | Chean Bang | R-PV | NEM | 16.1 | Astronergy 575Wp | 28 | Solinteg MHT-12K-25 hybrid | Completed | Invoice Completed | N/A | N/A | 2023-10-12 | 2023-10-25 | Completed Project Milestones | 2024-07-05 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2023-11-15 | 2023-11-15 | 2033-11-30 | N/A | N/A | N/A | N/A | 13 | #VALUE!
2310083 | Ong Eng Guan | #VALUE! | Chean Bang | R-PV | NEM | 8.05 | Astronergy 575Wp | 14 | Solinteg MHT-8K-25 hybrid | Completed | 2nd invoice | N/A | N/A | 2023-10-31 | 2023-11-29 | NEM Commencement Date | 2025-08-06 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2024-02-19 | 2024-02-19 | 2034-02-28 | N/A | N/A | N/A | N/A | 29 | #VALUE!
2310084 | Chia Le Chin | #VALUE! | Chean Bang | R-PV | NEM | 8.05 | Astronergy 575Wp | 14 | Solinteg MHT-8K-25 hybrid | Completed | Invoice Completed | N/A | N/A | 2023-11-01 | 2023-11-29 | NEM Commencement Date | 2025-08-06 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | 2024-02-09 | 2024-02-19 | 2024-02-19 | 2034-02-28 | N/A | N/A | N/A | N/A | 28 | #VALUE!
2305024 | Beh Poh Loh | #VALUE! | Chean Bang | R-PV | NEM | 12.65 | Astronergy 575Wp | 22 | GoodWe GW10KN-ET | Completed | Pending 1st Invoice | N/A | N/A | 2023-07-06 | 2023-07-20 | Completed Project Milestones | 2025-10-09 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | 2024-06-06 | 2024-06-20 | 2024-06-20 | 2034-06-30 | N/A | N/A | N/A | N/A | 14 | #VALUE!
2307052 | Ngoh Win Nee | #VALUE! | Chean Bang | R-PV | NEM | 4.6 | Astronergy 575Wp | 8 | Solinteg MHS-3.6K-30 hybrid | Completed | 1st invoice | N/A | N/A | 2023-08-24 | 2023-09-13 | Certificate Generated | 2024-08-01 | Completed | Completed | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 20 | #VALUE!
2304010 | Tung Seng Chang | #VALUE! | Simon | R-PV | NEM | 13.625 | - | - | Goodwe GW10K-SDT-20 | Completed | 1st invoice | N/A | N/A | 2023-06-30 | 2023-07-13 | Certificate Generated | 2024-07-01 | Completed | Completed | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 13 | #VALUE!
2308065 | Pua Hock Meng | #VALUE! | Chean Bang | R-PV | NEM | 8.625 | Astronergy 575Wp | 15 | Solinteg MHT-8K-25 hybrid | Completed | 4th invoice | N/A | N/A | 2023-09-21 | 2023-10-12 | NEM Commencement Date | 2024-12-06 | Completed | Completed | N/A | Completed | PJ Plus | 2024-10-01 | Completed | Completed | Completed | 2024-11-04 | 2024-11-05 | 2024-11-05 | 2034-11-30 | N/A | N/A | N/A | N/A | 21 | 390
2306009 | Dato Arif Stephen bin Abdullah | #VALUE! | Simon | R-BESS | SELCO | 85.1 | Astronergy 575Wp | 148 | Solax X3-Ultra 20kW x 3 | Completed | Invoice Completed | N/A | N/A | N/A | N/A | N/A | N/A | Completed | Completed | N/A | Completed | Completed | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | #VALUE! | #VALUE!
2303003 | Greenlast Housing Development Sdn Bhd | #VALUE! | Chean Bang | C&I-PV | NEM | 23 | Astronergy 575Wp | 40 | Goodwe GW20K-SDT-20 | Completed | Invoice Completed | N/A | N/A | 2023-12-15 | 2024-01-30 | NEM Commencement Date | 2024-12-28 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2024-06-21 | 2024-06-21 | 2034-06-30 | N/A | N/A | Completed | Completed | 46 | #VALUE!
2311040 | DBTS Industries Sdn Bhd | #VALUE! | SImon | C&I-PV | NEM | 93 | - | - | - | Completed | 1st invoice | N/A | N/A | N/A | N/A | N/A | N/A | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | N/A | N/A | N/A | N/A | #VALUE! | #VALUE!
2308007 | EV Connection Sdn Bhd (The Pines Melaka) | #VALUE! | Simon | EV Charger | - | 0 | - | - | - | Completed | Invoice Completed | N/A | N/A | N/A | N/A | N/A | N/A | Completed | Completed | N/A | Completed | Completed | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | #VALUE! | #VALUE!
2311094 | Ching Kok Keong | #VALUE! | Chean Bang | R-PV | NEM | 9.775 | Astronergy 575Wp | 17 | Solinteg MHT-8K-25 hybrid | Completed | Invoice Completed | N/A | N/A | 2023-11-29 | 2024-01-30 | Completed Project Milestones | 2025-10-09 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | 2025-07-16 | 2024-07-24 | 2024-07-24 | 2034-07-31 | N/A | N/A | N/A | N/A | 62 | #VALUE!
2311095 | Chu Yin Siong | #VALUE! | Chean Bang | R-PV | NEM | 12.65 | Astronergy 575Wp | 22 | Solinteg MHT-10K-25 hybrid | Completed | Invoice Completed | N/A | N/A | 2023-11-28 | 2024-02-06 | NEM Commencement Date | 2025-09-10 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2024-07-08 | 2024-07-08 | 2034-07-31 | N/A | N/A | N/A | N/A | 70 | #VALUE!
2311039 | DC Handal EV Charging Hub | #VALUE! | Simon | C&I-PV | SELCO | 370.055 | - | - | - | Completed | Invoice Completed | N/A | N/A | N/A | N/A | N/A | N/A | Completed | Completed | N/A | Completed | Completed | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | #VALUE! | #VALUE!
2311012 | EV Connection Sdn Bhd (IOI Citymall, Putrajaya) | #VALUE! | Simon | EV Charger | - | 0 | - | - | - | Completed | Invoice Completed | N/A | N/A | N/A | N/A | N/A | N/A | Completed | Completed | N/A | Completed | Completed | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | #VALUE! | #VALUE!
2311089 | Susan Lau Shiew Hung | #VALUE! | Simon | R-PV | NEM | 11.5 | Astronergy 575Wp | 20 | GoodWe GW10K-SDT-20 | Completed | Invoice Completed | N/A | N/A | 2024-05-03 | 2024-05-20 | Completed Project Milestones | 2025-04-28 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | 2024-07-02 | 2024-07-06 | 2024-07-06 | 2034-07-31 | N/A | N/A | N/A | N/A | 17 | #VALUE!
2312118 | Dr Suntheresan A/L Ganapathy | #VALUE! | Ong | R-PV | NEM | 13.8 | Astronergy 575Wp | 24 | Solinteg MHT-12K-25 hybrid | Completed | Invoice Completed | N/A | N/A | 2024-02-09 | 2024-04-03 | Completed Project Milestones | 2025-04-22 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2024-05-11 | 2024-05-11 | 2034-05-31 | N/A | N/A | N/A | N/A | 54 | #VALUE!
2309070 | Saiful Lizan Bin Ibrahim | #VALUE! | Simon | R-PV | NEM | 13.8 | Astronergy 575Wp | 24 | Solinteg MHT-12K-25 hybrid | Completed | Invoice Completed | N/A | N/A | 2024-07-13 | 2024-07-24 | Completed Project Milestones | 2025-05-15 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2024-09-16 | 2024-09-16 | 2034-09-30 | N/A | N/A | N/A | N/A | 11 | #VALUE!
2310075 | Chong Fong Chin(Jessie) | #VALUE! | Chean Bang | R-PV | NEM | 14.625 | Astronergy 585Wp | 25 | Solinteg MHT-12K-25 hybrid | Completed | Pending 1st Invoice | N/A | N/A | 2024-04-01 | 2024-04-30 | Certificate Generated | 2025-03-01 | Completed | Completed | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 29 | #VALUE!
2310076 | Loo Thiam Seng | #VALUE! | Tham | R-PV | NEM | 8.26 | Astronergy 590Wp | 14 | Huawei SUN2000-6KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-03-06 | 2025-03-11 | Certificate Generated | 2026-03-05 | Completed | Completed | N/A | Completed | Completed | 2025-04-15 | 2025-04-17 | Completed | 2025-04-28 | 2025-04-25 | 2025-04-28 |  |  | N/A | N/A | N/A | N/A | 5 | 55
2310085 | Chew Mei May | #VALUE! | Simon | R-PV | NEM | 12.075 | Astronergy 575Wp | 21 | Solinteg MHT-10K-25 hybrid | Completed | Invoice Completed | N/A | N/A | 2024-03-23 | 2024-04-02 | Completed Project Milestones | 2025-08-22 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | 2024-05-29 | 2024-06-12 | 2024-06-12 | 2034-06-30 | N/A | N/A | N/A | N/A | 10 | #VALUE!
2312113 | Razman Bin Samsudin | #VALUE! | Simon | R-PV | NEM | 13.8 | Astronergy 575Wp | 24 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | 2nd invoice | N/A | N/A | 2024-11-05 | 2024-11-21 | Certificate Generated | 2025-11-04 | Completed | Completed | N/A | Completed | AR Berkat | 2025-02-12 | Completed | Completed | 2025-08-22 | Completed | Completed |  |  | N/A | N/A | N/A | N/A | 16 | 387
2401121 | Chen Ah Hin | #VALUE! | Tham | R-PV | NEM | 11.7 | Astronergy 585Wp | 20 | Solinteg MHT-10K-25 hybrid | Completed | Invoice Completed | N/A | N/A | 2024-04-17 | 2024-04-25 | Completed Project Milestones | 2025-04-22 | Completed | Completed | N/A | Completed | AR Berkat | Completed | Completed | Completed | Completed | 2024-06-06 | 2024-06-08 | 2024-06-08 | 2034-06-30 | N/A | N/A | N/A | N/A | 8 | #VALUE!
2401124 | Lim Kok Teong | #VALUE! | Tham | R-PV | NEM | 17.55 | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-04-18 | 2024-04-25 | Completed Project Milestones | 2025-04-21 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | 2024-06-25 | 2024-06-27 | 2024-06-27 | 2034-06-30 | N/A | N/A | N/A | N/A | 7 | #VALUE!
2401131 | Chan Po Kok (JC Chan KEB) | #VALUE! | Tham | R-PV | NEM | 8.19 | Astronergy 585Wp | 14 | Huawei SUN2000-6KTL | Completed | Invoice Completed | N/A | N/A | 2024-04-19 | 2024-05-15 | Completed Project Milestones | 2025-04-30 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | 2024-07-02 | 2024-07-04 | 2024-07-04 | 2034-07-31 | N/A | N/A | N/A | N/A | 26 | #VALUE!
2401137 | Lim Kok Liang | #VALUE! | Tham | R-PV | NEM | 11.7 | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2024-04-09 | 2024-05-15 | Completed Project Milestones | 2025-04-28 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2024-06-20 | 2024-06-20 | 2024-06-30 | N/A | N/A | N/A | N/A | 36 | #VALUE!
2401147 | Susan Sung Fong Thieng | #VALUE! | Tham | R-PV | NEM | 11.7 | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2024-04-04 | 2024-05-08 | Completed Project Milestones | 2025-05-15 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | 2024-06-25 | 2024-07-01 | 2024-07-01 | 2034-07-31 | N/A | N/A | N/A | N/A | 34 | #VALUE!
2403165 | Lee Boon Huet | #VALUE! | Tham | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2024-04-16 | 2024-04-25 | Completed Project Milestones | 2025-04-21 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2024-06-19 | 2024-06-19 | 2034-06-30 | N/A | N/A | N/A | N/A | 9 | #VALUE!
2403167 | Ng Yunn Chong | #VALUE! | Tham | R-PV | NEM | 17.55 | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-04-02 | 2024-04-25 | Completed Project Milestones | 2025-04-28 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | 2024-05-29 | 2024-06-14 | 2024-06-14 | 2034-06-30 | N/A | N/A | N/A | N/A | 23 | #VALUE!
2403170 | Wong Hoon Sang | #VALUE! | Tham | R-PV | NEM | 10.53 | Astronergy 585Wp | 18 | Solinteg MHT-8K-25 hybrid | Completed | Invoice Completed | N/A | N/A | 2024-04-01 | 2024-06-04 | Completed Project Milestones | 2025-08-22 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2024-07-05 | 2024-07-05 | 2034-07-31 | N/A | N/A | N/A | N/A | 64 | #VALUE!
2403177 | Nor Aini binti Mohd Ashari | #VALUE! | Tham | R-PV | NEM | 4.68 | Astronergy 585Wp | 8 | Huawei SUN2000-4KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2024-05-28 | 2024-06-13 | Completed Project Milestones | 2025-04-28 | Completed | Completed | N/A | Completed | Completed | 2024-07-11 | Completed | Completed | Completed | 2024-09-26 | 2024-11-10 | 2024-11-10 | 2034-11-30 | N/A | N/A | N/A | N/A | 16 | 108
2403189 | Lai Kim Soon (Stella) | #VALUE! | Chean Bang | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Solinteg MHS-5K-30 hybrid | Completed | Invoice Completed | N/A | N/A | 2024-04-04 | 2024-04-25 | Completed Project Milestones | 2025-08-22 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | 2024-06-25 | 2024-07-09 | 2024-07-09 | 2034-07-31 | N/A | N/A | N/A | N/A | 21 | #VALUE!
2403190 | Tan Poh Poh | #VALUE! | Chean Bang | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Solinteg MHS-5K-30 hybrid | Completed | Invoice Completed | N/A | N/A | 2024-04-04 | 2024-04-25 | Completed Project Milestones | 2025-04-28 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | 2024-06-06 | 2024-06-17 | 2024-06-17 | 2034-06-30 | N/A | N/A | N/A | N/A | 21 | #VALUE!
2403197 | Leau Koo Sien (Eric) | #VALUE! | Chean Bang | R-PV | NEM | 16.38 | Astronergy 585Wp | 28 | Solinteg MHT-12K-25 hybrid | Completed | 1st invoice | N/A | N/A | 2024-04-22 | 2024-05-15 | Certificate Generated | 2025-04-01 | Completed | Completed | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 23 | #VALUE!
2403197-1 | Koon Kok Leong | #VALUE! | Tham | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2024-04-04 | 2024-04-25 | Completed Project Milestones | 2025-04-21 | Completed | Completed | N/A | Completed | Completed | Completed | 2024-05-16 | Completed | Completed | 2024-05-29 | 2024-06-05 | 2024-06-05 | 2034-06-30 | N/A | N/A | N/A | N/A | 21 | #VALUE!
2404206 | Wong Wai Kwong | #VALUE! | Chean Bang | R-PV | NEM | 8.19 | Astronergy 585Wp | 14 | Huawei SUN2000-6KTL | Completed | Invoice Completed | N/A | N/A | 2024-04-15 | 2024-04-25 | Completed Project Milestones | 2025-08-22 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2024-06-11 | 2024-06-11 | 2034-06-30 | N/A | N/A | N/A | N/A | 10 | #VALUE!
2404226 | Jimmy Kok Aik Lim | #VALUE! | Tham | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2024-04-22 | 2024-05-15 | Completed Project Milestones | 2025-04-21 | Completed | Completed | N/A | Completed | Completed | Completed | 2024-06-27 | Completed | Completed | 2024-07-09 | 2024-07-10 | 2024-07-10 | 2034-07-31 | N/A | N/A | N/A | N/A | 23 | #VALUE!
2401063 | Weller Air-Cond Parts Enterprise Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 26.91 | Astronergy 585Wp | 46 | Huawei SUN2000-20KTL | Pending GITA Application | Invoice Completed | N/A | N/A | 2024-05-22 | 2024-06-06 | NEM Commencement Date | 2025-06-08 | Completed | Completed | Completed | Completed | Completed | 2024-08-05 | Completed | Completed | Completed | 2024-09-26 | 2024-10-14 | 2024-10-14 | 2034-10-31 | N/A | N/A |  |  | 15 | 146
2401069 | Enviri Industries Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 290.4 | Jinko Solar 575Wp | 505 | Huawei SUN2000-100KTL x 2 Huawei SUN2000-36KTL x 1 | Completed | Invoice Completed | Completed | Completed | 2024-05-11 | 2024-07-19 | Completed Project Milestones | 2025-05-30 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2024-12-09 | 2024-12-31 | 2024-12-31 | 2034-12-31 | Completed | Completed | Completed | 2025-08-11 | 69 | #VALUE!
2402079 | Intergreen Holdings Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 46.8 | Astronergy 585Wp | 80 | Huawei SUN2000-12KTL-M5 x 2 Huawei SUN2000-12KTL-MB0 x 1 | Pending GITA Application | Invoice Completed | N/A | N/A | 2024-05-13 | 2024-05-29 | NEM Commencement Date | 2025-06-08 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2024-10-19 | 2024-10-25 | 2024-10-25 | 2034-10-31 | N/A | N/A |  |  | 16 | #VALUE!
2402080 | CK Fresh Sdn Bhd | #VALUE! | Tham | C&I-PV | SELCO | 43.29 | Astronergy 585Wp | 74 | Huawei SUN2000-30KTL | Pending GITA Application | Invoice Completed | N/A | N/A | N/A | N/A | N/A | N/A | Completed | Completed | Completed | Completed | Completed | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | #VALUE! | #VALUE!
2312120 | Ling Duon Kwan | #VALUE! | Tham | R-PV | NEM | 7.605 | Astronergy 585Wp | 13 | Huawei SUN2000-6KTL | Completed | Invoice Completed | N/A | N/A | 2024-04-18 | 2024-04-25 | Completed Project Milestones | 2025-04-21 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2024-05-23 | 2024-05-23 | 2034-05-31 | N/A | N/A | N/A | N/A | 7 | #VALUE!
2311092 | Tham Chee Man | #VALUE! | Tham | R-PV | NEM | 5.75 | Astronergy 575Wp | 10 | Solinteg MHS-5K-30 hybrid | Completed | 1st invoice | N/A | N/A | 2023-11-27 | 2024-01-16 | NEM Commencement Date | 2025-08-05 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | 2024-05-13 | 2024-05-14 | 2024-05-14 | 2034-05-31 | N/A | N/A | N/A | N/A | 50 | #VALUE!
2404230 | Yap Bee Im Marianne | #VALUE! | Tham | R-PV | NEM | 8.775 | Astronergy 585Wp | 15 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-05-03 | 2024-05-20 | NEM Commencement Date | 2025-04-22 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | 2024-07-02 | 2024-07-04 | 2024-07-04 | 2034-07-31 | N/A | N/A | N/A | N/A | 17 | #VALUE!
2401133 | Cheong Sau Ling | #VALUE! | Tham | R-PV | NEM | 8.775 | Astronergy 585Wp | 15 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-05-03 | 2024-05-20 | Completed Project Milestones | 2025-05-16 | Completed | Completed | N/A | Completed | Completed | 2024-10-17 | Completed | Completed | Completed | 2024-11-14 | 2024-11-18 | 2024-11-18 | 2034-11-30 | N/A | N/A | N/A | N/A | 17 | 178
2403171 | Sim Keng Chor | #VALUE! | Tham | R-PV | NEM | 17.55 | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-05-15 | 2024-06-04 | Completed Project Milestones | 2025-04-22 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | 2024-07-31 | 2024-08-07 | 2024-08-07 | 2034-08-31 | N/A | N/A | N/A | N/A | 20 | #VALUE!
2403176 | Nor Hana binti Supiran @ Soviran | #VALUE! | Tham | R-PV | NEM | 6.435 | Astronergy 585Wp | 11 | Huawei SUN2000-5KTL-M1 | Completed | Invoice Completed | N/A | N/A | 2024-05-05 | 2024-05-20 | Completed Project Milestones | 2025-04-22 | Completed | Completed | N/A | Completed | Completed | 2024-08-16 | Completed | Completed | Completed | Completed | 2024-09-19 | 2024-09-19 | 2034-09-30 | N/A | N/A | N/A | N/A | 15 | 114
2404229 | Ng Lay Ping | #VALUE! | Tham | R-PV | NEM | 14.625 | Astronergy 585Wp | 25 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-05-03 | 2024-05-20 | Completed Project Milestones | 2025-04-22 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | 2024-06-25 | 2024-06-27 | 2024-06-27 | 2034-06-30 | N/A | N/A | N/A | N/A | 17 | #VALUE!
2404211 | Nor Fadillah | #VALUE! | Tham | R-PV | NEM | 17.55 | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | Completed | Completed |  |  | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | 2024-07-09 | Completed |  |  | N/A | N/A | N/A | N/A | #VALUE! | #VALUE!
2404111 | Budi Jelas Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 26.91 | Astronergy 585Wp | 46 | Huawei SUN2000-20KTL | Pending GITA Application | Invoice Completed | N/A | N/A | 2024-06-10 | 2024-08-27 | NEM Commencement Date | 2025-06-08 | Completed | Completed | N/A | Completed | Bioserasi | 2024-12-10 | Completed | Completed | Completed | Completed | 2025-02-19 | 2025-02-19 | 2035-02-28 | N/A | N/A |  |  | 78 | 229
2404219 | Billy Teoh Wee Wei | #VALUE! | Tham | R-PV | NEM | 17.55 | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-07-13 | 2024-07-24 | Completed Project Milestones | 2025-04-22 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2024-08-28 | 2024-08-28 | 2034-08-31 | N/A | N/A | N/A | N/A | 11 | #VALUE!
2404214 | Teo En Chie | #VALUE! | Tham | R-PV | NEM | 15.795 | Astronergy 585Wp | 27 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-05-25 | 2024-06-06 | Completed Project Milestones | 2025-08-22 | Completed | Completed | N/A | Completed | Completed | 2024-07-10 | Completed | Completed | Completed | 2024-08-06 | 2024-08-13 | 2024-08-13 | 2034-08-31 | N/A | N/A | N/A | N/A | 12 | 69
2403102 | Sleep Matics (Asia) Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 374.4 | Astronergy 585Wp | 640 | Huawei SUN2000-115KTL x 2 Huawei SUN2000-50KTL x 1 | Pending ST License Application | 3rd invoice | Completed | Completed | 2025-06-25 | 2025-08-19 | Certificate Generated | 2026-06-24 | Completed | Completed | Completed | Completed | Ax Electro | 2025-10-07 | [11 empty] | 55 | 522
2312059 | CHL Foam Industries Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 345.15 | Astronergy 585Wp | 590 | Huawei SUN2000-115KTL x 2 Huawei SUN2000-30KTL x 1 | Pending GITA Application | Invoice Completed | Completed | Completed | 2024-08-06 | 2024-12-16 | Certificate Generated | 2025-11-26 | Completed | Completed | Completed | Completed | Ax Electro | 2025-02-03 | Completed | Completed | Completed | 2025-08-21 | 2025-09-12 | 2025-09-12 | 2035-09-30 | Completed | Completed |  |  | 132 | 276
2404255 | Ong Pui Fen | #VALUE! | Tham | R-PV | NEM | 7.605 | Astronergy 585Wp | 13 | Huawei SUN2000-6KTL | Completed | Invoice Completed | N/A | N/A | 2024-07-12 | 2024-08-11 | Completed Project Milestones | 2025-08-22 | Completed | Completed | N/A | Completed | AR Berkat | 2024-08-26 | Completed | Completed | Completed | 2024-09-26 | 2024-10-03 | 2024-10-03 | 2034-10-31 | N/A | N/A | N/A | N/A | 30 | 106
2404242 | Chua Boon Seng | #VALUE! | Azra | R-PV | NEM | 10.53 | Astronergy 585Wp | 21 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-07-13 | 2024-07-24 | Completed Project Milestones | 2025-04-22 | Completed | Completed | N/A | Completed | PJ Plus | 2024-08-26 | Completed | Completed | Completed | 2024-09-24 | 2024-09-30 | 2024-09-30 | 2034-09-30 | N/A | N/A | N/A | N/A | 11 | 122
2405272 | Chan Hui Li | #VALUE! | Tham | R-PV | NEM | 9.36 | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-05-28 | 2024-06-13 | Completed Project Milestones | 2025-04-29 | Completed | Completed | N/A | Completed | PJ Plus | 2024-08-23 | Completed | Completed | Completed | 2024-09-03 | 2024-09-11 | 2024-09-11 | 2034-09-30 | N/A | N/A | N/A | N/A | 16 | 100
2405266 | Goh Wee Bang (Goh Swee Teng) | #VALUE! | Tham | R-PV | NEM | 13.455 | Astronergy 585Wp | 23 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2024-05-25 | 2024-06-06 | Completed Project Milestones | 2025-04-22 | Completed | Completed | N/A | Completed | AR Berkat | 2024-07-16 | Completed | Completed | Completed | 2024-07-31 | 2024-08-04 | 2024-08-04 | 2034-08-31 | N/A | N/A | N/A | N/A | 12 | 57
2405280 | Teoh Kah Ming | #VALUE! | Tham | R-PV | NEM | 9.36 | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-05-19 | 2024-06-20 | Completed Project Milestones | 2025-04-28 | Completed | Completed | N/A | Completed | AR Berkat | 2024-08-07 | Completed | Completed | Completed | Completed | 2024-08-27 | 2024-08-27 | 2034-08-31 | N/A | N/A | N/A | N/A | 32 | 89
2405294 | Gan Wei Kuan | 0 | Tham | 0 | 0 | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Pending 1st Invoice | N/A | N/A | 2024-07-13 | 2024-07-24 | Application Withdrawal | 2025-07-01 | Completed | Completed | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 11 | #VALUE!
2405296 | Haiu Chan Lai | #VALUE! | Tham | R-PV | NEM | 8.775 | Astronergy 585Wp | 15 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-05-31 | 2024-06-13 | Completed Project Milestones | 2025-04-21 | Completed | Completed | N/A | Completed | AR Berkat | 2024-11-01 | Completed | Completed | Completed | 2024-11-15 | 2024-11-18 | 2024-11-18 | 2034-11-30 | N/A | N/A | N/A | N/A | 13 | 183
2405307 | Shreeram Nadarajah | #VALUE! | Tham | R-PV | NEM | 8.19 | Astronergy 585Wp | 14 | Huawei SUN2000-6KTL | Completed | Invoice Completed | N/A | N/A | 2024-05-28 | 2024-06-13 | Completed Project Milestones | 2025-05-16 | Completed | Completed | N/A | Completed | AR Berkat | 2024-09-03 | Completed | Completed | Completed | 2024-09-24 | 2024-09-25 | 2024-09-25 | 2034-09-30 | N/A | N/A | N/A | N/A | 16 | 104
2404227 | Datin Tai Bee Choon | #VALUE! | Tham | R-PV | NEM | 17.55 | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-07-13 | 2024-07-24 | Completed Project Milestones | 2025-08-26 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 2024-10-30 | 2024-10-30 | 2034-10-31 | N/A | N/A | N/A | N/A | 11 | #VALUE!
2405315 | Yeap Say Woei | #VALUE! | Tham | R-PV | NEM | 13.455 | Astronergy 585Wp | 23 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2024-07-13 | 2024-07-24 | Completed Project Milestones | 2025-05-15 | Completed | Completed | N/A | Completed | Completed | Completed | Completed | Completed | Completed | 2024-09-03 | 2024-09-01 | 2024-09-01 | 2034-09-30 | N/A | N/A | N/A | N/A | 11 | #VALUE!
2405319 | Tan Zhi Cheng | #VALUE! | Tham | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2024-07-13 | 2024-07-24 | Completed Project Milestones | 2025-04-28 | Completed | Completed | N/A | Completed | AR Berkat | 2024-08-19 | Completed | Completed | Completed | 2024-09-04 | 2024-09-06 | 2024-09-06 | 2034-09-30 | N/A | N/A | N/A | N/A | 11 | 78
2405288 | Teh Siew Eng | #VALUE! | Tham | R-PV | NEM | 12.285 | Astronergy 585Wp | 21 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2024-07-23 | 2024-08-01 | Completed Project Milestones | 2025-04-28 | Completed | Completed | N/A | Completed | AR Berkat | 2024-08-28 | Completed | Completed | Completed | Completed | 2024-09-23 | 2024-09-23 | 2034-09-30 | N/A | N/A | N/A | N/A | 9 | 92
2404256 | Lai Chun Wai | #VALUE! | Azra | R-PV | NEM | 8.775 | Astronergy 585Wp | 14 | Solinteg MHT-8K-25 hybrid | Completed | Invoice Completed | N/A | N/A | 2024-07-27 | 2024-09-22 | NEM Commencement Date | 2025-08-15 | Completed | Completed | N/A | Completed | AR Berkat | 2024-09-28 | Completed | Completed | Completed | Completed | 2024-10-20 | 2024-10-20 | 2034-10-31 | N/A | N/A | N/A | N/A | 57 | 99
2406323 | Tay Poh Chai | #VALUE! | Tham | R-PV | NEM | 14.04 | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-07-13 | 2024-07-24 | Completed Project Milestones | 2025-05-15 | Completed | Completed | N/A | Completed | AR Berkat | 2024-08-05 | Completed | Completed | Completed | 2024-09-04 | 2024-09-06 | 2024-09-06 | 2034-09-30 | N/A | N/A | N/A | N/A | 11 | 52
2406336 | Alex How Chee Keong | #VALUE! | Tham | R-PV | NEM | 11.7 | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2024-07-13 | 2024-07-24 | Completed Project Milestones | 2025-04-22 | Completed | Completed | N/A | Completed | AR Berkat | 2024-08-20 | 2024-09-06 | Completed | Completed | 2024-09-24 | 2024-09-16 | 2024-09-16 | 2034-09-30 | N/A | N/A | N/A | N/A | 11 | 62
2406340 | How Mei Cheng | #VALUE! | Tham | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2024-07-13 | 2024-07-24 | Completed Project Milestones | 2025-04-21 | Completed | Completed | N/A | Completed | AR Berkat | 2024-08-24 | Completed | Completed | Completed | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2034-09-30 | N/A | N/A | N/A | N/A | 11 | 64
2406355 | Windy Ng | #VALUE! | Tham | R-PV | NEM | 9.36 | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-07-23 | 2024-08-01 | Completed Project Milestones | 2025-05-15 | Completed | Completed | N/A | Completed | AR Berkat | 2024-10-10 | Completed | Completed | Completed | Completed | 2024-10-27 | 2024-10-27 | 2034-10-31 | N/A | N/A | N/A | N/A | 9 | 104
2406357 | Zainuddin Zin | #VALUE! | Patricia | R-PV | NEM | 12.285 | Astronergy 585Wp | 21 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2024-07-25 | 2024-07-31 | Completed Project Milestones | 2025-08-22 | Completed | Completed | N/A | Completed | PJ Plus | 2024-08-29 | Completed | Completed | Completed | 2024-10-07 | 2024-10-20 | 2024-10-20 | 2034-10-31 | N/A | N/A | N/A | N/A | 6 | 62
2405019 | Handal Green Mobility Sdn Bhd (Encore Melaka) | #VALUE! | Simon | EV Charger | - | 0 | - | - | - | Completed | Invoice Completed | N/A | N/A | N/A | N/A | N/A | N/A | Completed | Completed | N/A | Completed | Completed | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | #VALUE! | #VALUE!
2406358 | Kwan Li Shan | #VALUE! | Tham | R-PV | NEM | 9.36 | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-07-22 | 2024-07-30 | Completed Project Milestones | 2025-04-29 | Completed | Completed | N/A | Completed | AR Berkat | 2024-09-14 | 2024-09-23 | Completed | Completed | Completed | 2024-10-06 | 2024-10-06 | 2034-10-31 | N/A | N/A | N/A | N/A | 8 | 75
2407360 | Liau Hui Kiem | #VALUE! | Tham | R-PV | NEM | 14.04 | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-08-01 | 2024-08-11 | Completed Project Milestones | 2025-04-21 | Completed | Completed | N/A | Completed | AR Berkat | 2024-09-02 | Completed | Completed | Completed | Completed | 2024-09-20 | 2024-09-20 | 2034-09-30 | N/A | N/A | N/A | N/A | 10 | 46
2407364 | Mohd Nasir Man | #VALUE! | Patricia | R-PV | NEM | 8.19 | Astronergy 585Wp | 14 | Huawei SUN2000-6KTL | Completed | Invoice Completed | N/A | N/A | 2024-07-25 | 2024-07-31 | Completed Project Milestones | 2025-08-22 | Completed | Completed | N/A | Completed | PJ Plus | 2024-09-03 | Completed | Completed | Completed | 2024-09-26 | 2024-10-20 | 2024-10-20 | 2034-10-31 | N/A | N/A | N/A | N/A | 6 | 57
2407375 | Tan Ger Ber | #VALUE! | Tham | R-PV | NEM | 14.04 | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-07-22 | 2024-07-30 | Completed Project Milestones | 2025-04-28 | Completed | Completed | N/A | Completed | AR Berkat | 2024-09-10 | Completed | Completed | Completed | 2024-09-26 | 2024-09-30 | 2024-09-30 | 2034-09-30 | N/A | N/A | N/A | N/A | 8 | 60
2407379 | Ng Boon Kiat (Daniel) | #VALUE! | Chean Bang | R-PV | NEM | 5.265 | Astronergy 585Wp | 9 | Solinteg MHS-5K-30 hybrid | Completed | Invoice Completed | N/A | N/A | 2024-07-22 | 2024-07-30 | Completed Project Milestones | 2025-08-22 | Completed | Completed | N/A | Completed | PJ Plus | 2024-08-20 | Completed | Completed | Completed | Completed | 2024-09-16 | 2024-09-16 | 2034-09-30 | N/A | N/A | N/A | N/A | 8 | 40
2407380 | How Yee Seun | #VALUE! | Tham | R-PV | NEM | 12.87 | Astronergy 585Wp | 22 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2024-07-27 | 2024-08-01 | Completed Project Milestones | 2025-04-21 | Completed | Completed | N/A | Completed | AR Berkat | 2024-08-29 | Completed | Completed | Completed | 2024-09-04 | 2024-09-13 | 2024-09-13 | 2034-09-30 | N/A | N/A | N/A | N/A | 5 | 47
2407381 | Lau Ah Leng | #VALUE! | Tham | R-PV | NEM | 12.285 | Astronergy 585Wp | 21 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2024-07-27 | 2024-08-01 | Completed Project Milestones | 2025-04-28 | Completed | Completed | N/A | Completed | AR Berkat | 2024-10-02 | Completed | Completed | Completed | 2024-10-16 | 2024-10-21 | 2024-10-21 | 2034-10-31 | N/A | N/A | N/A | N/A | 5 | 81
2407382 | Leong Tack Ming | #VALUE! | Tham | R-PV | NEM | 8.775 | Astronergy 585Wp | 15 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-08-01 | 2024-08-11 | Completed Project Milestones | 2025-04-28 | Completed | Completed | N/A | Completed | AR Berkat | 2025-01-08 | 2024-11-18 | Completed | 2025-11-18 | 2025-11-20 | 2024-11-21 | 2024-11-21 | 2034-11-30 | N/A | N/A | N/A | N/A | 10 | 177
2407383 | Charles Lew Chow Leng | #VALUE! | Tham | R-PV | NEM | 14.04 | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-07-24 | 2024-08-01 | Completed Project Milestones | 2025-04-21 | Completed | Completed | N/A | Completed | AR Berkat | 2024-09-09 | Completed | Completed | Completed | 2024-09-24 | 2024-09-25 | 2024-09-25 | 2034-09-30 | N/A | N/A | N/A | N/A | 8 | 56
2407384 | Loh Fook Khew | #VALUE! | Tham | R-PV | NEM | 12.285 | Astronergy 585Wp | 21 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2024-07-26 | 2024-08-01 | Completed Project Milestones | 2025-04-21 | Completed | Completed | N/A | Completed | AR Berkat | 2024-09-12 | Completed | Completed | Completed | 2024-09-26 | 2024-09-30 | 2024-09-30 | 2034-09-30 | N/A | N/A | N/A | N/A | 6 | 59
2407385 | Cheong Chin Meng | #VALUE! | Chean Bang | R-PV | NEM | 15.21 | Astronergy 585Wp | 26 | Solinteg MHT-12K-25 hybrid | Completed | Invoice Completed | N/A | N/A | 2024-07-25 | 2024-07-31 | Completed Project Milestones | 2025-04-29 | Completed | Completed | N/A | Completed | PJ Plus | 2024-09-10 | Completed | Completed | Completed | 2024-10-07 | 2024-10-20 | 2024-10-20 | 2034-10-31 | N/A | N/A | N/A | N/A | 6 | 57
2310035 | Advantic Nutraceuticals | #VALUE! | Tham | C&I-PV | NEM | 87.84 | Astronergy 610Wp | 144 | Huawei SUN2000-30KTL + Huawei SUN2000-36KTL | Pending GITA Application | Invoice Completed | N/A | N/A | 2025-06-26 | 2025-08-06 | Completed Project Milestones | 2026-06-25 | Completed | Completed | Completed | Completed | AR Berkat | 2025-06-09 | Completed | Completed | Completed | Completed | 2025-09-09 | 2025-09-09 | 2035-09-30 | N/A | N/A |  |  | 41 | 24
2403088 | Chua Tong Hin Hardware Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 37.44 | Astronergy 585Wp | 64 | Huawei SUN2000-30KTL | Pending GITA Application | Invoice Completed | N/A | N/A | 2024-11-12 | 2024-11-27 | NEM Commencement Date | 2025-06-08 | Completed | Completed | Completed | Completed | Bioserasi | 2024-12-27 | Completed | Completed | Completed | Completed | 2025-03-07 | 2025-03-07 | 2035-03-31 | N/A | N/A |  |  | 15 | 163
2407157 | NMSY Capital Sdn Bhd (Mohd Nasir) | #VALUE! | Patricia | C&I-PV | NEM | 18.72 | Astronergy 585Wp | 32 | Huawei SUN2000-17KTL | Completed | Invoice Completed | N/A | N/A | 2024-08-06 | 2024-09-10 | NEM Commencement Date | 2025-10-02 | Completed | Completed | Completed | Completed | PJ Plus | 2024-09-12 | Completed | Completed | Completed | 2024-09-26 | 2024-10-10 | 2024-10-10 | 2034-10-31 | N/A | N/A | N/A | N/A | 35 | 66
2312116 | Chua Ling Ling | #VALUE! | Tham | R-PV | NEM | 11.7 | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2024-08-14 | 2024-08-31 | Completed Project Milestones | 2025-04-22 | Completed | Completed | N/A | Completed | AR Berkat | 2024-09-20 | Completed | Completed | Completed | 2024-11-04 | 2024-11-11 | 2024-11-11 | 2034-11-30 | N/A | N/A | N/A | N/A | 17 | 94
2407388 | Yeo Chen Kok | #VALUE! | Tham | R-PV | NEM | 12.285 | Astronergy 585Wp | 21 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2024-08-01 | 2024-08-11 | Completed Project Milestones | 2025-04-28 | Completed | Completed | N/A | Completed | AR Berkat | 2024-09-27 | Completed | Completed | Completed | Completed | 2024-10-04 | 2024-10-04 | 2034-10-31 | N/A | N/A | N/A | N/A | 10 | 70
2407386 | Amirluddin bin Awang | #VALUE! | Chean Bang | R-PV | NEM | 12.285 | Astronergy 585Wp | 21 | Solinteg MHT-10K-25 hybrid | Completed | Invoice Completed | N/A | N/A | 2024-08-04 | 2024-08-14 | Completed Project Milestones | 2025-04-29 | Completed | Completed | N/A | Completed | PJ Plus | 2024-09-24 | Completed | Completed | Completed | 2024-10-07 | 2024-10-11 | 2024-10-11 | 2034-10-31 | N/A | N/A | N/A | N/A | 10 | 65
2403158 | Ong Gin Chin | #VALUE! | Tham | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2024-08-01 | 2024-09-19 | Completed Project Milestones | 2025-05-15 | Completed | Completed | N/A | Completed | Completed | 2024-10-09 | Completed | Completed | Completed | Completed | 2024-10-28 | 2014-10-28 | 2034-10-31 | N/A | N/A | N/A | N/A | 49 | 79
2404220 | Ng Seow Fong | #VALUE! | Tham | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2024-08-01 | 2024-09-12 | Completed Project Milestones | 2025-05-15 | Completed | Completed | N/A | Completed | AR Berkat | 2024-10-07 | Completed | Completed | Completed | 2024-10-16 | 2024-10-15 | 2024-10-15 | 2034-10-31 | N/A | N/A | N/A | N/A | 42 | 81
2403202 | Chuah Teah Soo | #VALUE! | Tham | R-PV | NEM | 10.53 | Astronergy 585Wp | 18 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-08-05 | 2024-08-13 | Completed Project Milestones | 2025-04-22 | Completed | Completed | N/A | Completed | Completed | 2024-09-01 | Completed | Completed | Completed | Completed | 2024-09-23 | 2024-09-23 | 2034-09-30 | N/A | N/A | N/A | N/A | 8 | 39
2407392 | Ecila Sim Ju-Inn | #VALUE! | Tham | R-PV | NEM | 11.7 | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2024-08-05 | 2024-09-12 | Completed Project Milestones | 2025-05-15 | Completed | Completed | N/A | Completed | AR Berkat | 2024-10-15 | Completed | Completed | Completed | 2024-10-23 | 2024-10-24 | 2024-10-24 | 2034-10-31 | N/A | N/A | N/A | N/A | 38 | 83
2404232 | Wong Yoke Chon | #VALUE! | Tham | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2024-08-06 | 2024-08-18 | Completed Project Milestones | 2025-08-22 | Completed | Completed | N/A | Completed | AR Berkat | 2024-09-30 | Completed | Completed | Completed | 2024-10-16 | 2024-10-24 | 2024-10-24 | 2034-10-31 | N/A | N/A | N/A | N/A | 12 | 97
2407397 | Foo Su Hoong | #VALUE! | Tham | R-PV | NEM | 15.21 | Astronergy 585Wp | 26 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-08-08 | 2024-08-27 | Completed Project Milestones | 2025-04-22 | Completed | Completed | N/A | Completed | AR Berkat | 2024-09-23 | Completed | Completed | Completed | 2024-10-03 | 2025-10-06 | 2024-10-06 | 2034-10-31 | N/A | N/A | N/A | N/A | 19 | 60
2404250 | Wan Johan Bin Rahim | #VALUE! | Tham | R-PV | NEM | 17.55 | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-08-07 | 2024-08-26 | Completed Project Milestones | 2025-04-28 | Completed | Completed | N/A | Completed | AR Berkat | 2024-10-14 | Completed | Completed | Completed | 2024-11-21 | 2024-11-22 | 2024-11-22 | 2024-11-30 | N/A | N/A | N/A | N/A | 19 | 77
2407399 | Koo Woon Kee | #VALUE! | Tham | R-PV | NEM | 10.53 | Astronergy 585Wp | 18 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-08-13 | 2024-08-30 | Completed Project Milestones | 2025-04-21 | Completed | Completed | N/A | Completed | AR Berkat | 2024-10-08 | 2024-10-03 | Completed | Completed | 2024-10-16 | 2024-10-18 | 2024-10-18 | 2034-10-31 | N/A | N/A | N/A | N/A | 17 | 74
2407394 | Nor Aini binti Mat Saman (Nazrul Latif) | #VALUE! | Patricia | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2024-08-05 | 2024-08-13 | Completed Project Milestones | 2025-08-22 | Completed | Completed | N/A | Completed | PJ Plus | 2024-09-19 | Completed | Completed | Completed | 2024-10-04 | 2024-10-18 | 2024-10-18 | 2034-10-31 | N/A | N/A | N/A | N/A | 8 | 50
2407397-1 | Teo Kai Yun | #VALUE! | Tham | R-PV | NEM | 15.21 | Astronergy 585Wp | 26 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-07-25 | 2024-11-11 | Completed Project Milestones | 2025-08-29 | Completed | Completed | N/A | Completed | AR Berkat | 2024-11-14 | Completed | Completed | 2025-12-12 | 2024-11-26 | 2024-12-12 | 2024-12-12 | 2034-12-31 | N/A | N/A | N/A | N/A | 109 | 104
2312114 | Chua Teng Teng | #VALUE! | Tham | R-PV | NEM | 11.7 | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2024-07-16 | 2024-08-09 | Completed Project Milestones | 2025-04-22 | Completed | Completed | N/A | Completed | AR Berkat | 2024-08-14 | Completed | Completed | Completed | Completed | 2024-10-18 | 2024-10-18 | 2034-10-31 | N/A | N/A | N/A | N/A | 24 | 57
2401123 | Lee Yoon Huat | #VALUE! | Tham | R-PV | NEM | 12.285 | Astronergy 585Wp | 21 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2024-08-01 | 2024-08-11 | Completed Project Milestones | 2025-04-28 | Completed | Completed | N/A | Completed | AR Berkat | 2024-09-18 | Completed | Completed | Completed | Completed | 2024-10-02 | 2024-10-02 | 2034-10-31 | N/A | N/A | N/A | N/A | 10 | 75
2404207 | Tan Boon Siang (Han Father) | #VALUE! | Tham | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2024-05-31 | 2024-06-14 | Completed Project Milestones | 2025-08-22 | Completed | Completed | N/A | Completed | AR Berkat | 2024-08-12 | Completed | Completed | Completed | 2024-08-28 | 2024-08-25 | 2024-08-25 | 2034-08-31 | N/A | N/A | N/A | N/A | 14 | 84
2408402 | Tee Cheong Tuan | #VALUE! | Tham | R-PV | NEM | 12.87 | Astronergy 585Wp | 22 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2024-08-13 | 2024-08-30 | Completed Project Milestones | 2025-04-28 | Completed | Completed | N/A | Completed | AR Berkat | 2024-10-28 | Completed | Completed | Completed | 2024-11-11 | 2024-11-12 | 2024-11-12 | 2034-11-30 | N/A | N/A | N/A | N/A | 17 | 84
2407372 | Dato Tay Tong Ben | #VALUE! | Tham | R-PV | NEM | 14.04 | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-08-13 | 2024-08-30 | Completed Project Milestones | 2025-04-28 | Completed | Completed | N/A | Completed | AR Berkat | 2024-09-25 | Completed | Completed | Completed | Completed | 2024-10-16 | 2024-10-16 | 2034-10-31 | N/A | N/A | N/A | N/A | 17 | 50
2405298 | Lim Choon Huat | #VALUE! | Tham | R-PV | NEM | 11.7 | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2024-08-13 | 2024-08-30 | Completed Project Milestones | 2025-04-21 | Completed | Completed | N/A | Completed | AR Berkat | 2024-09-24 | Completed | Completed | Completed | 2024-10-07 | 2024-10-16 | 2024-10-16 | 2034-10-31 | N/A | N/A | N/A | N/A | 17 | 60
2408404 | Ong Ling Gee | #VALUE! | Tham | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2024-08-13 | 2024-08-30 | Completed Project Milestones | 2025-04-28 | Completed | Completed | N/A | Completed | PJ Plus | 2024-10-24 | 2024-11-21 | Completed | 2024-11-25 | 2024-11-22 | 2024-11-25 | 2024-11-25 | 2034-11-30 | N/A | N/A | N/A | N/A | 17 | 74
2408401 | Kuek Soon Yeam | #VALUE! | Tham | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2024-08-14 | 2024-08-31 | Completed Project Milestones | 2025-04-21 | Completed | Completed | N/A | Completed | AR Berkat | 2024-10-16 | 2024-10-16 | Completed | Completed | 2024-11-04 | 2024-11-05 | 2024-11-05 | 2034-11-30 | N/A | N/A | N/A | N/A | 17 | 69
2408398 | Yap Siok Ching | #VALUE! | Tham | R-PV | NEM | 11.7 | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2024-08-25 | 2024-09-12 | Completed Project Milestones | 2025-05-15 | Completed | Completed | N/A | Completed | AR Berkat | 2024-10-18 | Completed | Completed | Completed | Completed | 2024-10-28 | 2024-10-28 | 2034-10-31 | N/A | N/A | N/A | N/A | 18 | 64
2408415 | Shahrin Merican | #VALUE! | Tham | R-PV | NEM | 17.55 | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-08-29 | 2024-10-01 | Completed Project Milestones | 2025-05-15 | Completed | Completed | N/A | Completed | AR Berkat | 2024-10-23 | Completed | Completed | Completed | Completed | 2024-11-01 | 2024-11-01 | 2024-11-30 | N/A | N/A | N/A | N/A | 33 | 63
2408425 | Chua Shen Huat | #VALUE! | Tham | R-PV | NEM | 14.04 | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-09-02 | 2024-09-26 | Completed Project Milestones | 2025-04-29 | Completed | Completed | N/A | Completed | AR Berkat | 2024-10-21 | Completed | Completed | Completed | Completed | 2024-11-08 | 2024-11-08 | 2034-11-30 | N/A | N/A | N/A | N/A | 24 | 55
2406334 | Yap Kee Leong | #VALUE! | Tham | R-PV | NEM | 14.04 | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-09-03 | 2024-10-02 | Completed Project Milestones | 2025-08-22 | Completed | Completed | N/A | Completed | AR Berkat | 2024-10-30 | Completed | Completed | Completed | 2024-11-15 | 2024-12-01 | 2024-12-01 | 2034-12-31 | N/A | N/A | N/A | N/A | 29 | 64
2407371 | Tiong Nguong Kiong | #VALUE! | Chean Bang | R-PV | NEM | 10.53 | Astronergy 585Wp | 18 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-09-10 | 2024-10-21 | Completed Project Milestones | 2025-08-22 | Completed | Completed | N/A | Completed | PJ Plus | 2024-10-23 | Completed | Completed | Completed | 2024-11-21 | 2024-12-08 | 2024-12-08 | 2034-12-31 | N/A | N/A | N/A | N/A | 41 | 56
2408409 | Lua Peck Lay | #VALUE! | Patricia | R-PV | NEM | 9.945 | Astronergy 585Wp | 17 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-09-09 | 2024-10-17 | Completed Project Milestones | 2025-08-22 | Completed | Completed | N/A | Completed | PJ Plus | 2024-10-08 | Completed | Completed | Completed | 2024-11-21 | 2025-02-13 | 2025-02-13 | 2035-02-28 | N/A | N/A | N/A | N/A | 38 | 39
2408411 | Akhman Aidi Putra | #VALUE! | Patricia | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2024-08-25 | 2024-09-12 | Completed Project Milestones | 2025-04-29 | Completed | Completed | N/A | Completed | PJ Plus | 2024-10-03 | Completed | Completed | Completed | Completed | 2024-10-16 | 2024-10-16 | 2034-10-31 | N/A | N/A | N/A | N/A | 18 | 49
2408408 | Chiang Yoke Har | #VALUE! | Patricia | R-PV | NEM | 17.55 | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-08-25 | 2024-09-12 | Completed Project Milestones | 2025-04-29 | Completed | Completed | N/A | Completed | PJ Plus | 2024-10-10 | Completed | Completed | Completed | 2024-11-04 | 2024-11-13 | 2024-11-13 | 2034-11-30 | N/A | N/A | N/A | N/A | 18 | 56
2408025 | Handal Green Mobility Sdn Bhd (ICE Gallery @ Pantai Sentral) | #VALUE! | Simon | EV Charger | - | 0 | - | - | - | Completed | Invoice Completed | N/A | N/A | N/A | N/A | N/A | N/A | Completed | Completed | N/A | Completed | AR Berkat | 2024-10-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | #VALUE! | 47
2408431 | Lor Yean Yean | #VALUE! | Tham | R-PV | NEM | 9.36 | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-09-11 | 2024-11-10 | Certificate Generated | 2025-10-28 | Completed | Completed | N/A | Completed | PJ Plus | 2025-01-23 | 2025-02-10 | Completed | 2025-02-26 | 2025-02-18 | 2025-02-26 | 2025-02-26 | 2035-02-28 | N/A | N/A | N/A | N/A | 60 | 136
2408432 | Lin Mok Kwai Yin | #VALUE! | Chean Bang | R-PV | NEM | 8.19 | Astronergy 585Wp | 14 | Huawei SUN2000-6KTL | Completed | Invoice Completed | N/A | N/A | 2024-09-29 | 2024-11-09 | Completed Project Milestones | 2025-04-28 | Completed | Completed | N/A | Completed | PJ Plus | 2024-11-28 | Completed | Completed | Completed | Completed | 2025-04-08 | 2025-04-08 | 2035-04-30 | N/A | N/A | N/A | N/A | 41 | 90
2408407 | Kwong Wui Ee | #VALUE! | Patricia | R-PV | NEM | 9.36 | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-09-09 | 2024-10-17 | Completed Project Milestones | 2025-04-29 | Completed | Completed | N/A | Completed | PJ Plus | 2024-10-30 | Completed | Completed | Completed | 2024-11-21 | 2025-01-06 | 2025-01-06 | 2035-01-31 | N/A | N/A | N/A | N/A | 38 | 55
2409441 | Cheu Chow Sew @ Chew Chow Sew | #VALUE! | Chean Bang | R-PV | NEM | 12.87 | Astronergy 585Wp | 22 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2024-09-09 | 2024-10-17 | Completed Project Milestones | 2025-04-29 | Completed | Completed | N/A | Completed | PJ Plus | 2024-11-05 | 2024-11-15 | Completed | 2024-11-27 | Completed | 2024-11-27 | 2024-11-27 | 2034-11-30 | N/A | N/A | N/A | N/A | 38 | 61
2408433 | Ng Ek Hoo | #VALUE! | Chean Bang | R-PV | NEM | 5.85 | Astronergy 585Wp | 10 | Huawei SUN2000-5KTL-M1 | Completed | Invoice Completed | N/A | N/A | 2024-09-11 | 2024-11-10 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2024-11-30 | 2024-11-27 | Completed | 2024-12-19 | 2024-12-05 | 2024-12-19 | 2024-12-19 | 2034-12-31 | N/A | N/A | N/A | N/A | 60 | 89
2409445 | Phang Kar Teck | #VALUE! | Patricia | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2024-09-11 | 2024-11-10 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-04-10 | Completed | Completed | Completed | Completed | Completed |  |  | N/A | N/A | N/A | N/A | 60 | 213
2408434 | Lim Ye Soon | #VALUE! | Chean Bang | R-PV | NEM | 14.04 | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-09-11 | 2024-10-21 | Completed Project Milestones | 2025-08-22 | Completed | Completed | N/A | Completed | PJ Plus | 2024-11-07 | Completed | Completed | Completed | 2024-12-05 | 2024-12-07 | 2024-12-07 | 2034-12-31 | N/A | N/A | N/A | N/A | 40 | 59
2409442 | Lee Chiou Horng | #VALUE! | Tham | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2024-09-10 | 2024-11-10 | Certificate Generated | 2025-10-18 | Completed | Completed | N/A | Completed | AR Berkat | 2025-04-11 | 2025-03-21 | Completed | Completed | Completed | Completed |  |  | N/A | N/A | N/A | N/A | 61 | 215
2409443 | Dato Lim Zhen Peng | #VALUE! | Tham | R-PV | NEM | 17.55 | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-09-10 | 2024-11-10 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2024-10-27 | 2025-12-16 | Completed | 2024-12-18 | 2024-12-17 | 2024-12-18 | 2024-12-18 | 2034-12-31 | N/A | N/A | N/A | N/A | 61 | 48
2408417 | Mohmad Nazeri bin Abdul Wahab | #VALUE! | Tham | R-PV | NEM | 17.55 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | Pending Meter Change | Invoice Completed | N/A | N/A | 2024-09-11 | 2024-10-31 | Certificate Generated | 2025-10-29 | Completed | Completed | N/A | Completed | AR Berkat | 2025-03-29 | Completed | Completed | Completed | Completed |  |  |  | N/A | N/A | N/A | N/A | 50 | 202
2409440 | Tan Say Kheng | #VALUE! | Tham | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2024-09-09 | 2024-10-17 | Completed Project Milestones | 2025-05-15 | Completed | Completed | N/A | Completed | AR Berkat | 2024-11-08 | Completed | Completed | Completed | 2024-11-19 | 2024-11-26 | 2024-11-26 | 2034-11-30 | N/A | N/A | N/A | N/A | 38 | 65
2405273 | Leong Ah Seng | #VALUE! | Tham | R-PV | NEM | 17.55 | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-09-10 | 2024-10-17 | Completed Project Milestones | 2025-04-21 | Completed | Completed | N/A | Completed | AR Berkat | 2025-01-07 | 2025-02-07 | Completed | 2025-02-12 | 2025-02-10 | 2025-02-12 | 2025-02-12 | 2035-02-28 | N/A | N/A | N/A | N/A | 37 | 131
2308064 | Low Yin Jun | #VALUE! | Simon | R-PV | NEM | 11.7 | Astronergy 585Wp | 20 | Solinteg MHT-10K-25 hybrid | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2024-08-08 | 2024-08-17 | Certificate Generated |  | Completed | Completed | N/A | Completed | Completed | 2025-04-23 | 2025-04-24 | Completed | 2025-04-28 | 2025-04-25 | 2025-04-28 |  |  | N/A | N/A | N/A | N/A | 9 | 99
2409447 | Chan Chee Tuck | #VALUE! | Chean Bang | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2024-09-11 | 2024-11-10 | Certificate Generated | 2025-10-20 | Completed | Completed | N/A | Completed | PJ Plus | 2024-12-05 | Completed | Completed | Completed | 2024-12-24 | 2024-12-22 | 2024-12-22 | 2024-12-31 | N/A | N/A | N/A | N/A | 60 | 134
2409444 | Tuan Noraizan Bt Tuan Long | #VALUE! | Chean Bang | R-PV | NEM | 9.36 | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-09-11 | 2024-11-10 | Certificate Generated | 2025-10-31 | Completed | Completed | N/A | Completed | PJ Plus | 2025-01-22 | Completed | Completed | Completed | Completed | 2025-03-04 | 2025-03-04 | 2035-03-31 | N/A | N/A | N/A | N/A | 60 | 71
2407368 | Noor Izzah Akmal Bt Mohd Nordin | #VALUE! | Chean Bang | R-PV | NEM | 12.87 | Astronergy 585Wp | 22 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2024-09-11 | 2024-11-10 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2024-11-21 | 2024-12-12 | Completed | 2024-12-25 | Completed | 2024-12-25 | 2024-12-25 | 2034-12-31 | N/A | N/A | N/A | N/A | 60 | 38
2409446 | Guok Diong Chong | #VALUE! | Tham | R-PV | NEM | 9.36 | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-09-11 | 2024-11-10 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2024-10-18 | 2024-11-26 | Completed | 2024-11-28 | 2024-11-26 | 2024-11-28 | 2024-11-28 | 2034-11-30 | N/A | N/A | N/A | N/A | 60 | -45544
2404249 | Tan Kheng Guan | #VALUE! | Tham | R-PV | NEM | 17.55 | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | Pending Site Installation | 1st invoice | N/A | N/A | 2024-09-11 | 2024-10-29 | Certificate Generated | 2025-10-27 | Completed | Completed | N/A | Completed |  |  | 2025-04-24 | [6 empty] | N/A | N/A | N/A | N/A | 48 | 97
2408424-1 | Low Bok Tek | #VALUE! | Tham | R-PV | NEM | 17.55 | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-09-11 | 2024-11-04 | Certificate Generated | 2025-10-31 | Completed | Completed | N/A | Completed | AR Berkat | 2024-12-17 | Completed | Completed | Completed | Completed | 2025-01-02 | 2025-01-02 | 2035-01-31 | N/A | N/A | N/A | N/A | 54 | 97
2408424-2 | Low Bok Tek | #VALUE! | Tham | R-PV | NEM | 17.55 | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-09-11 | 2024-10-31 | Certificate Generated | 2025-10-29 | Completed | Completed | N/A | Completed | AR Berkat | 2024-12-17 | Completed | Completed | Completed | Completed | 2025-01-02 | 2025-01-02 | 2035-01-31 | N/A | N/A | N/A | N/A | 50 | 169
2405284 | Amirul Hakim bin Omar | #VALUE! | Tham | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2024-09-11 | 2024-11-04 | Certificate Generated | 2025-10-31 | Completed | Completed | N/A | Completed | AR Berkat | 2025-02-27 | Completed | Completed | Completed | 2025-03-03 | Completed |  |  | N/A | N/A | N/A | N/A | 54 | 184
2409448 | Pang Chong Han | #VALUE! | Simon | R-PV | NEM | 8.26 | Astronergy 590Wp | 14 | Solinteg MHS-8K-25 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2024-09-11 | 2024-10-29 | Certificate Generated | 2025-10-27 | Completed | Completed | N/A | Completed | AR Berkat | 2025-03-14 | 2025-03-19 | Completed | 2025-03-20 | 2025-03-19 | Completed |  |  | N/A | N/A | N/A | N/A | 48 | 170
2408400 | Oh Chai Ean | #VALUE! | Chean Bang | R-PV | NEM | 17.55 | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-09-11 | 2024-11-04 | Certificate Generated | 2025-10-31 | Completed | Completed | N/A | Completed | PJ Plus | 2025-02-27 | Completed | Completed | Completed | 2025-03-27 | 2025-04-23 | 2025-04-23 | 2035-04-30 | N/A | N/A | N/A | N/A | 54 | 107
2409449-1 | Nurul Ain Binti Yahaya | #VALUE! | Chean Bang | R-PV | NEM | 9.36 | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-09-11 | 2024-11-04 | Certificate Generated | 2025-10-31 | Completed | Completed | N/A | Completed | PJ Plus | 2024-12-27 | Completed | Completed | Completed | Completed | 2025-02-28 | 2025-02-28 | 2035-02-28 | N/A | N/A | N/A | N/A | 54 | 63
2409452 | Yio Pee Ban | #VALUE! | Chean Bang | R-PV | NEM | 10.53 | Astronergy 585Wp | 18 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-09-24 | 2024-11-07 | Completed Project Milestones | 2025-08-22 | Completed | Completed | N/A | Completed | PJ Plus | 2024-11-13 | Completed | Completed | Completed | Completed | 2024-12-04 | 2024-12-04 | 2034-12-31 | N/A | N/A | N/A | N/A | 44 | 51
2409449 | Tan Hock Seng | #VALUE! | Tham | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2024-10-02 | 2024-11-08 | Completed Project Milestones | 2025-05-15 | Completed | Completed | N/A | Completed | AR Berkat | 2024-11-11 | Completed | Completed | Completed | 2024-12-02 | 2024-12-04 | 2024-12-04 | 2034-12-31 | N/A | N/A | N/A | N/A | 37 | 33
2409448-1 | Claris Lim Jink Niee (Lim Chin Horng) | #VALUE! | Tham | R-PV | NEM | 11.7 | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2024-10-03 | 2024-11-08 | Completed Project Milestones | 2025-08-22 | Completed | Completed | N/A | Completed | AR Berkat | 2024-10-29 | Completed | Completed | Completed | 2024-12-31 | 2025-01-06 | 2025-01-06 | 2035-01-31 | N/A | N/A | N/A | N/A | 36 | 28
2406343 | Dato Sim Keng Piao | #VALUE! | Tham | R-PV | NEM | 9.36 | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-10-02 | 2024-11-08 | Completed Project Milestones | 2025-05-15 | Completed | Completed | N/A | Completed | AR Berkat | 2024-10-19 | Completed | Completed | Completed | 2024-11-29 | 2024-12-01 | 2024-12-01 | 2034-12-31 | N/A | N/A | N/A | N/A | 37 | 45
2409455 | Muhamad Syamil bin Zulkafli | #VALUE! | Tham | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2024-10-03 | 2024-11-08 | Completed Project Milestones | 2025-08-22 | Completed | Completed | N/A | Completed | PJ Plus | 2024-11-11 | Completed | Completed | Completed | 2024-11-21 | 2024-12-06 | 2024-12-06 | 2034-12-31 | N/A | N/A | N/A | N/A | 36 | 91
2410064 | Zarita binti Saliman | #VALUE! | Tham | R-PV | NEM | 7.605 | Astronergy 585Wp | 13 | Solinteg MHS-5K-30 hybrid | Completed | Invoice Completed | N/A | N/A | 2024-10-10 | 2024-11-11 | Completed Project Milestones | 2025-05-15 | Completed | Completed | N/A | Completed | AR Berkat | 2024-12-03 | Completed | Completed | Completed | 2024-12-24 | 2024-12-22 | 2024-12-22 | 2034-12-31 | N/A | N/A | N/A | N/A | 32 | 126
2405305 | Chan Woei Jye | #VALUE! | Tham | R-PV | NEM | 10.53 | Astronergy 585Wp | 18 | Huawei SUN2000-8KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2024-10-23 | 2024-11-15 | Certificate Generated | 2025-10-22 | Completed | Completed | N/A | Completed | AR Berkat | 2025-02-11 | 2025-02-09 | Completed | Completed | Completed | Completed |  |  | N/A | N/A | N/A | N/A | 23 | 74
2409456 | Low Hong Chin | #VALUE! | Tham | R-PV | NEM | 11.115 | Astronergy 585Wp | 19 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2024-12-02 | 2024-12-09 | Completed Project Milestones | 2025-04-21 | Completed | Completed | N/A | Completed | AR Berkat | 2024-12-31 | 2025-01-14 | Completed | 2025-01-21 | 2025-01-17 | 2025-01-21 | 2025-01-21 | 2035-01-31 | N/A | N/A | N/A | N/A | 7 | 70
2410461 | Low Hong Choon | #VALUE! | Tham | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2025-01-03 | 2025-01-09 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2024-12-30 | 2025-01-15 | Completed | 2025-02-15 | 2025-01-17 | 2025-02-15 | 2025-02-15 | 2035-02-28 | N/A | N/A | N/A | N/A | 6 | #VALUE!
2409029 | Handal Green Mobility Sdn Bhd (Mazda Kuantan Showroom) | #VALUE! | Simon | EV Charger | - | 0 | - | - | - | Completed | Invoice Completed | N/A | N/A | N/A | N/A | N/A | N/A | Completed | Completed | N/A | Completed | Completed | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | #VALUE! | #VALUE!
2410032 | Handal Green Mobility Sdn Bhd (United Point Mall, Kuala Lumpur) | #VALUE! | Simon | EV Charger | - | 0 | - | - | - | Completed | Invoice Completed | N/A | N/A | N/A | N/A | N/A | N/A | Completed | Completed | N/A | Completed | Completed | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | #VALUE! | #VALUE!
2407167-1 | Econframe Marketing Sdn Bhd (Kilang 1 & 3) | #VALUE! | Tham | C&I-PV | NEM | 109.395 | Yingli Solar 585Wp | 187 | Huawei SUN2000-50KTL + SUN2000-36KTL | Pending GITA Application | Invoice Completed | N/A | N/A | 2024-09-25 | 2024-10-17 | NEM Commencement Date | 2025-10-02 | 2024-10-23 | Completed | Completed | Completed | Bioserasi | Completed | Completed | Completed | Completed | 2025-03-03 | 2025-03-12 | 2025-03-12 | 2035-03-31 | N/A | N/A |  |  | 22 | #VALUE!
2407167-2 | Econframe Marketing Sdn Bhd (Kilang 4) | #VALUE! | Tham | C&I-PV | NEM | 26.91 | Yingli Solar 585Wp | 46 | Huawei SUN2000-20KTL | Pending GITA Application | Invoice Completed | N/A | N/A | 2024-09-25 | 2024-10-17 | NEM Commencement Date | 2025-10-02 | 2024-10-23 | Completed | Completed | Completed | Bioserasi | Completed | Completed | Completed | Completed | 2025-02-20 | 2025-02-22 | 2025-02-22 | 2035-02-28 | N/A | N/A |  |  | 22 | #VALUE!
2407167-3 | Econframe Marketing Sdn Bhd (Kilang 20) | #VALUE! | Tham | C&I-PV | NEM | 67.275 | Yingli Solar 585Wp | 115 | Huawei SUN2000-50KTL | Pending GITA Application | Invoice Completed | N/A | N/A | 2024-09-25 | 2024-10-09 | NEM Commencement Date | 2025-10-02 | 2024-10-23 | Completed | Completed | Completed | Bioserasi | Completed | Completed | Completed | Completed | 2025-03-03 | 2025-03-12 | 2025-03-12 | 2035-03-31 | N/A | N/A |  |  | 14 | #VALUE!
2408174 | Zimandy Construction Sdn Bhd (Bandar Tenggara) | #VALUE! | Tham | C&I-PV | NEM | 120.95 | Astronergy 590Wp | 205 | Huawei SUN2000-40KTL +SUN2000-30KTL + SUN2000-20KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-03-21 | 2025-05-21 | Certificate Generated | 2026-03-23 | 2025-06-19 | Completed | Completed | Completed | PJ Plus | Completed | 2025-03-01 | Completed | 2025-10-25 | Completed | 2025-10-25 |  |  | N/A | N/A |  |  | 61 | 87
2408179 | Pelita Hijrah Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 107.64 | Astronergy 585Wp | 184 | Huawei SUN2000-20KTL x 4 | Pending GITA Application | Invoice Completed | N/A | N/A | 2024-11-24 | 2025-01-09 | NEM Commencement Date | 2025-06-08 | Completed | Completed | Completed | Completed |  | 2025-01-13 | Completed | Completed | Completed | Completed | 2025-03-13 | 2025-03-13 | 2035-03-31 | N/A | N/A |  |  | 46 | 87
2409185 | Kim Chong Mechanical Services Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 26.55 | Astronergy 590Wp | 45 | Huawei SUN2000-20KTL | Pending GITA Application | Invoice Completed | N/A | N/A | 2024-10-04 | 2024-11-21 | NEM Commencement Date | 2025-06-08 | 2024-10-23 | Completed | Completed | Completed | Bioserasi | 2024-12-23 | Completed | Completed | Completed | Completed | 2025-01-16 | 2025-01-16 | 2035-01-31 | N/A | N/A |  |  | 48 | 115
2410196 | Unilink Machinery Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 26.55 | Astronergy 590Wp | 45 | Huawei SUN2000-20KTL | Pending GITA Application | Invoice Completed | N/A | N/A | 2024-11-11 | 2024-11-27 | NEM Commencement Date | 2025-06-08 | Completed | Completed | Completed | Completed |  | 2025-01-23 | Completed | Completed | Completed | Completed | 2025-02-27 | 2025-02-27 | 2035-02-28 | N/A | N/A |  |  | 16 | 43
2410474 | Koe Ban Seng | #VALUE! | Tham | R-PV | NEM | 14.04 | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-11-05 | 2024-11-21 | Completed Project Milestones | 2025-04-21 | Completed | Completed | N/A | Completed | AR Berkat | 2024-12-06 | 2025-12-18 | Completed | 2024-12-24 | 2024-12-24 | 2024-12-24 | 2024-12-24 | 2034-12-31 | N/A | N/A | N/A | N/A | 16 | 228
2410468 | Teo Boon Ling | #VALUE! | Tham | R-PV | NEM | 11.7 | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2024-11-25 | 2024-12-02 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-06-17 | Completed | Completed | Completed | 2025-04-21 | Completed |  |  | N/A | N/A | N/A | N/A | 7 | 49
2409450 | David Hie Wen Jian | #VALUE! | Tham | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2024-11-05 | 2024-11-21 | Completed Project Milestones | 2025-04-22 | Completed | Completed | N/A | Completed | AR Berkat | 2024-12-13 | 2024-12-24 | Completed | 2025-01-04 | Completed | 2025-01-04 | 2025-01-04 | 2035-01-31 | N/A | N/A | N/A | N/A | 16 | 49
2411488 | Tan Kong Ling | #VALUE! | Chean Bang | R-PV | NEM | 10.53 | Astronergy 585Wp | 18 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-11-06 | 2024-11-21 | Certificate Generated | 2025-11-05 | Completed | Completed | N/A | Completed | PJ Plus | 2024-12-14 | 2024-12-28 | Completed | 2025-01-10 | Completed | 2025-01-10 | 2025-01-10 | 2035-01-31 | N/A | N/A | N/A | N/A | 15 | 49
2411487 | Lim Daw Woei | #VALUE! | Tham | R-PV | NEM | 15.21 | Astronergy 585Wp | 26 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-11-25 | 2024-12-02 | Certificate Generated | 2025-11-24 | Completed | Completed | N/A | Completed | AR Berkat | 2024-12-23 | 2025-01-04 | Completed | 2025-01-09 | 2025-01-06 | 2025-01-09 | 2025-01-09 | 2035-01-31 | N/A | N/A | N/A | N/A | 7 | 60
2410476 | Choong Chin Fong | #VALUE! | Tham | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2024-11-06 | 2024-12-11 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-01-03 | Completed | Completed | Completed | Completed | 2025-01-28 | 2025-01-28 | 2035-01-31 | N/A | N/A | N/A | N/A | 35 | -57
2407376 | Teoh Eng Siong | #VALUE! | Chean Bang | R-PV | NEM | 10.53 | Astronergy 585Wp | 18 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-08-07 | 2024-08-26 | Completed Project Milestones | 2025-08-22 | Completed | Completed | N/A | Completed | Completed | 2024-09-07 | Completed | Completed | Completed | 2024-09-26 | 2024-09-29 | 2024-09-29 | 2034-09-30 | N/A | N/A | N/A | N/A | 19 | 166
2410482 | Teo Thian Keong | #VALUE! | Tham | R-PV | NEM | 8.775 | Astronergy 585Wp | 15 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-11-25 | 2024-12-06 | Certificate Generated |  | Completed | Completed | N/A | Completed | Completed | 2025-01-09 | 2025-01-28 | Completed | 2025-02-05 | 2025-02-03 | 2025-02-05 | 2025-02-05 | 2025-02-28 | N/A | N/A | N/A | N/A | 11 | -45596
2410471 | Chua Lu Chuan | #VALUE! | Chean Bang | R-PV | NEM | 17.55 | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | Pending Site Installation | 1st invoice | N/A | N/A | 2024-10-15 | 2024-11-12 | Certificate Generated | 2025-10-14 | Completed | Completed | N/A | Completed | [9 empty] | N/A | N/A | N/A | N/A | 28 | 74
2411489 | Quah Ewe Lee | #VALUE! | Tham | R-PV | NEM | 14.04 | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-11-28 | 2024-12-03 | Completed Project Milestones | 2025-04-28 | Completed | Completed | N/A | Completed | Completed | 2024-12-24 | 2025-01-04 | Completed | 2025-01-09 | 2025-01-06 | 2025-01-09 | 2025-01-09 | 2035-01-31 | N/A | N/A | N/A | N/A | 5 | 56
2411486 | Lim Chee Keong | #VALUE! | Tham | R-PV | NEM | 13.455 | Astronergy 585Wp | 23 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2024-12-09 | 2024-12-17 | Completed Project Milestones | 2025-04-21 | Completed | Completed | N/A | Completed | Completed | 2025-01-21 | 2025-01-27 | Completed | 2025-01-31 | 2025-01-28 | 2025-01-31 | 2025-01-31 | 2035-01-31 | N/A | N/A | N/A | N/A | 8 | 42
2411500 | Ho Maw Chun | #VALUE! | Tham | R-PV | NEM | 14.16 | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2024-12-10 | 2024-12-17 | Completed Project Milestones | 2025-04-21 | Completed | Completed | N/A | Completed | Completed | 2025-01-13 | 2025-01-26 | Completed | 2025-02-06 | 2025-02-05 | 2025-02-06 | 2025-02-06 | 2035-02-28 | N/A | N/A | N/A | N/A | 7 | #VALUE!
2410034 | Handal Green Mobility Sdn Bhd (Pulse Grande Hotel) | #VALUE! | Chean Bang | EV Charger | - | 0 | - | - | - | Completed | Invoice Completed | N/A | N/A | N/A | N/A | N/A | N/A | Completed | Completed | N/A | Completed | Completed | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | #VALUE! | 101
2411494 | Pang Kim Soon | #VALUE! | Chean Bang | R-PV | NEM | 17.55 | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2024-12-09 | 2024-12-17 | Certificate Generated |  | Completed | Completed | N/A | Completed | Completed | 2025-03-06 | 2025-03-25 | Replacing Meter | 2025-04-08 | 2025-04-08 | Completed |  |  | N/A | N/A | N/A | N/A | 8 | 50
2411496 | Teong Lian Aik | #VALUE! | Tham | R-PV | NEM | 9.36 | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-12-28 | 2024-12-31 | Completed Project Milestones | 2025-05-15 | Completed | Completed | N/A | Completed | AR Berkat | 2025-01-15 | 2025-01-28 | Completed | 2025-02-02 | 2025-01-28 | 2025-02-02 | 2025-02-02 | 2035-02-28 | N/A | N/A | N/A | N/A | 3 | 71
2404224 | Vijayalakshmi a/p Krishnaswamy (Tan Sri Rama Iyer) | #VALUE! | Tham | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2024-12-30 | 2025-01-03 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-02-05 | 2025-02-09 | Completed | 2025-02-13 | 2025-02-12 | 2025-02-13 |  |  | N/A | N/A | N/A | N/A | 4 | 93
2411491 | Low Kim Keong | #VALUE! | Chean Bang | R-PV | NEM | 11.7 | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2024-12-30 | 2025-01-22 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-03-01 | 2025-03-27 | Completed | 2025-04-13 | 2025-04-03 | Completed |  |  | N/A | N/A | N/A | N/A | 23 | 28
2411490 | Chear Eng Soon | #VALUE! | Chean Bang | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | 2nd invoice | N/A | N/A | 2024-12-14 | 2024-12-17 | Completed Project Milestones | 2025-04-29 | Completed | Completed | N/A | Completed | AR Berkat | 2025-01-02 | 2025-01-16 | Completed | 2025-02-03 | 2025-01-17 | 2025-02-03 | 2025-02-03 | 2035-02-28 | N/A | N/A | N/A | N/A | 3 | 37
2412504 | Thiong Jeng Ell | #VALUE! | Patricia | R-PV | NEM | 9.36 | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2024-12-28 | 2024-12-31 | Completed Project Milestones | 2025-08-22 | Completed | Completed | N/A | Completed | PJ Plus | 2025-01-11 | 2025-02-05 | Completed | 2025-02-17 | 2025-02-04 | 2025-02-17 | 2025-02-17 | 2035-02-28 | N/A | N/A | N/A | N/A | 3 | 33
2412503 | Lian Hock Seng | #VALUE! | Chean Bang | R-PV | NEM | 14.04 | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2024-12-28 | 2024-12-31 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-01-09 | 2025-02-19 | Completed | 2025-02-24 | 2025-02-19 | Completed |  |  | N/A | N/A | N/A | N/A | 3 | 58
2410033 | Handal Green Mobility Sdn Bhd (Kuantan City Mall) | #VALUE! | Chean Bang | EV Charger | - | 0 | - | - | - | Completed | Invoice Completed | N/A | N/A | N/A | N/A | N/A | N/A | Completed | Completed | N/A | Completed | Completed | 2025-02-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | #VALUE! | 52
2412505 | Dong Mee Hong | #VALUE! | Patricia | R-PV | NEM | 14.04 | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2024-12-30 | 2025-01-20 | Certificate Generated | 2026-01-17 | Completed | Completed | N/A | Completed | PJ Plus | 2025-01-31 | 2025-02-07 | Completed | 2025-02-19 | 2025-02-18 | Completed |  |  | N/A | N/A | N/A | N/A | 21 | 38
2412509 | Muck Bei lee (Le Lodge Mansion) | #VALUE! | Chean Bang | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2025-01-03 | 2025-01-14 | Certificate Generated | 2026-01-08 | Completed | Completed | N/A | Completed | PJ Plus | 2025-01-20 | 2025-02-13 | Completed | 2025-02-28 | 2025-02-18 | 2025-02-28 | 2025-02-28 | 2035-02-28 | N/A | N/A | N/A | N/A | 11 | 44
2412515 | Liew Mun Meng | #VALUE! | Tham | R-PV | NEM | 17.55 | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2024-12-30 | 2025-01-20 | Certificate Generated | 2026-01-17 | Completed | Completed | N/A | Completed | AR Berkat | 2025-02-13 | 2025-02-18 | Completed | 2025-03-05 | 2025-02-19 | 2025-03-05 |  |  | N/A | N/A | N/A | N/A | 21 | 67
2410462 | Yee Mei Ling | #VALUE! | Tham | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2024-12-31 | 2025-01-03 | Certificate Generated | 2025-12-30 | Completed | Completed | N/A | Completed | AR Berkat | 2025-02-26 | 2025-03-17 | Completed | 2025-03-19 | 2025-03-17 | 2025-03-19 |  |  | N/A | N/A | N/A | N/A | 3 | 56
2412516 | Chareon Phromsuwan | #VALUE! | Tham | R-PV | NEM | 12.98 | Astronergy 590Wp | 22 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2024-12-31 | 2025-01-03 | Certificate Generated | 2025-12-30 | Completed | Completed | N/A | Completed | AR Berkat | 2025-02-17 | 2025-02-28 | Completed | 2025-03-04 | 2025-03-03 | 2025-03-04 | 2025-03-04 | 2035-03-31 | N/A | N/A | N/A | N/A | 3 | 56
2412521 | Christopher A De Souza | #VALUE! | Tham | R-PV | NEM | 15.34 | Astronergy 590Wp | 26 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2025-01-03 | 2025-01-14 | Certificate Generated | 2026-01-08 | Completed | Completed | N/A | Completed | AR Berkat | 2025-02-18 | 2025-02-28 | Completed | 2025-03-04 | 2025-03-03 | 2025-03-04 | 2025-03-04 | 2035-03-31 | N/A | N/A | N/A | N/A | 11 | 86
2412524 | Teng Lee Xung | #VALUE! | Chean Bang | R-PV | NEM | 14.16 | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-01-09 | 2025-01-17 | Certificate Generated | 2026-01-16 | Completed | Completed | N/A | Completed | PJ Plus | 2025-03-29 | 2025-02-05 | Replacing Meter | 2025-02-07 | Completed | Completed |  |  | N/A | N/A | N/A | N/A | 8 | 22
2412513 | Ganapathy Srihari a/l Rama Iyer | #VALUE! | Tham | R-PV | NEM | 10.03 | Astronergy 590Wp | 17 | Huawei SUN2000-8KTL | Pending NEM Welcome Letter | 2nd invoice | N/A | N/A | 2025-03-29 | 2025-05-19 | Certificate Generated |  | Completed | Completed | N/A | Completed | Completed | 2025-09-12 | Completed | Completed | Completed | Completed | Completed |  |  | N/A | N/A | N/A | N/A | 51 | 55
2501038 | Florence Poon | #VALUE! | Simon | EV Charger | - | 0 | 0 | - | - | Completed | Invoice Completed | N/A | N/A | N/A | N/A | N/A | N/A | Completed | Completed | N/A | Completed | Completed | 2025-01-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | #VALUE! | 51
2501532 | Prasert Phromsuwan | #VALUE! | Tham | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-02-07 | 2025-02-13 | Certificate Generated | 2025-11-28 | Completed | Completed | N/A | Completed | AR Berkat | 2025-03-05 | 2025-02-17 | Completed | 2025-02-22 | 2025-02-20 | 2025-02-22 |  |  | N/A | N/A | N/A | N/A | 6 | 42
2501544 | Gan Tek Chuan | #VALUE! | Patricia | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-02-13 | 2025-02-18 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-03-13 | 2025-03-24 | Completed | 2025-04-08 | 2025-03-27 | 2025-04-08 |  |  | N/A | N/A | N/A | N/A | 5 | 44
2502548 | Wong Kok Wai | #VALUE! | Chean Bang | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-02-17 | 2025-02-25 | Certificate Generated |  | Completed | Completed | N/A | Completed | Completed | 2025-03-08 | 2025-03-21 | Completed | 2025-04-13 | 2025-03-28 | 2025-04-13 |  |  | N/A | N/A | N/A | N/A | 8 | 237
2501545 | Lee Tian Look | #VALUE! | Chean Bang | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-02-21 | 2025-03-09 | Certificate Generated | 2026-02-20 | Completed | Completed | N/A | Completed | Completed | 2025-03-22 | 2025-03-24 | Completed | 2025-04-16 | Completed | 2025-04-16 |  |  | N/A | N/A | N/A | N/A | 16 | 131
2311088 | Lee Chean Chung | #VALUE! | Chean Bang | R-PV | NEM | 10.62 | Astronergy 590Wp | 18 | Huawei SUN2000-10KTL | Pending NEM Welcome Letter | 1st invoice | N/A | N/A | 2025-02-21 | 2025-03-09 | Certificate Generated | 2026-02-19 | Completed | Completed | N/A | Completed | AR Berkat | 2025-10-07 | 2025-04-14 |  |  | 2025-05-06 | Completed |  |  | N/A | N/A | N/A | N/A | 16 | 19
2502216 | Low Yi Chin | #VALUE! | Chean Bang | C&I-PV | NEM | 14.16 | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-02-21 | 2025-03-03 | Certificate Generated | 2026-02-20 | Completed | Completed | N/A | Completed | PJ Plus | 2025-06-24 | 2025-07-04 | Completed | 2025-07-16 | 2025-07-07 | 2025-07-16 |  |  | N/A | N/A | N/A | N/A | 10 | 28
2502553 | Salim Majid Zain Bin Abdul Majid | #VALUE! | Tham | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-02-18 | 2025-02-25 | Certificate Generated | 2026-02-17 | Completed | Completed | N/A | Completed | AR Berkat | 2025-03-03 | 2025-03-10 | Completed | 2025-03-17 | 2025-03-12 | 2025-03-17 |  |  | N/A | N/A | N/A | N/A | 7 | 62
2502552 | Anandan a/l Balakrishnan | #VALUE! | Tham | R-PV | NEM | 11.8 | Astronergy 590Wp | 20 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2025-02-21 | 2025-03-09 | Certificate Generated | 2026-02-20 | Completed | Completed | N/A | Completed | AR Berkat | 2025-03-13 | 2025-03-20 | Completed | 2025-04-04 | 2025-03-26 | 2025-04-04 | 2025-04-04 | 2035-04-30 | N/A | N/A | N/A | N/A | 16 | 32
2412519 | Liew Swee Fah | #VALUE! | Tham | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2025-02-21 | 2025-03-09 | Certificate Generated | 2026-02-20 | Completed | Completed | N/A | Completed | PJ Plus | 2025-04-17 | 2025-04-08 | Completed | 2025-05-20 | 2025-04-10 | 2025-05-20 | 2025-05-20 | 2035-05-31 | N/A | N/A | N/A | N/A | 16 | 33
2502547 | Chong Chee Hoo | #VALUE! | Tham | R-PV | NEM | 11.8 | Astronergy 590Wp | 20 | Huawei SUN2000-10KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-03-06 | 2025-03-14 | Certificate Generated | 2026-03-05 | Completed | Completed | N/A | Completed | AR Berkat | 2025-03-18 | 2025-03-26 | Completed | 2025-03-29 | 2025-03-27 | 2025-03-29 |  |  | N/A | N/A | N/A | N/A | 8 | 25
2502541 | Boo Kee Meng | #VALUE! | Tham | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-02-21 | 2025-02-25 | Certificate Generated | 2026-02-20 | Completed | Completed | N/A | Completed | AR Berkat | 2025-03-17 | 2025-04-15 |  |  | 2025-04-21 | Completed |  |  | N/A | N/A | N/A | N/A | 4 | 21
2502556 | Gan Chong Sing | #VALUE! | Patricia | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-02-21 | 2025-03-09 | Certificate Generated | 2026-02-20 | Completed | Completed | N/A | Completed | PJ Plus | 2025-03-14 | 2025-03-19 | Completed | 2025-04-08 | 2025-03-27 | 2025-04-08 |  |  | N/A | N/A | N/A | N/A | 16 | 17
2502551 | Tan Seng Shen | #VALUE! | Tham | R-PV | NEM | 14.16 | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-02-21 | 2025-02-25 | Certificate Generated | 2026-02-20 | Completed | Completed | N/A | Completed | AR Berkat | 2025-03-10 | 2025-03-20 | Completed | 2025-03-28 | Completed | Completed |  |  | N/A | N/A | N/A | N/A | 4 | 31
2502546 | Jordan Tan Heng Xiang | #VALUE! | Tham | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-6KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-02-21 | 2025-02-25 | Certificate Generated | 2026-02-20 | Completed | Completed | N/A | Completed | AR Berkat | 2025-03-06 | 2025-03-28 | Completed | 2025-04-14 | 2025-04-08 | 2025-04-14 |  |  | N/A | N/A | N/A | N/A | 4 | 18
2502559 | Wong Peng Soon | #VALUE! | Chean Bang | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-02-21 | 2025-03-09 | Certificate Generated | 2026-02-19 | Completed | Completed | N/A | Completed | PJ Plus | 2025-03-20 | 2025-03-21 | Completed | 2025-03-29 | 2025-03-26 | 2025-03-29 |  |  | N/A | N/A | N/A | N/A | 16 | 217
2501537 | Chan My Ling | #VALUE! | Tham | R-PV | NEM | 12.39 | Astronergy 590Wp | 21 | Huawei SUN2000-10KTL | Completed | Invoice Completed | N/A | N/A | 2025-02-18 | 2025-02-25 | Certificate Generated | 2026-02-17 | Completed | Completed | N/A | Completed | AR Berkat | 2025-03-07 | 2025-03-11 | Completed | 2025-03-13 | Completed | 2025-03-13 | 2025-03-13 | 2035-03-31 | N/A | N/A | N/A | N/A | 7 | 35
2502550 | Ricky Goh Hoon Kan | #VALUE! | Chean Bang | R-PV | NEM | 14.75 | Astronergy 590Wp | 25 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | 1st invoice | N/A | N/A | 2025-02-21 | 2025-03-09 | Certificate Generated | 2026-02-20 | Completed | Completed | N/A | Completed | Completed | 2025-09-23 | Completed | Completed | Completed | 2025-09-30 | Completed |  |  | N/A | N/A | N/A | N/A | 16 | 49
2502543 | Chow Leong Choon | #VALUE! | Ong | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2025-02-27 | 2025-03-09 | Certificate Generated | 2026-02-26 | Completed | Completed | N/A | Completed | AR Berkat | 2025-03-24 | 2025-03-26 | Completed | 2025-03-27 | 2025-03-26 | 2025-03-27 | 2025-03-27 | 2035-03-31 | N/A | N/A | N/A | N/A | 10 | 35
2502560 | Lim Sooi Poh | #VALUE! | Tham | R-PV | NEM | 14.16 | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-02-27 | 2025-03-09 | Certificate Generated | 2026-02-26 | Completed | Completed | N/A | Completed | AR Berkat | 2025-04-08 | 2025-03-28 | Completed | 2025-04-14 | 2025-04-10 | 2025-04-14 |  |  | N/A | N/A | N/A | N/A | 10 | 43
2408411-1 | Eng Khai Shu | #VALUE! | Tham | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-03-06 | 2025-03-14 | Certificate Generated | 2026-03-05 | Completed | Completed | N/A | Completed | AR Berkat | 2025-03-20 | 2025-04-09 | Completed | 2025-04-11 | 2025-04-10 | 2025-04-11 |  |  | N/A | N/A | N/A | N/A | 8 | -45713
2502569 | Chew Beng Hock | #VALUE! | Ong | R-PV | NEM | 8.85 | Astronergy 590Wp | 15 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2025-02-27 | 2025-03-18 | Certificate Generated | 2026-02-26 | Completed | Completed | N/A | Completed | AR Berkat | 2025-04-04 | Completed | Completed | 2025-04-23 | 2025-04-22 | 2025-04-23 | 2025-04-23 | 2035-04-30 | N/A | N/A | N/A | N/A | 19 | 113
2502565 | Yeo Shu Jin | #VALUE! | Simon | R-PV | NEM | 7.67 | Astronergy 590Wp | 13 | Huawei SUN2000-6KTL | Pending Site Installation | 1st invoice | N/A | N/A | 2025-03-06 | 2025-03-14 | Certificate Generated | 2026-03-05 | Completed | Completed | N/A | Completed |  |  | Completed | Completed | Completed | 2025-04-18 | Completed |  |  | N/A | N/A | N/A | N/A | 8 | 30
2502549 | Har Hock Lee | #VALUE! | Patricia | R-PV | NEM | 14.16 | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | 2nd invoice | N/A | N/A | 2025-03-12 | 2025-03-24 | Certificate Generated | 2026-03-14 | Completed | Completed | N/A | Completed | PJ Plus | 2025-06-17 | 2025-04-09 | Replacing Meter | 2025-04-14 | 2025-04-14 | Completed |  |  | N/A | N/A | N/A | N/A | 12 | 46
2405286 | Wong Wai Hung | #VALUE! | Tham | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-03-06 | 2025-03-25 | Certificate Generated | 2026-03-05 | Completed | Completed | N/A | Completed | AR Berkat | 2025-03-27 | 2025-04-07 | Completed | 2025-04-10 | 2025-04-08 | 2025-04-10 |  |  | N/A | N/A | N/A | N/A | 19 | 46
2501527 | Kuan Guan Chong | #VALUE! | Tham | R-PV | NEM | 11.8 | Astronergy 590Wp | 20 | Huawei SUN2000-10KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-03-11 | 2025-03-18 | Certificate Generated | 2026-03-10 | Completed | Completed | N/A | Completed | PJ Plus | 2025-04-14 | 2025-04-09 | Completed | Completed | 2025-04-10 | Completed |  |  | N/A | N/A | N/A | N/A | 7 | 22
2501529 | Kuan Kian Yang | #VALUE! | Tham | R-PV | NEM | 10.62 | Astronergy 590Wp | 18 | Huawei SUN2000-8KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-03-11 | 2025-03-18 | Certificate Generated | 2026-03-10 | Completed | Completed | N/A | Completed | PJ Plus | 2025-04-15 | 2025-04-07 | Completed | Completed | 2025-04-10 | Completed |  |  | N/A | N/A | N/A | N/A | 7 | 41
2502581 | Loh Chee Kuan | #VALUE! | Tham | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-03-12 | 2025-03-18 | Certificate Generated | 2026-03-11 | Completed | Completed | N/A | Completed | AR Berkat | 2025-03-24 | 2025-04-05 | Completed | 2025-04-07 | Completed | 2025-04-07 |  |  | N/A | N/A | N/A | N/A | 6 | 24
2501540 | Mohd Rushdi Bin Haji Abu Bakar | #VALUE! | Patricia | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-03-11 | 2025-03-18 | Certificate Generated | 2026-03-10 | Completed | Completed | N/A | Completed | PJ Plus | 2025-04-12 | 2025-04-04 | Completed | 2025-04-13 | Completed | 2025-04-13 |  |  | N/A | N/A | N/A | N/A | 7 | 102
2502571 | Ting Kam Peng | #VALUE! | Tham | R-PV | NEM | 11.8 | Astronergy 590Wp | 20 | Huawei SUN2000-10KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-03-07 | 2025-03-18 | Certificate Generated | 2026-03-06 | Completed | Completed | N/A | Completed | AR Berkat | 2025-03-25 | 2025-03-25 | Completed | 2025-04-03 | 2025-03-27 | Completed |  |  | N/A | N/A | N/A | N/A | 11 | 23
2502568 | Lim See Peng | #VALUE! | Tham | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-6KTL-M1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-03-13 | 2025-03-19 | Certificate Generated | 2026-03-12 | Completed | Completed | N/A | Completed | AR Berkat | 2025-06-10 | 2025-04-11 | Payment Required | 2025-04-14 | 2025-04-15 | Completed |  |  | N/A | N/A | N/A | N/A | 6 | 52
2404258 | Chan Yee Wan | #VALUE! | Tham | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2025-03-12 | 2025-03-18 | Certificate Generated | 2026-03-11 | Completed | Completed | N/A | Completed | AR Berkat | 2025-03-25 | Completed | Completed | 2025-04-14 | 2025-04-03 | 2025-04-14 | 2025-04-14 | 2035-04-30 | N/A | N/A | N/A | N/A | 6 | 35
2503588 | Lee Xue Cheng | #VALUE! | Tham | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-03-12 | 2025-03-18 | Certificate Generated | 2026-03-11 | Completed | Completed | N/A | Completed | AR Berkat | 2025-04-21 | 2025-04-11 | Completed | 2025-04-21 | 2025-04-18 | 2025-04-21 |  |  | N/A | N/A | N/A | N/A | 6 | 33
2502561 | Dennis Lee Jia Seng | #VALUE! | Tham | R-PV | NEM | 15.93 | Astronergy 590Wp | 27 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2025-03-12 | 2025-03-18 | Certificate Generated | 2026-03-11 | Completed | Completed | N/A | Completed | AR Berkat | 2025-04-10 | Completed | Completed | 2025-04-30 | 2025-04-24 | 2025-04-30 | 2025-04-30 | 2035-04-30 | N/A | N/A | N/A | N/A | 6 | 101
2503590 | Teh Wee Loon | #VALUE! | Tham | R-PV | NEM | 14.16 | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-03-13 | 2025-03-19 | Certificate Generated | 2026-03-12 | Completed | Completed | N/A | Completed | AR Berkat | 2025-04-08 | 2025-04-09 | Completed | 2025-04-16 | 2025-04-15 | 2025-04-16 |  |  | N/A | N/A | N/A | N/A | 6 | 56
2502570 | Tang Wei Keong | #VALUE! | Tham | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-03-13 | 2025-03-19 | Certificate Generated | 2026-03-12 | Completed | Completed | N/A | Completed | AR Berkat | 2025-06-16 | Completed | Completed | Completed | 2025-04-16 | Completed |  |  | N/A | N/A | N/A | N/A | 6 | 56
2502573 | Wong Jun Kit | #VALUE! | Simon | R-PV | NEM | 6.49 | Astronergy 590Wp | 11 | Huawei SUN2000-5KTL-M1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-03-12 | 2025-03-18 | Certificate Generated | 2026-03-11 | Completed | Completed | N/A | Completed | AR Berkat | 2025-05-02 | 2025-04-09 | Completed | 2025-04-16 | 2025-04-14 | 2025-04-16 |  |  | N/A | N/A | N/A | N/A | 6 | -45722
2503593 | Rashid Bin Darlan | #VALUE! | Patricia | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-03-12 | 2025-03-18 | Certificate Generated | 2026-03-11 | Completed | Completed | N/A | Completed | PJ Plus | 2025-05-02 | 2025-03-25 | Completed | 2025-04-14 | 2025-03-26 | 2025-04-14 |  |  | N/A | N/A | N/A | N/A | 6 | 16
2501211 | Great Beauty Furniture Sdn Bhd | #VALUE! | Chean Bang | C&I-PV | NEM | 26.55 | Astronergy 590Wp | 45 | Huawei SUN2000-20KTL | Pending Site Installation | 1st invoice | N/A | N/A | 2025-05-05 | 2025-05-20 | Certificate Generated | 2026-05-04 | Completed | Completed | Completed | Completed | [9 empty] | N/A | N/A | N/A | N/A | 15 | 150
2502589 | Chin Kok Leng | #VALUE! | Patricia | R-PV | NEM | 8.85 | Astronergy 590Wp | 15 | Huawei SUN2000-8KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-03-10 | 2025-03-18 | Certificate Generated | 2026-03-09 | Completed | Completed | N/A | Completed | PJ Plus | 2025-03-26 | Completed | Completed | Completed | 2025-03-26 | Completed |  |  | N/A | N/A | N/A | N/A | 8 | 60
2403090 | Mei Shun Fang Manufacturing Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 476.13 | Astronergy 590Wp | 807 | 0 | Pending ST License Approval | 5th invoice | 2025-05-05 | 2025-05-20 | 2025-05-30 | 2025-07-21 | Certificate Generated |  | Completed | Completed | Completed |  | AR Berkat | 2025-08-04 | [7 empty] | 2025-10-23 |  |  |  | 52 | 61
2502557 | Chin Yee Fa | #VALUE! | Patricia | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2025-03-13 | 2025-03-19 | Certificate Generated | 2025-03-12 | Completed | Completed | N/A | Completed | PJ Plus | 2025-05-06 | Completed | Completed | 2025-04-23 | Completed | 2025-04-23 | 2025-04-23 | 2035-04-30 | N/A | N/A | N/A | N/A | 6 | 50
2503594 | Wong Teck Keng | #VALUE! | Patricia | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | 2nd invoice | N/A | N/A | 2025-03-13 | 2025-03-17 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-04-29 | Completed | Completed | 2025-04-07 | Completed | 2025-04-07 |  |  | N/A | N/A | N/A | N/A | 4 | #REF!
2503597 | Bhajan Singh a/l S Bachan Singh | #VALUE! | Chean Bang | R-PV | NEM | 10.62 | Astronergy 590Wp | 18 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2025-03-13 | 2025-04-23 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-04-30 | 2025-04-25 | Completed | 2025-05-10 | 2025-04-30 | 2025-05-10 | 2025-05-10 | 2035-05-31 | N/A | N/A | N/A | N/A | 41 | #REF!
2502588 | Khadillah binti Hassan | #VALUE! | Patricia | R-PV | NEM | 8.85 | Astronergy 590Wp | 15 | Huawei SUN2000-8KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-03-13 | 2025-03-17 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-04-28 | Completed | Completed | 2025-04-22 | Completed | 2025-04-22 |  |  | N/A | N/A | N/A | N/A | 4
2502040 | ST Rosyam Mall (Plus Xnergy Services Sdn Bhd) | #VALUE! | Simon | EV Charger | 0 | 0 | - | - | - | Completed | Invoice Completed | N/A | N/A | N/A | N/A | N/A | N/A | Completed | Completed | N/A | Completed | Completed | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | #VALUE!
2503595 | Lim Zhi Jie | #VALUE! | Tham | R-PV | NEM | 14.16 | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-03-14 | 2025-03-20 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-04-09 | 2025-04-09 | Completed | 2025-04-18 | 2025-04-15 | 2025-04-18 |  |  | N/A | N/A | N/A | N/A | 6
2503586 | Safinaz Binti Mohd Sharif | #VALUE! | Patricia | R-PV | NEM | 6.49 | Astronergy 590Wp | 11 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-03-25 | 2025-03-26 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-05-14 | Completed | Completed | Completed | Completed | Completed |  |  | N/A | N/A | N/A | N/A | 1
2503604 | Kong Chun Seng | #VALUE! | Tham | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-03-25 | 2025-03-26 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-04-18 | 2025-04-16 | Completed | 2025-04-23 | 2025-04-18 | 2025-04-23 |  |  | N/A | N/A | N/A | N/A | 1
2503598 | Lew Yuen Tang | #VALUE! | Tham | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-04-03 | 2025-04-04 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-04-25 | 2025-04-16 | Completed | 2025-04-22 | 2025-04-21 | 2025-04-22 |  |  | N/A | N/A | N/A | N/A | 1
2503609 | Yau Hwee Tien | #VALUE! | Tham | R-PV | NEM | 14.16 | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-03-25 | 2025-05-19 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-05-22 | 2025-05-27 | Completed | 2025-06-20 | Completed | 2025-06-20 |  |  | N/A | N/A | N/A | N/A | 55
2503610 | Datuk Abdul Rani | #VALUE! | Tham | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2025-03-28 | 2025-04-04 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-04-16 | 2025-04-09 | Completed | 2025-04-17 | 2025-04-14 | 2025-04-17 | 2025-04-17 | 2035-04-30 | N/A | N/A | N/A | N/A | 7
2503611 | Augustine Kok Hwai Nam | #VALUE! | Tham | R-PV | NEM | 7.67 | Astronergy 590Wp | 13 | Huawei SUN2000-6KTL | Completed | Invoice Completed | N/A | N/A | 2025-03-28 | 2025-04-04 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-04-09 | 2025-04-16 | Completed | 2025-04-22 | 2025-04-21 | 2025-04-22 | 2025-04-22 | 2035-04-30 | N/A | N/A | N/A | N/A | 7
2501524 | Jeremy Koo Wui Ken | #VALUE! | Tham | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-03-28 | 2025-04-04 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-04-14 | Completed | Completed | Completed | 2025-04-16 | Completed |  |  | N/A | N/A | N/A | N/A | 7
2503617 | Vinny Len Siew Meng | #VALUE! | Patricia | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-03-28 | 2025-04-04 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-04-25 | 2025-04-16 | Completed | 2025-04-27 | 2025-04-24 | 2025-04-27 |  |  | N/A | N/A | N/A | N/A | 7
2503601 | William Song Jian Tat | #VALUE! | Tham | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | Pending Site Installation | 1st invoice | N/A | N/A | 2025-04-24 | 2025-05-19 | Certificate Generated | 2026-04-23 | Completed | Completed | N/A | Completed |  |  | Pending SEDA | [6 empty] | N/A | N/A | N/A | N/A | 25
2503619 | Haslina binti Othman | 0 | Patricia | 0 | 0 | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending Site Installation | 1st invoice | N/A | N/A | 2025-04-04 | 2025-04-14 | Certificate Generated | 2026-04-03 | Completed | Completed | N/A | Completed |  |  | 2025-04-18 | [6 empty] | N/A | N/A | N/A | N/A | 10
2504623 | Choy Poh Chu | #VALUE! | Patricia | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2025-04-09 | 2025-04-10 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-04-22 | 2025-04-18 | Completed | 2025-07-15 | 2025-04-21 | 2025-05-19 | 2025-05-19 | 2035-05-31 | N/A | N/A | N/A | N/A | 1
2503589 | Chong Shiuh Dyi | #VALUE! | Tham | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-04-09 | 2025-04-15 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-04-24 | 2025-04-18 | Completed | 2025-05-07 | Completed | 2025-05-07 |  |  | N/A | N/A | N/A | N/A | 6
2504633 | Yong Chee Seng | #VALUE! | Tham | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-04-11 | 2025-04-15 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-06-11 | 2025-04-17 | Completed | Completed | Completed | Completed |  |  | N/A | N/A | N/A | N/A | 4
2504636 | Nur Salinahany binti Hanafiah | #VALUE! | Patricia | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-04-11 | 2025-04-15 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-05-10 | 2025-04-18 | Completed | 2025-04-28 | 2025-04-22 | 2025-04-28 |  |  | N/A | N/A | N/A | N/A | 4
2406152 | Chara Sdn Bhd | #VALUE! | Simon | C&I-PV | NEM | 93.17 | Astronergy 605Wp | 154 | Huawei SN2000-40KTL + Huawei SUN2000-30KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-05-06 | 2025-05-17 | Certificate Generated |  | Completed | Completed | Completed | Completed | AX | 2025-06-16 | 2025-06-30 | Completed | 2025-07-21 | 2025-07-21 | Completed |  |  | N/A | N/A | N/A | N/A | 11
2504640 | Ng Mong Ping | #VALUE! | Tham | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-04-18 | 2025-04-21 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-05-09 | 2025-04-24 | Completed | Completed | Completed | Completed |  |  | N/A | N/A | N/A | N/A
2504638 | Lai Boon Liong | #VALUE! | Tham | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-04-17 | 2025-04-21 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-05-08 | 2025-04-24 | Completed | 2025-05-16 | 2025-05-06 | 2025-05-16 |  |  | N/A | N/A | N/A | N/A | 4
2504652 | Khairul Hisham Bin Mohamed | #VALUE! | Patricia | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | Completed | Invoice Completed | N/A | N/A | 2025-04-23 | 2025-04-28 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-05-15 | 2025-04-30 | Completed | 2025-06-02 | 2025-05-29 | 2025-06-02 | 2025-06-02 |  | N/A | N/A | N/A | N/A | 5
2504647 | Tan Hock Cheng | #VALUE! | Patricia | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-04-23 | 2025-04-28 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-05-29 | 2025-04-30 | Completed | Completed | 2025-05-08 | Completed |  |  | N/A | N/A | N/A | N/A | 5
2504658 | Phang Yeong Chin | #VALUE! | Ong | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | 2nd invoice | N/A | N/A | 2025-04-24 | 2025-04-28 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-06-04 | 2025-04-30 | Completed | Completed | 2025-05-13 | Completed |  |  | N/A | N/A | N/A | N/A | 4
2503614 | Yap Weoi Kee | 0 | Simon | 0 | 0 | 0 | Astronergy 590Wp | 15 | Solax 8kW | Pending Site Installation | 1st invoice | N/A | N/A | 2025-04-26 | 2025-04-29 | Certificate Generated | 2026-04-25 | Completed | Completed | N/A | Completed |  |  | 2025-04-30 | [6 empty] | N/A | N/A | N/A | N/A | 3
2504643 | Lee Sui Lian | #VALUE! | Patricia | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-04-26 | 2025-05-07 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-05-21 | 2025-05-27 | Completed | Completed | 2025-06-24 | Completed |  |  | N/A | N/A | N/A | N/A | 11
2504663 | Too Seng Eng | #VALUE! | Patricia | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-6KTL-M1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-04-26 | 2025-04-28 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-05-28 | 2025-04-30 | Completed | Completed | 2025-05-29 | Completed |  |  | N/A | N/A | N/A | N/A | 2
2504671 | Anthony Phua Kin Loong | #VALUE! | Patricia | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | Pending Site Installation | 1st invoice | N/A | N/A | 2025-05-06 | 2025-07-07 | Certificate Generated | 2026-05-05 | Completed | Completed | N/A | Completed |  |  | 2025-05-18 | Completed | 2025-06-02 | Completed | 2025-06-02 |  |  | N/A | N/A | N/A | N/A | 62
2506644 | Chang Kok Sang (Chang Vun Yu) | #VALUE! | Tham | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2025-05-06 | 2025-06-03 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-06-03 | 2025-06-17 | Completed | 2025-06-19 | Completed | 2025-06-19 | 2025-06-19 | 2035-06-30 | N/A | N/A | N/A | N/A | 28
2505675 | Tee Hup Soon | #VALUE! | Patricia | R-PV | NEM | 15.34 | Astronergy 590Wp | 26 | Huawei SUN2000-12KTL | Pending Site Installation | 1st invoice | N/A | N/A | 2025-05-06 | 2025-07-31 | Certificate Generated | 2026-05-05 | Completed | Completed | N/A | Completed | [9 empty] | N/A | N/A | N/A | N/A | 86
2502564 | Muhammad Arif Stephen bin Abddullah | #VALUE! | Simon | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Solinteg MHT-12K-25 hybrid | Pending NEM Welcome Letter | 1st invoice | N/A | N/A | 2025-05-13 | 2025-05-20 | Certificate Generated | 2026-05-12 | Completed | Completed | N/A | Completed | AR Berkat | 2025-05-23 | 2025-05-30 | Completed | 2025-06-09 | 2025-06-18 | Completed |  |  | N/A | N/A | N/A | N/A | 7
2504664 | Law Meng Siong | #VALUE! | Patricia | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | Pending NEM Qouta Approval | 1st invoice | N/A | N/A | 2025-05-13 |  | Waiting for Verification |  | Completed | Completed | N/A | Completed | [9 empty] | N/A | N/A | N/A | N/A | -45790
2504651 | Teh Bat Kuan (Teh Eng Lim) | #VALUE! | Tham | R-PV | NEM | 14.16 | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2025-05-14 | 2025-05-20 | Certificate Generated |  | Completed | Completed | N/A | Completed | Completed | 2025-06-13 | Completed | Completed | Completed | 2025-07-04 | 2025-07-10 | 2025-07-10 | 2035-07-31 | N/A | N/A | N/A | N/A | 6
2504049 | Ayer Keroh R&R (Southbound) - Green EV Charge Sdn Bhd | #VALUE! | Simon | EV Charger | 0 | 0 | - | - | - | Completed | 1st invoice | N/A | N/A | N/A | N/A | N/A | N/A | Completed | Completed | N/A | Completed | AR Berkat | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | #VALUE!
2505686 | Lai Kwee Far | #VALUE! | Patricia | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-05-14 | 2025-06-03 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-06-06 | 2025-06-10 | Completed | 2025-06-19 | Completed | 2025-06-19 |  |  | N/A | N/A | N/A | N/A | 20
2503603 | Dr Balbinder Singh a/l Gurbaksh Singh | #VALUE! | Tham | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-05-16 | 2025-05-20 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-06-05 | 2025-06-11 | Completed | 2025-07-04 | 2025-07-02 | 2025-07-04 |  |  | N/A | N/A | N/A | N/A | 4
2302004 | Ong Ah Chai | #VALUE! | Chean Bang | R-PV | NEM | 8.85 | Astronergy 590Wp | 15 | Huawei SUN2000-8KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-05-15 | 2025-05-20 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-06-10 | 2025-07-02 | Completed | 2025-07-06 | 2025-07-03 | 2025-07-06 |  |  | N/A | N/A | N/A | N/A | 5
2503225 | Weller Air-Cond Parts Enterprise Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 97.6 | Astronergy 610Wp | 160 | Huawei SUN2000-50KTL + SUN2000-20KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-05-21 | 2025-06-10 | Certificate Generated |  | Completed | Completed | Completed | Completed | Ax Electro | 2025-08-01 | 2025-08-07 | Completed | 2025-09-02 | 2025-08-22 | 2025-09-02 |  |  | N/A | N/A |  |  | 20
2403185 | Wan Kong Wing | #VALUE! | Tham | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-05-16 | 2025-05-20 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-06-06 | 2025-06-21 | Completed | 2025-06-25 | 2025-06-24 | 2025-06-25 |  |  | N/A | N/A | N/A | N/A | 4
2410194 | Berjayapak Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 207.08 | Yingli Solar 620Wp | 334 | Huawei SUN2000-50KTL + SUN2000-20KTL | Pending Site Installation | 3rd invoice | N/A | N/A | 2025-05-23 | 2025-06-10 | Certificate Generated |  | Completed | Completed | Completed | Completed | [9 empty] | N/A | N/A |  |  | 18
2504669 | Zohairen Bin Mhamad Sori | #VALUE! | Tham | R-PV | NEM | 10.62 | Astronergy 590Wp | 18 | Huawei SUN2000-8KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-05-20 | 2025-05-27 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-09-11 | 2025-09-12 | Completed | 2025-09-21 | 2025-09-22 | 2025-09-21 |  |  | N/A | N/A | N/A | N/A | 7
2504660 | Roshahni Binti Mhammad | #VALUE! | Chean Bang | R-PV | NEM | 14.75 | Astronergy 590Wp | 25 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-05-20 | 2025-09-23 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-10-01 | 2025-09-25 | Completed | 2025-10-03 | Completed | 2025-10-03 |  |  | N/A | N/A | N/A | N/A | 126
2410191 | Jowee Trading Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 53.68 | Astronergy 620Wp | 88 | Huawei SUN2000-20KTL x 2 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-06-26 | 2025-07-18 | Certificate Generated |  | Completed | Completed | Completed | Completed | PJ Plus | 2025-08-07 | 2025-08-15 | Completed | 2025-09-21 | 2025-08-28 | 2025-09-21 |  |  | N/A | N/A |  |  | 22
2505695 | Nur Salwahani Bt Muhammad | #VALUE! | Patricia | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | Pending Site Installation | 1st invoice | N/A | N/A | 2025-05-20 | 2025-05-24 | Certificate Generated | 2026-04-10 | Completed | Completed | N/A | Completed | [9 empty] | N/A | N/A | N/A | N/A | 4
2505672 | Tham Wai Hong | #VALUE! | Patricia | R-PV | NEM | 8.85 | Astronergy 590Wp | 15 | Huawei SUN2000-8KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-05-21 | 2025-05-24 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-06-04 | 2025-05-29 | Completed | 2025-06-19 | 2025-06-03 | 2025-06-19 |  |  | N/A | N/A | N/A | N/A | 3
2505684 | Ng Heng Hock | #VALUE! | Patricia | R-PV | NEM | 11.21 | Astronergy 590Wp | 19 | Huawei SUN2000-10KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-05-21 | 2025-05-24 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-06-12 | Completed | Completed | 2025-07-11 | 2025-07-08 | 2025-07-11 |  |  | N/A | N/A | N/A | N/A | 3
2505697 | Chong Yee Sam | #VALUE! | Patricia | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending Site Installation | 1st invoice | N/A | N/A | 2025-05-21 | 2025-05-24 | Certificate Generated | 2026-05-20 | Completed | Completed | N/A | Completed | [9 empty] | N/A | N/A | N/A | N/A | 3
2505688 | Heng Mooi Sing | #VALUE! | Tham | R-PV | NEM | 16.52 | Astronergy 590Wp | 28 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2025-05-21 | 2025-05-24 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-06-25 | 2025-07-08 | Completed | 2025-07-17 | Completed | 2025-07-17 | 2025-07-17 | 2035-07-31 | N/A | N/A | N/A | N/A | 3
2505682 | Lee Soo Kean | #VALUE! | Patricia | R-PV | NEM | 13.42 | Astronergy 610Wp | 22 | Huawei SUN2000-10KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-05-21 | 2025-07-07 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-07-12 | 2025-07-09 | Completed | 2025-07-30 | 2025-07-27 | 2025-07-30 |  |  | N/A | N/A | N/A | N/A | 47
2505699 | Kiren Kaur A/P Bhajan Singh | #VALUE! | Chean Bang | R-PV | NEM | 11.8 | Astronergy 590Wp | 20 | Huawei SUN2000-10KTL | Pending Site Installation | 1st invoice | N/A | N/A | 2025-05-21 | 2025-06-06 | Certificate Generated | 2026-05-20 | Completed | Completed | N/A | Completed | [9 empty] | N/A | N/A | N/A | N/A | 16
2503612 | Low Bok Tek | #VALUE! | Tham | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | Pending Site Installation | Invoice Completed | N/A | N/A | 2027-05-21 | 2025-05-24 | Certificate Generated | 2026-05-20 | Completed | Completed | N/A | Completed | [9 empty] | N/A | N/A | N/A | N/A | -727
2505680 | Chiang Hock Chiong | #VALUE! | Patricia | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | Pending Site Installation | 1st invoice | N/A | N/A | 2027-05-21 | 2025-05-29 | Certificate Generated | 2026-05-20 | Completed | Completed | N/A | Completed | [9 empty] | N/A | N/A | N/A | N/A | -722
2503607 | Goh Boon Leng | #VALUE! | Tham | R-PV | NEM | 10.62 | Astronergy 590Wp | 18 | Huawei SUN2000-8KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-06-20 | 2025-06-24 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-07-29 | 2025-07-29 | Completed | 2025-08-09 | 2025-08-08 | 2025-08-09 |  |  | N/A | N/A | N/A | N/A | 4
2505711 | Lee Len Foong | #VALUE! | Chean Bang | R-PV | NEM | 8.26 | Astronergy 590Wp | 14 | Huawei SUN2000-6KTL | Pending NEM Qouta Approval | 1st invoice | N/A | N/A | 2025-05-29 |  | Waiting for Verification |  | Completed | Completed | N/A | Completed | [9 empty] | N/A | N/A | N/A | N/A | -45806
2505713 | Yap Swee Piau | #VALUE! | Patricia | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-06-13 | 2025-06-25 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-07-02 | Completed | Completed | 2025-07-31 | 2025-07-23 | 2025-07-31 |  |  | N/A | N/A | N/A | N/A | 12
2505714 | Kong King Wai | #VALUE! | Tham | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending Site Installation | 1st invoice | N/A | N/A | 2025-06-04 | 2025-06-16 | Certificate Generated | 2025-06-16 | Completed | Completed | N/A | Completed | [9 empty] | N/A | N/A | N/A | N/A | 12
2405306 | Leong Ah Seng | #VALUE! | Tham | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | Completed | Invoice Completed | N/A | N/A | 2025-05-21 | 2025-06-09 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-06-26 | 2025-07-07 | Completed | 2025-07-16 | 2025-07-15 | 2025-07-16 | 2025-07-16 | 2025-07-31 | N/A | N/A | N/A | N/A | 19
2505705 | Lee Kee Chew | #VALUE! | Tham | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2025-06-03 | 2025-06-16 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-06-24 | Completed | Completed | 2025-07-26 | 2025-07-15 | 2025-07-26 | 2025-07-15 | 2035-07-31 | N/A | N/A | N/A | N/A | 13
2505717 | Sia Wee Leng | #VALUE! | Tham | R-PV | NEM | 16.52 | Astronergy 590Wp | 28 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-06-06 | 2025-06-22 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-07-03 | 2025-07-08 | Completed | 2025-07-16 | 2025-07-11 | 2025-07-16 |  |  | N/A | N/A | N/A | N/A | 16
2505699-1 | Leong Wai Wung | #VALUE! | Tham | R-PV | NEM | 11.8 | Astronergy 590Wp | 20 | Huawei SUN2000-10KTL | Pending NEM Qouta Submission | 1st invoice | N/A | N/A |  |  |  |  | Completed | Completed | N/A | Completed | [9 empty] | N/A | N/A | N/A | N/A | 0
2505719 | Lim Jun Hong | #VALUE! | Tham | R-PV | NEM | 11.78 | Astronergy 620Wp | 19 | Huawei SUN2000-10KTL | Pending NEM Welcome Letter | 2nd invoice | N/A | N/A | 2025-06-06 | 2025-08-03 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-08-01 | Completed | Completed | 2025-08-09 | Completed | 2025-08-09 |  |  | N/A | N/A | N/A | N/A | 58
2505687 | Thayananthan A/L Lokanatan | #VALUE! | Patricia | R-PV | NEM | 10.03 | Astronergy 590Wp | 17 | Huawei SUN2000-8KTL | Pending NEM Qouta Approval | 2nd invoice | N/A | N/A | 2025-06-25 |  | Waiting for Verification |  | Completed | Completed | N/A | Completed | [9 empty] | N/A | N/A | N/A | N/A | -45833
2505718 | Koh Kheat Kian | #VALUE! | Chean Bang | R-PV | NEM | 7.44 | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-M1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-06-12 | 2025-06-28 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-08-01 | Completed | Completed | 2025-08-19 | Completed | 2025-08-19 |  |  | N/A | N/A | N/A | N/A | 16
2506726 | Poh Pun Hong | #VALUE! | Ong | R-PV | NEM | 7.44 | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-06-12 | 2025-06-28 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-07-30 | 2025-07-28 | Completed | 2025-08-07 | Completed | 2025-08-07 |  |  | N/A | N/A | N/A | N/A | 16
2506735 | Lee Meng Fui | #VALUE! | Patricia | R-PV | NEM | 7.44 | Astronergy 610Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-06-13 | 2025-06-28 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-07-10 | 2025-07-04 | Completed | 2025-07-08 | 2025-07-07 | 2025-07-08 |  |  | N/A | N/A | N/A | N/A | 15
2506734 | Leow Siew Lian (Tee Hong Yee) | #VALUE! | Patricia | R-PV | NEM | 11.16 | Astronergy 610Wp | 18 | Huawei SUN2000-8KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-06-13 | 2025-06-28 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-07-11 | 2025-07-02 | Completed | 2025-07-11 | 2025-07-04 | 2025-07-11 |  |  | N/A | N/A | N/A | N/A | 15
2505708 | Mohd Shariff | #VALUE! | Tham | R-PV | NEM | 7.44 | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Qouta Submission | 1st invoice | N/A | N/A |  |  |  |  | Completed | Completed | N/A | Completed | [9 empty] | N/A | N/A | N/A | N/A | 0
2506744 | Gan Chin Sam | #VALUE! | Tham | R-PV | NEM | 14.88 | Astronergy 620Wp | 24 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | 2nd invoice | N/A | N/A | 2025-06-13 | 2025-07-16 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-08-07 | 2025-08-14 | Completed | 2025-08-25 | 2025-08-19 | 2025-08-25 |  |  | N/A | N/A | N/A | N/A | 33
2506727 | Tan Lee Khing | #VALUE! | Patricia | R-PV | NEM | 12.4 | Astronergy 620Wp | 20 | Huawei SUN2000-10KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-06-16 | 2025-06-28 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-07-31 | 2025-08-01 | Completed | 2025-08-19 | 2025-08-08 | 2025-08-19 |  |  | N/A | N/A | N/A | N/A | 12
2505054 | DK Senza Residence | #VALUE! | Simon | EV Charger | 0 | 0 | - | - | - | Completed | 1st invoice | N/A | N/A | N/A | N/A | N/A | N/A | Completed | Completed | N/A | Completed | AR Berkat | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | #VALUE!
2506752 | Ng Cheng Hoe | #VALUE! | Tham | R-PV | NEM | 7.44 | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-06-20 | 2025-06-28 | Certificate Generated |  | Completed | Completed | N/A | Completed | Ar Berkat | 2025-07-31 | 2025-07-29 | Completed | 2025-08-06 | 2025-08-06 | 2025-08-06 |  |  | N/A | N/A | N/A | N/A | 8
2501523 | Chen Kim Hock | #VALUE! | Tham | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | Pending Meter Change | 1st invoice | N/A | N/A | 2025-06-23 | 2025-08-02 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-09-23 | 2025-10-07 | Replacing Meter | 2025-10-24 |  |  |  |  | N/A | N/A | N/A | N/A | 40
2506748 | Teh Foo Hock | #VALUE! | Patricia | R-PV | NEM | 8.68 | Astronergy 620Wp | 14 | Huawei SUN2000-8KTL | Pending NEM Welcome Letter | 1st invoice | N/A | N/A | 2025-06-20 | 2025-06-28 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-08-19 | 2025-08-27 | Completed | 2025-09-05 | Completed | 2025-09-05 |  |  | N/A | N/A | N/A | N/A | 8
2505709 | Tan Heng Lian | #VALUE! | Patricia | R-PV | NEM | 17.98 | Astronergy 620Wp | 29 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-06-18 | 2025-06-28 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-08-02 | 2025-08-04 | Completed | 2025-08-07 | 2025-08-06 | 2025-08-07 |  |  | N/A | N/A | N/A | N/A | 10
2501531 | Mohamad Hafizi Bin Abdul Rahman | #VALUE! | Patricia | R-PV | NEM | 13.64 | Astronergy 620Wp | 22 | Huawei SUN2000-10KTL | Pending Site Installation | 1st invoice | N/A | N/A | 2025-06-18 | 2025-06-28 | Certificate Generated | 2026-06-17 | Completed | Completed | N/A | Completed | [9 empty] | N/A | N/A | N/A | N/A | 10
2506757 | Chai Cheong Sing | #VALUE! | Patricia | R-PV | NEM | 7.44 | Astronergy 620Wp | 12 | Huawei SUN2000-6KTL-M1 | Completed | Invoice Completed | N/A | N/A | 2025-06-24 | 2025-07-17 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-08-12 | 2025-08-26 | Completed | 2025-09-10 | Completed | 2025-09-10 | 2025-09-10 | 2035-09-30 | N/A | N/A | N/A | N/A | 23
2505259 | Liew Wen Qi | #VALUE! | Patricia | C&I-PV | NEM | 19.52 | Astronergy 610Wp | 32 | Huawei SUN2000-17KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-06-26 | 2025-07-22 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-07-26 | 2025-07-28 | Completed | Completed | 2025-08-01 | Completed |  |  | N/A | N/A | N/A | N/A | 26
2506758 | Goh Boon Meng | #VALUE! | Patricia | R-PV | NEM | 17.98 | Astronergy 620Wp | 29 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-06-20 | 2025-09-10 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-10-03 | 2025-10-07 | Completed | Completed | Completed | Completed |  |  | N/A | N/A | N/A | N/A | 82
2506762 | Megat Mohd Nashrul Bin Ahmad Zulkepli | #VALUE! | Patricia | R-PV | NEM | 12.4 | Astronergy 620Wp | 20 | Huawei SUN2000-10KTL | Pending NEM Qouta Submission | 1st invoice | N/A | N/A |  |  |  |  | Completed | Completed | N/A | Completed | [9 empty] | N/A | N/A | N/A | N/A | 0
2506753 | Lim Geok Suan | #VALUE! | Patricia | R-PV | NEM | 11.78 | Astronergy 620Wp | 19 | Huawei SUN2000-10KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-06-25 | 2205-07-15 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-07-30 | 2025-07-31 | Completed | 2025-08-05 | 2025-08-01 | 2025-08-05 |  |  | N/A | N/A | N/A | N/A | 65763
2506768 | Yap Lee Yan | #VALUE! | Patricia | R-PV | NEM | 11.16 | Astronergy 620Wp | 18 | Huawei SUN2000-10KTL | Pending NEM Welcome Letter | 2nd invoice | N/A | N/A | 2025-06-25 | 2025-07-16 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-08-16 | 2025-08-22 | Completed | 2025-10-02 | 2025-08-28 | 2025-10-02 |  |  | N/A | N/A | N/A | N/A | 21
2506761 | Lee Swee Li | #VALUE! | Patricia | R-PV | NEM | 13.64 | Astronergy 620Wp | 22 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-06-25 | 2025-09-08 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-09-17 | Completed | Completed | Completed | 2025-09-22 | Completed |  |  | N/A | N/A | N/A | N/A | 75
2506779 | Koo Hing Yew | #VALUE! | Patricia | R-PV | NEM | 7.44 | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-06-25 | 2025-07-16 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-08-13 | 2025-08-19 | Completed | Completed | 2025-08-22 | Completed |  |  | N/A | N/A | N/A | N/A | 21
2506781 | Teng Lily | #VALUE! | Patricia | R-PV | NEM | 7.44 | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | 2nd invoice | N/A | N/A | 2025-06-25 | 2025-07-16 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-08-25 | 2025-09-10 | Completed | 2025-10-09 | 2025-10-08 | 2025-10-09 |  |  | N/A | N/A | N/A | N/A | 21
2506782 | Tan Shu Huat | #VALUE! | Patricia | R-PV | NEM | 14.88 | Astronergy 620Wp | 24 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-06-25 | 2025-07-16 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-08-27 | 2025-08-27 | Completed | 2025-09-13 | Completed | 2025-09-13 |  |  | N/A | N/A | N/A | N/A | 21
2506746 | Tan Wan Ngee | #VALUE! | Patricia | R-PV | NEM | 9.92 | Astronergy 620Wp | 16 | Huawei SUN2000-8KTL | Pending Site Installation | 1st invoice | N/A | N/A | 2025-06-25 | 2025-07-17 | Certificate Generated | 2026-06-24 | Completed | Completed | N/A | Completed | [9 empty] | N/A | N/A | N/A | N/A | 22
2506780 | Yeo Khai Boon | #VALUE! | Patricia | R-PV | NEM | 9.92 | Astronergy 620Wp | 16 | Huawei SUN2000-8KTL | Pending Site Installation | 2nd invoice | N/A | N/A | 2025-06-25 | 2025-09-08 | Certificate Generated | 2026-06-24 | Completed | Completed | N/A | Completed | [9 empty] | N/A | N/A | N/A | N/A | 75
2506778 | Teo Lun Wei | #VALUE! | Patricia | R-PV | NEM | 7.44 | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending Site Installation | 1st invoice | N/A | N/A | 2025-06-25 | 2025-07-16 | Certificate Generated | 2026-06-24 | Completed | Completed | N/A | Completed | [9 empty] | N/A | N/A | N/A | N/A | 21
2506745 | Lee Ban Hong | #VALUE! | Tham | R-PV | NEM | 14.88 | Astronergy 620Wp | 24 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-06-20 | 2025-08-02 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-08-04 | 2025-08-04 | Completed | 2025-08-14 | 2025-08-14 | 2025-08-14 |  |  | N/A | N/A | N/A | N/A | 43
2506789 | Wu Sio Yunn | #VALUE! | Patricia | R-PV | NEM | 9.92 | Astronergy 620Wp | 16 | Huawei SUN2000-8KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-06-26 | 2025-07-17 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-08-20 | 2025-08-22 | Completed | 2025-09-25 | 2025-08-28 | 2025-09-25 |  |  | N/A | N/A | N/A | N/A | 21
2404254 | Meor Farizal Bin Ramli | #VALUE! | Chean Bang | R-PV | SELCO | 5.58 | Astronergy 620Wp | 9 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | N/A | N/A | N/A | N/A | Completed | Completed | N/A | Completed | PJ Plus | 2025-08-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | #VALUE!
2506732 | Chai Shwu Yi (Tan Lewin) | #VALUE! | Simon | R-PV | NEM | 7.44 | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | 2nd invoice | N/A | N/A | 2025-06-26 | 2025-07-17 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-08-20 | 2025-08-20 | Completed | 2025-09-05 | Completed | 2025-09-05 |  |  | N/A | N/A | N/A | N/A | 21
2506767 | Lee Lee Tan @ Tan Lee Lee | #VALUE! | Tham | R-PV | NEM | 7.44 | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 | Completed | Invoice Completed | N/A | N/A | 2025-06-26 | 2025-07-16 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-08-26 | 2025-08-27 | Completed | 2025-09-10 | 2025-09-22 | 2025-09-10 | 2025-09-10 | 2035-09-30 | N/A | N/A | N/A | N/A | 20
2506759 | Yim Kai Mun | #VALUE! | Patricia | R-PV | NEM | 10.54 | Astronergy 620Wp | 17 | Huawei SUN2000-8KTL | Pending NEM Welcome Letter | 2nd invoice | N/A | N/A | 2025-06-26 | 2025-07-17 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-08-05 | 2025-08-01 | Completed | 2025-08-07 | 2025-08-04 | 2025-08-07 |  |  | N/A | N/A | N/A | N/A | 21
2506794 | Ahmad Fadhil Bin Alias | #VALUE! | Patricia | R-PV | NEM | 9.92 | Astronergy 620Wp | 16 | Huawei SUN2000-8KTL | Pending NEM Welcome Letter | 2nd invoice | N/A | N/A | 2025-06-27 | 2025-09-25 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-10-07 | 2025-10-08 | Completed | 2025-10-26 | Completed | 2025-10-26 |  |  | N/A | N/A | N/A | N/A | 90
2506798 | Lew Sieow Shih | #VALUE! | Patricia | R-PV | NEM | 7.44 | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending Site Installation | 1st invoice | N/A | N/A | 2025-06-27 | 2025-07-17 | Certificate Generated | 2026-06-26 | Completed | Completed | N/A | Completed | [9 empty] | N/A | N/A | N/A | N/A | 20
2506773 | Leiw Chew Choi | #VALUE! | Patricia | R-PV | NEM | 14.88 | Astronergy 620Wp | 24 | Huawei SUN2000-12KTL | Pending Site Installation | 1st invoice | N/A | N/A | 2025-06-27 | 2025-07-16 | Certificate Generated | 2026-06-26 | Completed | Completed | N/A | Completed | [9 empty] | N/A | N/A | N/A | N/A | 19
2506789-1 | Lim Kim Kiew | #VALUE! | Chean Bang | R-PV | NEM | 7.44 | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-06-26 | 2025-07-17 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-06-06 | 2025-08-11 | Completed | Completed | 2025-08-14 | Completed |  |  | N/A | N/A | N/A | N/A | 21
2506786 | Lim Chee Seng | #VALUE! | Tham | R-PV | NEM | 13.64 | Astronergy 620Wp | 22 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-06-30 | 2025-08-01 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-08-13 | 2025-08-13 | Completed | 2025-08-18 | 2025-08-19 | 2025-08-18 |  |  | N/A | N/A | N/A | N/A | 32
2505260 | Canning Garden Baptist Church | #VALUE! | Patricia | C&I-PV | NEM | 48.36 | Astronergy 620Wp | 78 | Huawei SUN2000-36KTL | Pending Meter Change | 2nd invoice | N/A | N/A | 2025-06-26 | 2025-08-07 | Certificate Generated |  | Completed | Completed | N/A | Completed | AR Berkat | 2025-10-13 | 2025-10-21 | Payment Required | 2025-10-24 |  |  |  |  | N/A | N/A | N/A | N/A | 42
2506799 | Lee Cheow Ban | #VALUE! | Patricia | R-PV | NEM | 13.64 | Astronergy 620Wp | 22 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-06-27 | 2025-07-16 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-08-07 | 2025-08-11 | Completed | 2025-08-27 | 2025-08-14 | 2025-08-27 |  |  | N/A | N/A | N/A | N/A | 19
2506276 | Tew Ah Sing @ Teo Ah Sing | #VALUE! | Chean Bang | R-PV | NEM | 19.84 | Astronergy 620Wp | 32 | Huawei SUN2000-17KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-06-30 | 2025-08-03 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-09-02 | Completed | Completed | 2025-09-24 | 2025-09-22 | 2025-09-24 |  |  | N/A | N/A | N/A | N/A | 34
2506785 | Mohd Nurazuwan Bin Radzi | #VALUE! | Patricia | R-PV | NEM | 13.64 | Astronergy 620Wp | 22 | Huawei SUN2000-12KTL | Pending NEM Qouta Approval | 1st invoice | N/A | N/A | 2025-06-30 |  | Waiting for Verification |  | Completed | Completed | N/A | Completed | [9 empty] | N/A | N/A | N/A | N/A | -45838
2506801 | Lim Joo Eng | #VALUE! | Patricia | R-PV | NEM | 17.98 | Astronergy 620Wp | 29 | Huawei SUN2000-12KTL | Pending Site Installation | 1st invoice | N/A | N/A | 2025-06-30 | 2025-08-01 | Certificate Generated | 2026-06-29 | Completed | Completed | N/A | Completed | [9 empty] | N/A | N/A | N/A | N/A | 32
2503223 | Insultec Duragate Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 58.9 | Yingli Solar 620Wp | 95 | Huawei SUN2000-50KTL | Pending Site Installation | 2nd invoice | N/A | N/A | 2025-06-26 | 2025-08-06 | Certificate Generated |  | Completed | Completed | N/A | Completed | [9 empty] | N/A | N/A |  |  | 41
2506802 | Hung Wen Hao | #VALUE! | Patricia | R-PV | NEM | 13.64 | Astronergy 620Wp | 22 | Huawei SUN2000-12KTL | Pending NEM Qouta Approval | Pending 1st Invoice | N/A | N/A | 2025-06-30 |  | Waiting for Verification |  | Completed | Completed | N/A | Completed | [9 empty] | N/A | N/A | N/A | N/A | -45838
2412510 | How Toon Huah | #VALUE! | Chean Bang | R-PV | NEM | 14.88 | Astronergy 620Wp | 24 | Huawei SUN2000-12KTL | Pending NEM Welcome Letter | Invoice Completed | N/A | N/A | 2025-06-25 | 2025-08-03 | Certificate Generated |  | Completed | Completed | N/A | Completed | PJ Plus | 2025-08-21 | Completed | Completed | 2025-09-08 | 2025-09-03 | 2025-09-08 |  |  | N/A | N/A | N/A | N/A | 39
2504051 | G. Semanggol R&R (Northbound) - Green EV Charge Sdn Bhd | #VALUE! | Simon | EV Charger | 0 | 0 | 0 | 0 | 0 | Pending ST License Application | Pending 1st Invoice | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | #VALUE!
2505056 | TMG Mall Tanjung Lumpur (Handal Green Mobility) | #VALUE! | Chean Bang | EV Charger | 0 | 0 | 0 | 0 | 0 | Pending ST License Application | Invoice Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | #VALUE!
2507833 | Yee Main Way | #VALUE! | Patricia | R-PV | SELCO | 12.4 | Astronergy 620Wp | 20 | Solax 10kW | Pending Site Installation | Invoice Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | N/A | N/A | N/A | N/A | #VALUE!
2409030 | TMG Mall Bandar Indera Mahkota (Handal Green Mobility) | #VALUE! | Chean Bang | EV Charger | 0 | 0 | 0 | 0 | 0 | Pending Site Installation | Invoice Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | N/A | N/A | N/A | N/A | #VALUE!
2507059 | TMG Mall IM16 (Handal Green Mobility) | #VALUE! | Chean Bang | EV Charger | 0 | 0 | 0 | 0 | 0 | Pending Site Installation | Invoice Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | N/A | N/A | N/A | N/A | #VALUE!
2507060 | TMG Mall Temerloh (Handal Green Mobility) | #VALUE! | Chean Bang | EV Charger | 0 | 0 | 0 | 0 | 0 | Pending Site Installation | Invoice Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | N/A | N/A | N/A | N/A | #VALUE!
2508858 | Chan Weng Leong | #VALUE! | Patricia | R-PV | SELCO | 16.12 | Astronergy 620Wp | 26 | Solax 12kW | Completed | Invoice Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Completed | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | #VALUE!
2507062 | Tapah R&R (Southbound) - Green EV Charge Sdn Bhd | #VALUE! | Simon | EV Charger | 0 | 0 | 0 | 0 | 0 | Pending Site Installation | 1st invoice | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | N/A | N/A | N/A | N/A | #VALUE!
2509863 | Goh Soon Teck | #VALUE! | Patricia | R-PV | SELCO | 9.92 | Astronergy 620Wp | 16 | Solax 7.5kW | Pending Site Installation | 1st invoice | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [13 empty] | #VALUE!
2507840 | Chew Kok leong | #VALUE! | Patricia | R-PV | SELCO | 15.5 | Astronergy 620Wp | 25 | Solax 12kW | Pending Site Installation | 1st invoice | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [13 empty] | #VALUE!
2508857 | Chong Horng Tat | #VALUE! | Ong | R-PV | SELCO | 8.68 | Astronergy 620Wp | 14 | Solax 8kW | Pending Site Installation | 2nd invoice | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [13 empty] | #VALUE!
2305008 | Yeap Chooi Hock | #VALUE! | Patricia | C&I-PV | SELCO | 17.98 | Astronergy 620Wp | 29 | Solax 15kW | Pending Site Installation | 1st invoice | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [13 empty] | #VALUE!
2508856 | Eddie Leong Kai Sheng | #VALUE! | Ong | R-PV | SELCO | 18.6 | Astronergy 620Wp | 30 | Fox ESS 12kW | Pending Site Installation | 1st invoice | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [13 empty] | #VALUE!
2510877 | Wang Pay Chen | #VALUE! | Patricia | R-PV | SELCO | 9.92 | Astronergy 620Wp | 16 | Solax 8kW | Pending Site Installation | 1st invoice | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [13 empty] | #VALUE!
2511887 | Lee Hang Meng | #VALUE! | Patricia | R-PV | SELCO | 12.4 | Astronergy 620Wp | 19 | Fox ESS 10kW | Pending Site Installation | 1st invoice | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [13 empty] | #VALUE!
2305019 | Soe Yew Seng | #VALUE! | Simon | R-PV | SELCO | 15.5 | Astronergy 620Wp | 25 | Fox ESS 12kW | Pending Site Installation | 1st invoice | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [13 empty] | #VALUE!
Note on R209: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Change to 17.7kWp
Note on S218: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SEDA queries on the voltage
Note on R221: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Change to three phase
Note on R222: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Change in PV capacity

## In Progress
Item | To Be Done (X) | In Progress (Y) | Completed (Z)
SEDA NEMCD | 368 | 105 | 229
ST License | 3 | #VALUE! | 2
LHDN Stamping | -105 | 2 | 303
GITA Asset | 13 | #VALUE! | 2
Project No | Client Name | Location | Sales PIC | Category | Scheme | System Capacity | Module | Module Quantity | Inverter | 0 | Project Status
2310076 | Loo Thiam Seng | #VALUE! | Tham | R-PV | NEM | 8.26 | Astronergy 590Wp | 14 | Huawei SUN2000-6KTL | 0 | Pending NEM Welcome Letter
2312113 | Razman Bin Samsudin | #VALUE! | Simon | R-PV | NEM | 13.8 | Astronergy 575Wp | 24 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2401063 | Weller Air-Cond Parts Enterprise Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 26.91 | Astronergy 585Wp | 46 | Huawei SUN2000-20KTL | 0 | Pending GITA Application
2402079 | Intergreen Holdings Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 46.8 | Astronergy 585Wp | 80 | Huawei SUN2000-12KTL-M5 x 2 Huawei SUN2000-12KTL-MB0 x 1 | 0 | Pending GITA Application
2402080 | CK Fresh Sdn Bhd | #VALUE! | Tham | C&I-PV | SELCO | 43.29 | Astronergy 585Wp | 74 | Huawei SUN2000-30KTL | 0 | Pending GITA Application
2404211 | Nor Fadillah | #VALUE! | Tham | R-PV | NEM | 17.55 | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2404111 | Budi Jelas Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 26.91 | Astronergy 585Wp | 46 | Huawei SUN2000-20KTL | 0 | Pending GITA Application
2403102 | Sleep Matics (Asia) Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 374.4 | Astronergy 585Wp | 640 | Huawei SUN2000-115KTL x 2 Huawei SUN2000-50KTL x 1 | 0 | Pending ST License Application
2312059 | CHL Foam Industries Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 345.15 | Astronergy 585Wp | 590 | Huawei SUN2000-115KTL x 2 Huawei SUN2000-30KTL x 1 | 0 | Pending GITA Application
2310035 | Advantic Nutraceuticals | #VALUE! | Tham | C&I-PV | NEM | 87.84 | Astronergy 610Wp | 144 | Huawei SUN2000-30KTL + Huawei SUN2000-36KTL | 0 | Pending GITA Application
2403088 | Chua Tong Hin Hardware Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 37.44 | Astronergy 585Wp | 64 | Huawei SUN2000-30KTL | 0 | Pending GITA Application
2409445 | Phang Kar Teck | #VALUE! | Patricia | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2409442 | Lee Chiou Horng | #VALUE! | Tham | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | 0 | Pending NEM Welcome Letter
2408417 | Mohmad Nazeri bin Abdul Wahab | #VALUE! | Tham | R-PV | NEM | 17.55 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | 0 | Pending Meter Change
2308064 | Low Yin Jun | #VALUE! | Simon | R-PV | NEM | 11.7 | Astronergy 585Wp | 20 | Solinteg MHT-10K-25 hybrid | 0 | Pending NEM Welcome Letter
2404249 | Tan Kheng Guan | #VALUE! | Tham | R-PV | NEM | 17.55 | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | 0 | Pending Site Installation
2405284 | Amirul Hakim bin Omar | #VALUE! | Tham | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2409448 | Pang Chong Han | #VALUE! | Simon | R-PV | NEM | 8.26 | Astronergy 590Wp | 14 | Solinteg MHS-8K-25 | 0 | Pending NEM Welcome Letter
2405305 | Chan Woei Jye | #VALUE! | Tham | R-PV | NEM | 10.53 | Astronergy 585Wp | 18 | Huawei SUN2000-8KTL | 0 | Pending NEM Welcome Letter
2407167-1 | Econframe Marketing Sdn Bhd (Kilang 1 & 3) | #VALUE! | Tham | C&I-PV | NEM | 109.395 | Yingli Solar 585Wp | 187 | Huawei SUN2000-50KTL + SUN2000-36KTL | 0 | Pending GITA Application
2407167-2 | Econframe Marketing Sdn Bhd (Kilang 4) | #VALUE! | Tham | C&I-PV | NEM | 26.91 | Yingli Solar 585Wp | 46 | Huawei SUN2000-20KTL | 0 | Pending GITA Application
2407167-3 | Econframe Marketing Sdn Bhd (Kilang 20) | #VALUE! | Tham | C&I-PV | NEM | 67.275 | Yingli Solar 585Wp | 115 | Huawei SUN2000-50KTL | 0 | Pending GITA Application
2408174 | Zimandy Construction Sdn Bhd (Bandar Tenggara) | #VALUE! | Tham | C&I-PV | NEM | 120.95 | Astronergy 590Wp | 205 | Huawei SUN2000-40KTL +SUN2000-30KTL + SUN2000-20KTL | 0 | Pending NEM Welcome Letter
2408179 | Pelita Hijrah Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 107.64 | Astronergy 585Wp | 184 | Huawei SUN2000-20KTL x 4 | 0 | Pending GITA Application
2409185 | Kim Chong Mechanical Services Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 26.55 | Astronergy 590Wp | 45 | Huawei SUN2000-20KTL | 0 | Pending GITA Application
2410196 | Unilink Machinery Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 26.55 | Astronergy 590Wp | 45 | Huawei SUN2000-20KTL | 0 | Pending GITA Application
2410468 | Teo Boon Ling | #VALUE! | Tham | R-PV | NEM | 11.7 | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL | 0 | Pending NEM Welcome Letter
2410471 | Chua Lu Chuan | #VALUE! | Chean Bang | R-PV | NEM | 17.55 | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | 0 | Pending Site Installation
2411494 | Pang Kim Soon | #VALUE! | Chean Bang | R-PV | NEM | 17.55 | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2404224 | Vijayalakshmi a/p Krishnaswamy (Tan Sri Rama Iyer) | #VALUE! | Tham | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2411491 | Low Kim Keong | #VALUE! | Chean Bang | R-PV | NEM | 11.7 | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL | 0 | Pending NEM Welcome Letter
2412503 | Lian Hock Seng | #VALUE! | Chean Bang | R-PV | NEM | 14.04 | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2412505 | Dong Mee Hong | #VALUE! | Patricia | R-PV | NEM | 14.04 | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2412515 | Liew Mun Meng | #VALUE! | Tham | R-PV | NEM | 17.55 | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2410462 | Yee Mei Ling | #VALUE! | Tham | R-PV | NEM | 7.02 | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2412524 | Teng Lee Xung | #VALUE! | Chean Bang | R-PV | NEM | 14.16 | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2412513 | Ganapathy Srihari a/l Rama Iyer | #VALUE! | Tham | R-PV | NEM | 10.03 | Astronergy 590Wp | 17 | Huawei SUN2000-8KTL | 0 | Pending NEM Welcome Letter
2501532 | Prasert Phromsuwan | #VALUE! | Tham | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | 0 | Pending NEM Welcome Letter
2501544 | Gan Tek Chuan | #VALUE! | Patricia | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2502548 | Wong Kok Wai | #VALUE! | Chean Bang | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2501545 | Lee Tian Look | #VALUE! | Chean Bang | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2311088 | Lee Chean Chung | #VALUE! | Chean Bang | R-PV | NEM | 10.62 | Astronergy 590Wp | 18 | Huawei SUN2000-10KTL | 0 | Pending NEM Welcome Letter
2502216 | Low Yi Chin | #VALUE! | Chean Bang | C&I-PV | NEM | 14.16 | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2502553 | Salim Majid Zain Bin Abdul Majid | #VALUE! | Tham | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2502547 | Chong Chee Hoo | #VALUE! | Tham | R-PV | NEM | 11.8 | Astronergy 590Wp | 20 | Huawei SUN2000-10KTL | 0 | Pending NEM Welcome Letter
2502541 | Boo Kee Meng | #VALUE! | Tham | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2502556 | Gan Chong Sing | #VALUE! | Patricia | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2502551 | Tan Seng Shen | #VALUE! | Tham | R-PV | NEM | 14.16 | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2502546 | Jordan Tan Heng Xiang | #VALUE! | Tham | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-6KTL | 0 | Pending NEM Welcome Letter
2502559 | Wong Peng Soon | #VALUE! | Chean Bang | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | 0 | Pending NEM Welcome Letter
2502550 | Ricky Goh Hoon Kan | #VALUE! | Chean Bang | R-PV | NEM | 14.75 | Astronergy 590Wp | 25 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2502560 | Lim Sooi Poh | #VALUE! | Tham | R-PV | NEM | 14.16 | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2408411-1 | Eng Khai Shu | #VALUE! | Tham | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2502565 | Yeo Shu Jin | #VALUE! | Simon | R-PV | NEM | 7.67 | Astronergy 590Wp | 13 | Huawei SUN2000-6KTL | 0 | Pending Site Installation
2502549 | Har Hock Lee | #VALUE! | Patricia | R-PV | NEM | 14.16 | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2405286 | Wong Wai Hung | #VALUE! | Tham | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2501527 | Kuan Guan Chong | #VALUE! | Tham | R-PV | NEM | 11.8 | Astronergy 590Wp | 20 | Huawei SUN2000-10KTL | 0 | Pending NEM Welcome Letter
2501529 | Kuan Kian Yang | #VALUE! | Tham | R-PV | NEM | 10.62 | Astronergy 590Wp | 18 | Huawei SUN2000-8KTL | 0 | Pending NEM Welcome Letter
2502581 | Loh Chee Kuan | #VALUE! | Tham | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2501540 | Mohd Rushdi Bin Haji Abu Bakar | #VALUE! | Patricia | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2502571 | Ting Kam Peng | #VALUE! | Tham | R-PV | NEM | 11.8 | Astronergy 590Wp | 20 | Huawei SUN2000-10KTL | 0 | Pending NEM Welcome Letter
2502568 | Lim See Peng | #VALUE! | Tham | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-6KTL-M1 | 0 | Pending NEM Welcome Letter
2503588 | Lee Xue Cheng | #VALUE! | Tham | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2503590 | Teh Wee Loon | #VALUE! | Tham | R-PV | NEM | 14.16 | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2502570 | Tang Wei Keong | #VALUE! | Tham | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | 0 | Pending NEM Welcome Letter
2502573 | Wong Jun Kit | #VALUE! | Simon | R-PV | NEM | 6.49 | Astronergy 590Wp | 11 | Huawei SUN2000-5KTL-M1 | 0 | Pending NEM Welcome Letter
2503593 | Rashid Bin Darlan | #VALUE! | Patricia | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2501211 | Great Beauty Furniture Sdn Bhd | #VALUE! | Chean Bang | C&I-PV | NEM | 26.55 | Astronergy 590Wp | 45 | Huawei SUN2000-20KTL | 0 | Pending Site Installation
2502589 | Chin Kok Leng | #VALUE! | Patricia | R-PV | NEM | 8.85 | Astronergy 590Wp | 15 | Huawei SUN2000-8KTL | 0 | Pending NEM Welcome Letter
2403090 | Mei Shun Fang Manufacturing Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 476.13 | Astronergy 590Wp | 807 | 0 | 0 | Pending ST License Approval
2503594 | Wong Teck Keng | #VALUE! | Patricia | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2502588 | Khadillah binti Hassan | #VALUE! | Patricia | R-PV | NEM | 8.85 | Astronergy 590Wp | 15 | Huawei SUN2000-8KTL | 0 | Pending NEM Welcome Letter
2503595 | Lim Zhi Jie | #VALUE! | Tham | R-PV | NEM | 14.16 | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2503586 | Safinaz Binti Mohd Sharif | #VALUE! | Patricia | R-PV | NEM | 6.49 | Astronergy 590Wp | 11 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2503604 | Kong Chun Seng | #VALUE! | Tham | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | 0 | Pending NEM Welcome Letter
2503598 | Lew Yuen Tang | #VALUE! | Tham | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | 0 | Pending NEM Welcome Letter
2503609 | Yau Hwee Tien | #VALUE! | Tham | R-PV | NEM | 14.16 | Astronergy 590Wp | 24 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2501524 | Jeremy Koo Wui Ken | #VALUE! | Tham | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | 0 | Pending NEM Welcome Letter
2503617 | Vinny Len Siew Meng | #VALUE! | Patricia | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2503601 | William Song Jian Tat | #VALUE! | Tham | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | 0 | Pending Site Installation
2503619 | Haslina binti Othman | 0 | Patricia | 0 | 0 | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending Site Installation
2503589 | Chong Shiuh Dyi | #VALUE! | Tham | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2504633 | Yong Chee Seng | #VALUE! | Tham | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2504636 | Nur Salinahany binti Hanafiah | #VALUE! | Patricia | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2406152 | Chara Sdn Bhd | #VALUE! | Simon | C&I-PV | NEM | 93.17 | Astronergy 605Wp | 154 | Huawei SN2000-40KTL + Huawei SUN2000-30KTL | 0 | Pending NEM Welcome Letter
2504640 | Ng Mong Ping | #VALUE! | Tham | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | 0 | Pending NEM Welcome Letter
2504638 | Lai Boon Liong | #VALUE! | Tham | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | 0 | Pending NEM Welcome Letter
2504647 | Tan Hock Cheng | #VALUE! | Patricia | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2504658 | Phang Yeong Chin | #VALUE! | Ong | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2503614 | Yap Weoi Kee | 0 | Simon | 0 | 0 | 0 | Astronergy 590Wp | 15 | Solax 8kW | 0 | Pending Site Installation
2504643 | Lee Sui Lian | #VALUE! | Patricia | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2504663 | Too Seng Eng | #VALUE! | Patricia | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-6KTL-M1 | 0 | Pending NEM Welcome Letter
2504671 | Anthony Phua Kin Loong | #VALUE! | Patricia | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | 0 | Pending Site Installation
2505675 | Tee Hup Soon | #VALUE! | Patricia | R-PV | NEM | 15.34 | Astronergy 590Wp | 26 | Huawei SUN2000-12KTL | 0 | Pending Site Installation
2502564 | Muhammad Arif Stephen bin Abddullah | #VALUE! | Simon | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Solinteg MHT-12K-25 hybrid | 0 | Pending NEM Welcome Letter
2504664 | Law Meng Siong | #VALUE! | Patricia | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | 0 | Pending NEM Qouta Approval
2505686 | Lai Kwee Far | #VALUE! | Patricia | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2503603 | Dr Balbinder Singh a/l Gurbaksh Singh | #VALUE! | Tham | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2302004 | Ong Ah Chai | #VALUE! | Chean Bang | R-PV | NEM | 8.85 | Astronergy 590Wp | 15 | Huawei SUN2000-8KTL | 0 | Pending NEM Welcome Letter
2503225 | Weller Air-Cond Parts Enterprise Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 97.6 | Astronergy 610Wp | 160 | Huawei SUN2000-50KTL + SUN2000-20KTL | 0 | Pending NEM Welcome Letter
2403185 | Wan Kong Wing | #VALUE! | Tham | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2410194 | Berjayapak Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 207.08 | Yingli Solar 620Wp | 334 | Huawei SUN2000-50KTL + SUN2000-20KTL | 0 | Pending Site Installation
2504669 | Zohairen Bin Mhamad Sori | #VALUE! | Tham | R-PV | NEM | 10.62 | Astronergy 590Wp | 18 | Huawei SUN2000-8KTL | 0 | Pending NEM Welcome Letter
2504660 | Roshahni Binti Mhammad | #VALUE! | Chean Bang | R-PV | NEM | 14.75 | Astronergy 590Wp | 25 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2410191 | Jowee Trading Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 53.68 | Astronergy 620Wp | 88 | Huawei SUN2000-20KTL x 2 | 0 | Pending NEM Welcome Letter
2505695 | Nur Salwahani Bt Muhammad | #VALUE! | Patricia | R-PV | NEM | 9.44 | Astronergy 590Wp | 16 | Huawei SUN2000-8KTL | 0 | Pending Site Installation
2505672 | Tham Wai Hong | #VALUE! | Patricia | R-PV | NEM | 8.85 | Astronergy 590Wp | 15 | Huawei SUN2000-8KTL | 0 | Pending NEM Welcome Letter
2505684 | Ng Heng Hock | #VALUE! | Patricia | R-PV | NEM | 11.21 | Astronergy 590Wp | 19 | Huawei SUN2000-10KTL | 0 | Pending NEM Welcome Letter
2505697 | Chong Yee Sam | #VALUE! | Patricia | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending Site Installation
2505682 | Lee Soo Kean | #VALUE! | Patricia | R-PV | NEM | 13.42 | Astronergy 610Wp | 22 | Huawei SUN2000-10KTL | 0 | Pending NEM Welcome Letter
2505699 | Kiren Kaur A/P Bhajan Singh | #VALUE! | Chean Bang | R-PV | NEM | 11.8 | Astronergy 590Wp | 20 | Huawei SUN2000-10KTL | 0 | Pending Site Installation
2503612 | Low Bok Tek | #VALUE! | Tham | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | 0 | Pending Site Installation
2505680 | Chiang Hock Chiong | #VALUE! | Patricia | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | 0 | Pending Site Installation
2503607 | Goh Boon Leng | #VALUE! | Tham | R-PV | NEM | 10.62 | Astronergy 590Wp | 18 | Huawei SUN2000-8KTL | 0 | Pending NEM Welcome Letter
2505711 | Lee Len Foong | #VALUE! | Chean Bang | R-PV | NEM | 8.26 | Astronergy 590Wp | 14 | Huawei SUN2000-6KTL | 0 | Pending NEM Qouta Approval
2505713 | Yap Swee Piau | #VALUE! | Patricia | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2505714 | Kong King Wai | #VALUE! | Tham | R-PV | NEM | 7.08 | Astronergy 590Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending Site Installation
2505717 | Sia Wee Leng | #VALUE! | Tham | R-PV | NEM | 16.52 | Astronergy 590Wp | 28 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2505699-1 | Leong Wai Wung | #VALUE! | Tham | R-PV | NEM | 11.8 | Astronergy 590Wp | 20 | Huawei SUN2000-10KTL | 0 | Pending NEM Qouta Submission
2505719 | Lim Jun Hong | #VALUE! | Tham | R-PV | NEM | 11.78 | Astronergy 620Wp | 19 | Huawei SUN2000-10KTL | 0 | Pending NEM Welcome Letter
2505687 | Thayananthan A/L Lokanatan | #VALUE! | Patricia | R-PV | NEM | 10.03 | Astronergy 590Wp | 17 | Huawei SUN2000-8KTL | 0 | Pending NEM Qouta Approval
2505718 | Koh Kheat Kian | #VALUE! | Chean Bang | R-PV | NEM | 7.44 | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-M1 | 0 | Pending NEM Welcome Letter
2506726 | Poh Pun Hong | #VALUE! | Ong | R-PV | NEM | 7.44 | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2506735 | Lee Meng Fui | #VALUE! | Patricia | R-PV | NEM | 7.44 | Astronergy 610Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2506734 | Leow Siew Lian (Tee Hong Yee) | #VALUE! | Patricia | R-PV | NEM | 11.16 | Astronergy 610Wp | 18 | Huawei SUN2000-8KTL | 0 | Pending NEM Welcome Letter
2505708 | Mohd Shariff | #VALUE! | Tham | R-PV | NEM | 7.44 | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Qouta Submission
2506744 | Gan Chin Sam | #VALUE! | Tham | R-PV | NEM | 14.88 | Astronergy 620Wp | 24 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2506727 | Tan Lee Khing | #VALUE! | Patricia | R-PV | NEM | 12.4 | Astronergy 620Wp | 20 | Huawei SUN2000-10KTL | 0 | Pending NEM Welcome Letter
2506752 | Ng Cheng Hoe | #VALUE! | Tham | R-PV | NEM | 7.44 | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2501523 | Chen Kim Hock | #VALUE! | Tham | R-PV | NEM | 17.7 | Astronergy 590Wp | 30 | Huawei SUN2000-12KTL | 0 | Pending Meter Change
2506748 | Teh Foo Hock | #VALUE! | Patricia | R-PV | NEM | 8.68 | Astronergy 620Wp | 14 | Huawei SUN2000-8KTL | 0 | Pending NEM Welcome Letter
2505709 | Tan Heng Lian | #VALUE! | Patricia | R-PV | NEM | 17.98 | Astronergy 620Wp | 29 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2501531 | Mohamad Hafizi Bin Abdul Rahman | #VALUE! | Patricia | R-PV | NEM | 13.64 | Astronergy 620Wp | 22 | Huawei SUN2000-10KTL | 0 | Pending Site Installation
2505259 | Liew Wen Qi | #VALUE! | Patricia | C&I-PV | NEM | 19.52 | Astronergy 610Wp | 32 | Huawei SUN2000-17KTL | 0 | Pending NEM Welcome Letter
2506758 | Goh Boon Meng | #VALUE! | Patricia | R-PV | NEM | 17.98 | Astronergy 620Wp | 29 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2506762 | Megat Mohd Nashrul Bin Ahmad Zulkepli | #VALUE! | Patricia | R-PV | NEM | 12.4 | Astronergy 620Wp | 20 | Huawei SUN2000-10KTL | 0 | Pending NEM Qouta Submission
2506753 | Lim Geok Suan | #VALUE! | Patricia | R-PV | NEM | 11.78 | Astronergy 620Wp | 19 | Huawei SUN2000-10KTL | 0 | Pending NEM Welcome Letter
2506768 | Yap Lee Yan | #VALUE! | Patricia | R-PV | NEM | 11.16 | Astronergy 620Wp | 18 | Huawei SUN2000-10KTL | 0 | Pending NEM Welcome Letter
2506761 | Lee Swee Li | #VALUE! | Patricia | R-PV | NEM | 13.64 | Astronergy 620Wp | 22 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2506779 | Koo Hing Yew | #VALUE! | Patricia | R-PV | NEM | 7.44 | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2506781 | Teng Lily | #VALUE! | Patricia | R-PV | NEM | 7.44 | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2506782 | Tan Shu Huat | #VALUE! | Patricia | R-PV | NEM | 14.88 | Astronergy 620Wp | 24 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2506746 | Tan Wan Ngee | #VALUE! | Patricia | R-PV | NEM | 9.92 | Astronergy 620Wp | 16 | Huawei SUN2000-8KTL | 0 | Pending Site Installation
2506780 | Yeo Khai Boon | #VALUE! | Patricia | R-PV | NEM | 9.92 | Astronergy 620Wp | 16 | Huawei SUN2000-8KTL | 0 | Pending Site Installation
2506778 | Teo Lun Wei | #VALUE! | Patricia | R-PV | NEM | 7.44 | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending Site Installation
2506745 | Lee Ban Hong | #VALUE! | Tham | R-PV | NEM | 14.88 | Astronergy 620Wp | 24 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2506789 | Wu Sio Yunn | #VALUE! | Patricia | R-PV | NEM | 9.92 | Astronergy 620Wp | 16 | Huawei SUN2000-8KTL | 0 | Pending NEM Welcome Letter
2506732 | Chai Shwu Yi (Tan Lewin) | #VALUE! | Simon | R-PV | NEM | 7.44 | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2506759 | Yim Kai Mun | #VALUE! | Patricia | R-PV | NEM | 10.54 | Astronergy 620Wp | 17 | Huawei SUN2000-8KTL | 0 | Pending NEM Welcome Letter
2506794 | Ahmad Fadhil Bin Alias | #VALUE! | Patricia | R-PV | NEM | 9.92 | Astronergy 620Wp | 16 | Huawei SUN2000-8KTL | 0 | Pending NEM Welcome Letter
2506798 | Lew Sieow Shih | #VALUE! | Patricia | R-PV | NEM | 7.44 | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending Site Installation
2506773 | Leiw Chew Choi | #VALUE! | Patricia | R-PV | NEM | 14.88 | Astronergy 620Wp | 24 | Huawei SUN2000-12KTL | 0 | Pending Site Installation
2506789-1 | Lim Kim Kiew | #VALUE! | Chean Bang | R-PV | NEM | 7.44 | Astronergy 620Wp | 12 | Huawei SUN2000-5KTL-L1 | 0 | Pending NEM Welcome Letter
2506786 | Lim Chee Seng | #VALUE! | Tham | R-PV | NEM | 13.64 | Astronergy 620Wp | 22 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2505260 | Canning Garden Baptist Church | #VALUE! | Patricia | C&I-PV | NEM | 48.36 | Astronergy 620Wp | 78 | Huawei SUN2000-36KTL | 0 | Pending Meter Change
2506799 | Lee Cheow Ban | #VALUE! | Patricia | R-PV | NEM | 13.64 | Astronergy 620Wp | 22 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2506276 | Tew Ah Sing @ Teo Ah Sing | #VALUE! | Chean Bang | R-PV | NEM | 19.84 | Astronergy 620Wp | 32 | Huawei SUN2000-17KTL | 0 | Pending NEM Welcome Letter
2506785 | Mohd Nurazuwan Bin Radzi | #VALUE! | Patricia | R-PV | NEM | 13.64 | Astronergy 620Wp | 22 | Huawei SUN2000-12KTL | 0 | Pending NEM Qouta Approval
2506801 | Lim Joo Eng | #VALUE! | Patricia | R-PV | NEM | 17.98 | Astronergy 620Wp | 29 | Huawei SUN2000-12KTL | 0 | Pending Site Installation
2503223 | Insultec Duragate Sdn Bhd | #VALUE! | Tham | C&I-PV | NEM | 58.9 | Yingli Solar 620Wp | 95 | Huawei SUN2000-50KTL | 0 | Pending Site Installation
2506802 | Hung Wen Hao | #VALUE! | Patricia | R-PV | NEM | 13.64 | Astronergy 620Wp | 22 | Huawei SUN2000-12KTL | 0 | Pending NEM Qouta Approval
2412510 | How Toon Huah | #VALUE! | Chean Bang | R-PV | NEM | 14.88 | Astronergy 620Wp | 24 | Huawei SUN2000-12KTL | 0 | Pending NEM Welcome Letter
2504051 | G. Semanggol R&R (Northbound) - Green EV Charge Sdn Bhd | #VALUE! | Simon | EV Charger | 0 | 0 | 0 | 0 | 0 | 0 | Pending ST License Application
2505056 | TMG Mall Tanjung Lumpur (Handal Green Mobility) | #VALUE! | Chean Bang | EV Charger | 0 | 0 | 0 | 0 | 0 | 0 | Pending ST License Application
2507833 | Yee Main Way | #VALUE! | Patricia | R-PV | SELCO | 12.4 | Astronergy 620Wp | 20 | Solax 10kW | 0 | Pending Site Installation
2409030 | TMG Mall Bandar Indera Mahkota (Handal Green Mobility) | #VALUE! | Chean Bang | EV Charger | 0 | 0 | 0 | 0 | 0 | 0 | Pending Site Installation
2507059 | TMG Mall IM16 (Handal Green Mobility) | #VALUE! | Chean Bang | EV Charger | 0 | 0 | 0 | 0 | 0 | 0 | Pending Site Installation
2507060 | TMG Mall Temerloh (Handal Green Mobility) | #VALUE! | Chean Bang | EV Charger | 0 | 0 | 0 | 0 | 0 | 0 | Pending Site Installation
2507062 | Tapah R&R (Southbound) - Green EV Charge Sdn Bhd | #VALUE! | Simon | EV Charger | 0 | 0 | 0 | 0 | 0 | 0 | Pending Site Installation
2509863 | Goh Soon Teck | #VALUE! | Patricia | R-PV | SELCO | 9.92 | Astronergy 620Wp | 16 | Solax 7.5kW | 0 | Pending Site Installation
2507840 | Chew Kok leong | #VALUE! | Patricia | R-PV | SELCO | 15.5 | Astronergy 620Wp | 25 | Solax 12kW | 0 | Pending Site Installation
2508857 | Chong Horng Tat | #VALUE! | Ong | R-PV | SELCO | 8.68 | Astronergy 620Wp | 14 | Solax 8kW | 0 | Pending Site Installation
2305008 | Yeap Chooi Hock | #VALUE! | Patricia | C&I-PV | SELCO | 17.98 | Astronergy 620Wp | 29 | Solax 15kW | 0 | Pending Site Installation
2508856 | Eddie Leong Kai Sheng | #VALUE! | Ong | R-PV | SELCO | 18.6 | Astronergy 620Wp | 30 | Fox ESS 12kW | 0 | Pending Site Installation
2510877 | Wang Pay Chen | #VALUE! | Patricia | R-PV | SELCO | 9.92 | Astronergy 620Wp | 16 | Solax 8kW | 0 | Pending Site Installation
2511887 | Lee Hang Meng | #VALUE! | Patricia | R-PV | SELCO | 12.4 | Astronergy 620Wp | 19 | Fox ESS 10kW | 0 | Pending Site Installation
2305019 | Soe Yew Seng | #VALUE! | Simon | R-PV | SELCO | 15.5 | Astronergy 620Wp | 25 | Fox ESS 12kW | 0 | Pending Site Installation

## Finance Tracker
[11 empty] | 1st Payment |  |  |  | 2nd Payment |  |  |  | 3rd Payment |  |  |  | 4th Payment |  |  |  | 5th Payment |  |  |  | VO Payment
Project No | Client Name | Project Value | VO | Sales PIC | Category | Payment Type | Invoice Status | Payment Status | Total Invoiced | Total Paid | 1st Invoice Date | Invoiced Amount | 1st Payment Date | 1st Payment | 2nd Invoice Date | Invoice Amount | 2nd Payment Date | Payment Received | 3rd Invoice Date | Invoice Amount | 3rd Payment Date | Payment Received | 4th Invoice Date | Invoice Amount | 4th Payment Date | Payment Received | 5th Invoice Date | Invoice Amount | 5th Payment Date | Payment Received | VO Invoiced Date | VO Invoice Amount | VO Payment Date | VO Payment
2303005 | Wong Kim Mei | 32000 | 0 | Simon | R-PV | Self finance | Invoice Completed | Payment Completed | 32000 | 32000 | 2023-07-10 | 500 | 2023-07-10 | 500 | 2023-07-06 | 25600 | 2023-07-11 | 25600 | 2023-09-26 | 5900 | 2023-09-28 | 5900
2303006 | Ang Ching Ming | 40000 | 0 | Simon | R-PV | Self finance | Pending 1st Invoice | Pending 1st Payment | 0 | 0
2304016 | Tan Sei Choon | 31000 | 0 | Chean Bang | R-PV | Self finance | Invoice Completed | Payment Completed | 31000 | 31000 | 2023-05-29 | 500 | 2023-05-29 | 500 | 2023-08-11 | 27000 | 2023-08-14 | 27000 | 2023-09-06 | 3500 | 2023-09-07 | 3500
2305021 | Ho Hon Kit | 20000 | 0 | Simon | R-PV | Self finance | Pending 1st Invoice | Pending 1st Payment | 0 | 0
2305026 | Stanley Ang Leng Chuan | 40000 | 0 | Simon | R-PV | Self finance | Invoice Completed | Payment Completed | 40000 | 40000 | 2023-06-26 | 500 | 2023-06-26 | 500 | 2023-08-14 | 34500 | 2023-08-16 | 34500 | 2023-11-14 | 5000 | 2023-11-23 | 5000
2306033 | Foo Tuang Lee | 16000 | 0 | Chean Bang | R-PV | Self finance | Invoice Completed | Payment Completed | 16000 | 16000 | 2023-06-06 | 500 | 2023-06-06 | 500 | 2023-07-06 | 13000 | 2023-07-11 | 13000 | 2023-07-06 | 2500 | 2023-09-21 | 2500
2306037 | Tan Hong Guan | 36575 | 0 | Simon | R-PV | Self finance | Invoice Completed | Payment Completed | 36575 | 36575 | 2023-09-26 | 18287.5 | 2023-09-26 | 18287.5 | 2023-11-14 | 18287.5 | 2023-12-15 | 18287.5
2307040 | Law Soo Chin | 40000 | 0 | Chean Bang | R-PV | Self finance | Invoice Completed | Payment Completed | 40000 | 40000 | 2023-07-11 | 500 | 2023-07-11 | 500 | 2023-09-06 | 34500 | 2023-09-09 | 34500 | 2023-11-14 | 5000 | 2023-11-16 | 5000
2305011 | Kossan FRP Marketing (M) Sdn Bhd | 242000 | 0 | Simon | C&I-PV | Cash | 2nd invoice | 2nd payment | 217800 | 217800 | 2023-11-14 | 108900 | 2023-12-15 | 108900 | 2024-04-26 | 108900 | 2024-04-26 | 108900
2304007 | MTJ Development Sdn Bhd (Intercontinental KL) | 188800 | 0 | Simon | C&I-PV | Cash | 4th invoice | 3rd payment | 182540 | 169920 | 2023-07-13 | 18880 | 2023-07-17 | 18880 | 2023-07-13 | 66080 | 2023-07-17 | 66080 | 2023-11-14 | 84960 | 2023-12-20 | 84960 | 2024-07-25 | 12620
2307042 | Dato' Sri Ng Chong Keong | 50000 | 0 | Chean Bang | R-PV | Self finance | Invoice Completed | Payment Completed | 50000 | 50000 | 2023-09-07 | 2500 | 2023-09-07 | 2500 | 2023-10-26 | 15000 | 2023-10-27 | 15000 | 2023-11-02 | 27500 | 2023-11-03 | 27500 | 2024-03-11 | 5000 | 2024-03-12 | 5000
2308058 | Cheong Yik Yin | 30000 | 0 | Simon | R-PV | Self finance | Pending 1st Invoice | Pending 1st Payment | 0 | 0
2308062 | Lim Chin Joo | 42300 | 0 | Simon | R-PV | Self finance | Pending 1st Invoice | Pending 1st Payment | 0 | 0
2309068 | Kee Siew Chuan (Ngo Woon Wah) | 28500 | 0 | Chean Bang | R-PV | Self finance | 1st invoice | 1st payment | 500 | 500 | 2023-10-20 | 500 | 2023-10-20 | 500
2310078 | Lee Nyok Cheng | 52000 | 0 | Chean Bang | R-PV | Self finance | Invoice Completed | Payment Completed | 52000 | 52000 | 2023-10-09 | 1000 | 2023-10-09 | 1000 | 2023-10-23 | 45000 | 2023-10-23 | 45000 | 2023-11-17 | 6000 | 2023-11-17 | 6000
2310083 | Ong Eng Guan | 31000 | 0 | Chean Bang | R-PV | Self finance | 2nd invoice | 2nd payment | 26000 | 26000 | 2023-10-23 | 500 | 2023-10-23 | 500 | 2024-01-15 | 25500 | 2024-01-16 | 25500
2310084 | Chia Le Chin | 34000 | 0 | Chean Bang | R-PV | Cash + instalment | Invoice Completed | Payment Completed | 34000 | 34000 | 2023-10-22 | 500 | 2023-10-22 | 500 | 2024-01-19 | 33500 | 2024-01-24 | 33500
2305024 | Beh Poh Loh | 42500 | 6000 | Chean Bang | R-PV | Self finance | Pending 1st Invoice | Pending 1st Payment | 0 | 0
2307052 | Ngoh Win Nee | 22100 | 0 | Chean Bang | R-PV | Credit Card Instalment | 1st invoice | 1st payment | 500 | 500 | 2023-08-18 | 500 | 2023-08-18 | 500
2304010 | Tung Seng Chang | 20650 | 0 | Simon | R-PV | Cash | 1st invoice | 1st payment | 2065 | 2065 | 2023-07-06 | 2065 | 2023-07-13 | 2065
2308065 | Pua Hock Meng | 33000 | 2500 | Chean Bang | R-PV | Self finance | 4th invoice | 4th payment | 38000 | 38000 | 2023-07-09 | 500 | 2023-07-09 | 500 | 2023-11-02 | 33000 | 2024-09-04 | 33000 | 2023-11-02 | 2000 | 2023-11-02 | 2000 | 2023-11-02 | 2500 | 2024-04-09 | 2500
2306009 | Dato Arif Stephen bin Abdullah | 720000 | 0 | Simon | R-BESS | Cash | Invoice Completed | Payment Completed | 720000 | 720000 | 2023-09-25 | 432000 | 2023-09-26 | 432000 | 2024-01-03 | 108000 | 2024-01-04 | 108000 | 2024-03-11 | 180000 | 2024-03-19 | 180000
2303003 | Greenlast Housing Development Sdn Bhd | 80000 | 0 | Chean Bang | C&I-PV | Self finance | Invoice Completed | Payment Completed | 80000 | 80000 | 2024-01-18 | 8000 | 2024-02-21 | 8000 | 2024-04-28 | 28000 | 2024-04-29 | 28000 | 2024-07-12 | 44000 | 2024-07-20 | 44000
2311040 | DBTS Industries Sdn Bhd | 91000 | 0 | SImon | C&I-PV | Cash | 1st invoice | 1st payment | 81900 | 81900 | 2024-04-02 | 81900 | 2024-04-26 | 81900
2308007 | EV Connection Sdn Bhd (The Pines Melaka) | 93380 | 0 | Simon | EV Charger | Cash | Invoice Completed | Payment Completed | 93380 | 93380 | 2023-11-15 | 46690 | 2023-11-20 | 46690 | 2024-10-29 | 46690 | 2024-12-24 | 46690
2311094 | Ching Kok Keong | 37000 | 0 | Chean Bang | R-PV | Self finance | Invoice Completed | Payment Completed | 37000 | 37000 | 2023-11-30 | 500 | 2023-11-30 | 500 | 2024-06-29 | 36500 | 2024-06-30 | 36500
2311095 | Chu Yin Siong | 44600 | 0 | Chean Bang | R-PV | Self finance | Invoice Completed | Payment Completed | 44600 | 44600 | 2023-12-25 | 500 | 2023-12-25 | 500 | 2023-05-16 | 42100 | 2024-05-20 | 42100 | 2024-06-07 | 2000 | 2025-05-29 | 2000
2311039 | DC Handal EV Charging Hub | 280080 | 46945 | Simon | C&I-PV | Self finance | Invoice Completed | Payment Completed | 327025 | 327025 | 2024-01-03 | 126036 | 2024-01-19 | 126036 | 2024-10-29 | 126036 | 2024-12-24 | 126036 | 2024-12-02 | 28008 | 2024-12-24 | 28008 | [8 empty] | 2024-10-29 | 46945 | 2024-12-24 | 46945
2311012 | EV Connection Sdn Bhd (IOI Citymall, Putrajaya) | 109000 | 0 | Simon | EV Charger | Cash | Invoice Completed | Payment Completed | 109000 | 109000 | 2024-01-11 | 54500 | 2024-01-11 | 54500 | 2024-10-29 | 54500 | 2024-12-24 | 54500
2311089 | Susan Lau Shiew Hung | 37500 | 0 | Simon | R-PV | Self finance | Invoice Completed | 2nd payment | 37500 | 35500 | 2023-11-30 | 500 | 2023-11-30 | 500 | 2024-06-05 | 35000 | 2024-06-05 | 35000 | 2025-04-02 | 2000
2312118 | Dr Suntheresan A/L Ganapathy | 54930 | 0 | Ong | R-PV | Self finance | Invoice Completed | Payment Completed | 54930 | 54930 | 2024-01-05 | 1000 | 2024-01-05 | 1000 | 2024-04-01 | 51930 | 2024-02-04 | 51930 | 2024-05-24 | 2000 | 2024-05-24 | 2000
2309070 | Saiful Lizan Bin Ibrahim | 48902 | 0 | Simon | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 48902 | 48902 | 2024-01-12 | 500 | 2024-01-12 | 500 | 2024-06-09 | 48402 | 2024-06-09 | 48402
2310075 | Chong Fong Chin(Jessie) | 45600 | 0 | Chean Bang | R-PV | Self finance | Pending 1st Invoice | Pending 1st Payment | 0 | 0
2310076 | Loo Thiam Seng | 24000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 24000 | 24000 | 2024-04-04 | 500 | 2024-04-04 | 500 | 2025-05-28 | 23500 | 2025-05-28 | 23500
2310085 | Chew Mei May | 47786 | 0 | Simon | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 47786 | 47786 | 2023-11-29 | 500 | 2023-11-29 | 500 | 2024-04-21 | 47286 | 2024-04-24 | 47286
2312113 | Razman Bin Samsudin | 44000 | 0 | Simon | R-PV | Self finance | 2nd invoice | 2nd payment | 42000 | 17000 | 2024-01-23 | 500 | 2024-01-23 | 500 | 2025-02-18 | 41500 | 2025-03-10 | 16500
2401121 | Chen Ah Hin | 40000 | 0 | Tham | R-PV | Self finance | Invoice Completed | 3rd payment | 40000 | 39800 | 2024-04-01 | 500 | 2024-04-01 | 500 | 2024-05-15 | 37500 | 2024-05-15 | 37500 | 2024-05-15 | 2000 | 5/15/2024 | 1800
2401124 | Lim Kok Teong | 53708 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 53708 | 53708 | 2024-04-02 | 500 | 2024-04-02 | 500 | 2024-05-16 | 53208 | 2024-05-16 | 53208
2401131 | Chan Po Kok (JC Chan KEB) | 29500 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 29500 | 29500 | 2024-04-12 | 500 | 2024-04-12 | 500 | 2024-06-04 | 29000 | 2024-06-04 | 29000
2401137 | Lim Kok Liang | 40900 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 40900 | 40900 | 2024-03-27 | 500 | 2024-03-27 | 500 | 2024-05-19 | 40400 | 2024-05-19 | 40400
2401147 | Susan Sung Fong Thieng | 40440 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 40440 | 40440 | 2024-04-01 | 500 | 2024-04-01 | 500 | 2024-05-28 | 39940 | 2024-05-28 | 39940
2403165 | Lee Boon Huet | 24600 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 24600 | 24600 | 2024-04-01 | 500 | 2024-04-01 | 500 | 2024-05-28 | 24100 | 2024-05-28 | 24100
2403167 | Ng Yunn Chong | 47500 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 47500 | 47500 | 2024-03-24 | 500 | 2024-03-24 | 500 | 2024-04-29 | 45000 | 2024-04-29 | 45000 | 2024-07-05 | 2000 | 2024-07-05 | 2000
2403170 | Wong Hoon Sang | 35600 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 35600 | 35600 | 2024-03-15 | 500 | 2024-03-15 | 500 | 2024-04-26 | 33100 | 2024-04-26 | 33100 | 2024-08-01 | 2000 | 2024-08-01 | 2000
2403177 | Nor Aini binti Mohd Ashari | 20000 | 0 | Tham | R-PV | Self finance | Invoice Completed | 2nd payment | 20000 | 16000 | 2024-03-25 | 500 | 2024-03-25 | 500 | 2024-12-13 | 19500 | 2025-04-04 | 15500
2403189 | Lai Kim Soon (Stella) | 27500 | 0 | Chean Bang | R-PV | Self finance | Invoice Completed | Payment Completed | 27500 | 27500 | 2024-03-29 | 500 | 2024-03-29 | 500 | 2024-06-07 | 25000 | 2024-06-07 | 25000 | 2024-07-02 | 2000 | 2024-07-02 | 2000
2403190 | Tan Poh Poh | 21000 | 0 | Chean Bang | R-PV | Self finance | Invoice Completed | Payment Completed | 21000 | 21000 | 2024-03-29 | 500 | 2024-03-29 | 500 | 2024-06-20 | 20500 | 2024-06-20 | 20500
2403197 | Leau Koo Sien (Eric) | 48600 | 0 | Chean Bang | R-PV | Self finance | 1st invoice | 1st payment | 500 | 500 | 2024-03-29 | 500 | 2024-03-29 | 500
2403197-1 | Koon Kok Leong | 27237.2 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 27237.2 | 27237.2 | 2024-04-01 | 500 | 2024-04-01 | 500 | 2024-05-11 | 26737.2 | 2024-05-15 | 26737.2
2404206 | Wong Wai Kwong | 31000 | 0 | Chean Bang | R-PV | Cash + instalment | Invoice Completed | Payment Completed | 31000 | 31000 | 2024-04-04 | 500 | 2024-04-04 | 500 | 2024-05-08 | 30500 | 2024-05-13 | 30500
2404226 | Jimmy Kok Aik Lim | 25100 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 25100 | 25100 | 2024-04-14 | 500 | 2024-04-14 | 500 | 2024-07-12 | 24600 | 2024-07-14 | 24600
2401063 | Weller Air-Cond Parts Enterprise Sdn Bhd | 82000 | 0 | Tham | C&I-PV | Self finance | Invoice Completed | Payment Completed | 82000 | 82000 | 2024-04-15 | 8200 | 2024-04-15 | 8200 | 2024-07-04 | 28700 | 2024-07-10 | 28700 | 2024-09-02 | 36900 | 2024-10-21 | 36900 | 2024-10-21 | 8200 | 2025-04-17 | 8200
2401069 | Enviri Industries Sdn Bhd | 668000 | 2610 | Tham | C&I-PV | Self finance | Invoice Completed | Payment Completed | 670610 | 670610 | 2024-04-08 | 66800 | 2024-04-08 | 66800 | 2024-07-17 | 233800 | 2024-07-24 | 233800 | 2024-09-02 | 300600 | 2024-12-31 | 300600 | 2025-01-24 | 66800 | 2025-02-03 | 66800 |  |  |  |  | 2024-10-03 | 2610 | 2024-10-09 | 2610
2402079 | Intergreen Holdings Sdn Bhd | 194600 | 0 | Tham | C&I-PV | Self finance | Invoice Completed | Payment Completed | 194600 | 194600 | 2024-04-22 | 19460 | 2024-04-22 | 19460 | 2024-09-02 | 68110 | 2024-09-10 | 68110 | 2024-09-02 | 48650 | 2024-09-10 | 48650 | 2024-12-05 | 38920 | 2024-12-13 | 38920 | 2024-12-26 | 19460 | 2024-12-30 | 19460
2402080 | CK Fresh Sdn Bhd | 120000 | 1500 | Tham | C&I-PV | Self finance | Invoice Completed | Payment Completed | 122500 | 121500 | 2024-04-17 | 12000 | 2024-04-17 | 12000 | 2024-07-04 | 42000 | 2024-07-23 | 42000 | 2024-09-02 | 66000 | 2025-07-09 | 65000 | [8 empty] | 2024-10-08 | 2500 | 2024-10-08 | 2500
2312120 | Ling Duon Kwan | 27500 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 27500 | 27500 | 2024-04-09 | 500 | 2024-04-09 | 500 | 2024-05-09 | 25000 | 2024-05-09 | 25000 | 2025-05-30 | 2000 | 2025-05-30 | 2000
2311092 | Tham Chee Man | 22000 | 0 | Tham | R-PV | Self finance | 1st invoice | 1st payment | 500 | 500 | 2023-11-27 | 500 | 2023-11-27 | 500
2404230 | Yap Bee Im Marianne | 32500 | -2000 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 30500 | 30500 | 2024-04-20 | 500 | 2024-04-20 | 500 | 2024-06-27 | 30000 | 2024-06-28 | 30000
2401133 | Cheong Sau Ling | 34460 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 34460 | 34460 | 2024-04-22 | 500 | 2024-04-22 | 500 | 2024-11-21 | 33960 | 2024-11-21 | 33960
2403171 | Sim Keng Chor | 52400 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 52400 | 52400 | 2024-04-22 | 500 | 2024-04-22 | 500 | 2024-07-23 | 51900 | 2024-07-23 | 51900
2403176 | Nor Hana binti Supiran @ Soviran | 30500 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 30500 | 30500 | 2024-04-24 | 500 | 2024-04-24 | 500 | 2024-08-20 | 28000 | 2024-09-26 | 28000 | 2024-09-26 | 2000 | 2024-09-26 | 2000
2404229 | Ng Lay Ping | 41600 | -1600 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 40000 | 40000 | 2024-04-25 | 500 | 2024-04-25 | 500 | 2024-06-06 | 39500 | 2024-06-07 | 39500
2404211 | Nor Fadillah | 49600 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 49600 | 49600 | 2024-04-26 | 500 | 2024-04-26 | 500 | 2024-06-10 | 47100 | 2024-10-06 | 47100 | 2024-09-18 | 2000 | 2024-09-18 | 2000
2404111 | Budi Jelas Sdn Bhd | 81000 | 0 | Tham | C&I-PV | Self finance | Invoice Completed | Payment Completed | 81000 | 81000 | 2024-05-16 | 8100 | 2024-05-16 | 8100 | 2024-09-02 | 28350 | 2024-12-06 | 28350 | 2025-05-06 | 44550 | 2025-05-06 | 44550
2404219 | Billy Teoh Wee Wei | 52000 | 0 | Tham | R-PV | Cash + instalment | Invoice Completed | Payment Completed | 52000 | 52000 | 2024-04-29 | 500 | 2024-04-29 | 500 | 2024-08-19 | 51500 | 2024-08-31 | 51500
2404214 | Teo En Chie | 48200 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 48200 | 48200 | 2024-05-02 | 500 | 2024-05-02 | 500 | 2024-07-03 | 47700 | 2024-09-07 | 47700
2403102 | Sleep Matics (Asia) Sdn Bhd | 744800 | 0 | Tham | C&I-PV | Self finance | 3rd invoice | 1st payment | 786320 | 74480 | 2024-05-19 | 74480 | 2024-06-19 | 74480 | 2025-09-12 | 260680 |  |  | 2025-11-03 | 335160 | [10 empty] | 2025-09-12 | 116000
2312059 | CHL Foam Industries Sdn Bhd | 690300 | 130000 | Tham | C&I-PV | Self finance | Invoice Completed | Payment Completed | 820300 | 820300 | 2024-06-10 | 69030 | 2024-06-10 | 69030 | 2024-11-14 | 241605 | 2024-11-20 | 241605 | 2025-04-29 | 310635 | 2025-04-29 | 310635 | 2025-09-24 | 69030 | 2025-09-25 | 69030 |  |  |  |  | 2024-11-15 | 130000 | 2024-11-20 | 130000
2404255 | Ong Pui Fen | 30260 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 30260 | 30260 | 2024-05-14 | 500 | 2024-05-14 | 500 | 2024-08-27 | 29760 | 2024-08-27 | 29760
2404242 | Chua Boon Seng | 35000 | 0 | Azra | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 35000 | 35000 | 2024-05-23 | 500 | 2024-05-23 | 500 | 2024-09-03 | 34500 | 2024-08-19 | 34500
2405272 | Chan Hui Li | 32180 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 32180 | 32180 | 2024-05-15 | 500 | 2024-05-15 | 500 | 2024-08-27 | 31680 | 2024-08-27 | 31680
2405266 | Goh Wee Bang (Goh Swee Teng) | 41000 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 41000 | 41000 | 2024-05-16 | 500 | 2024-05-16 | 500 | 2024-07-12 | 38500 | 2024-07-12 | 38500 | 2024-09-03 | 2000 | 2024-09-03 | 2000
2405280 | Teoh Kah Ming | 34600 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 34600 | 34600 | 2024-05-10 | 500 | 2024-05-10 | 500 | 2024-08-22 | 34100 | 2024-08-22 | 34100
2405294 | Gan Wei Kuan | 25100 | 0 | Tham | 0 | Self finance | Pending 1st Invoice | Pending 1st Payment | 0 | 0
2405296 | Haiu Chan Lai | 32000 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 32000 | 32000 | 2024-05-28 | 500 | 2024-05-28 | 500 | 2024-11-23 | 31500 | 2024-11-23 | 31500
2405307 | Shreeram Nadarajah | 28000 | 4600 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 32600 | 32600 | 2024-10-03 | 500 | 2024-10-03 | 500 | 2024-10-03 | 27500 | 2024-10-03 | 27500 | 2024-10-03 | 4600 | 2024-10-03 | 4600
2404227 | Datin Tai Bee Choon | 52400 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 52400 | 52400 | 2024-05-30 | 500 | 2024-05-30 | 500 | 2024-11-26 | 51900 | 2024-11-26 | 51900
2405315 | Yeap Say Woei | 40000 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 40000 | 40000 | 2024-06-03 | 500 | 2024-06-03 | 500 | 2024-08-11 | 37500 | 2024-08-12 | 37500 | 2024-11-22 | 2000 | 2024-11-29 | 2000
2405319 | Tan Zhi Cheng | 26240 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 26240 | 26240 | 2024-06-05 | 500 | 2024-06-05 | 500 | 2024-08-19 | 25740 | 2024-08-19 | 25740
2405288 | Teh Siew Eng | 41840 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 41840 | 41840 | 2024-05-28 | 500 | 2024-05-28 | 500 | 2024-08-23 | 39340 | 2024-08-23 | 39340 | 2024-11-22 | 2000 | 2024-11-22 | 2000
2404256 | Lai Chun Wai | 33100 | 0 | Azra | R-PV | Self finance | Invoice Completed | Payment Completed | 33100 | 33100 | 2024-06-21 | 500 | 2024-06-21 | 500 | 2024-09-20 | 30600 | 2024-09-20 | 30600 | 2024-10-18 | 2000 | 2024-10-18 | 2000
2406323 | Tay Poh Chai | 40000 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 40000 | 40000 | 2024-06-14 | 500 | 2024-06-14 | 500 | 2024-08-14 | 37500 | 2024-08-14 | 37500 | 2024-11-22 | 2000 | 2024-11-30 | 2000
2406336 | Alex How Chee Keong | 31000 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 31000 | 31000 | 2024-06-19 | 500 | 2024-06-19 | 500 | 2024-08-20 | 30500 | 2024-08-20 | 30500
2406340 | How Mei Cheng | 24100 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 24100 | 24100 | 2024-06-22 | 500 | 2024-06-22 | 500 | 2024-08-24 | 23600 | 2024-08-24 | 23600
2406355 | Windy Ng | 27000 | -1872 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 25128 | 25128 | 2024-10-17 | 500 | 2024-10-17 | 500 | 2024-10-16 | 24500 | 2024-10-22 | 24500 | 2024-10-17 | 128 | 2024-11-03 | 128
2406357 | Zainuddin Zin | 38000 | 0 | Patricia | R-PV | Self finance | Invoice Completed | Payment Completed | 38000 | 38000 | 2024-06-28 | 500 | 2024-06-28 | 500 | 2024-08-30 | 35500 | 2024-08-30 | 35500 | 2024-12-14 | 2000 | 2024-12-14 | 2000
2405019 | Handal Green Mobility Sdn Bhd (Encore Melaka) | 90800 | 0 | Simon | EV Charger | Cash | Invoice Completed | Payment Completed | 90800 | 90800 | 2024-07-05 | 45400 | 2024-07-09 | 45400 | 2024-08-13 | 45400 | 2024-09-09 | 45400
2406358 | Kwan Li Shan | 30000 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 30000 | 30000 | 2024-06-28 | 500 | 2024-06-28 | 500 | 2024-09-13 | 27500 | 2024-09-14 | 27500 | 2024-11-22 | 2000 | 2024-11-28 | 2000
2407360 | Liau Hui Kiem | 45020 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 45020 | 45020 | 2024-09-26 | 500 | 2024-09-26 | 500 | 2024-09-26 | 44520 | 2024-09-26 | 44520
2407364 | Mohd Nasir Man | 25000 | 0 | Patricia | R-PV | Self finance | Invoice Completed | Payment Completed | 25000 | 25000 | 2024-09-07 | 500 | 2024-09-07 | 500 | 2024-08-30 | 22500 | 2024-09-12 | 22500 | 2024-12-13 | 2000 | 2025-04-22 | 2000
2407375 | Tan Ger Ber | 39980 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 39980 | 39980 | 2024-07-12 | 500 | 2024-07-12 | 500 | 2024-09-12 | 39480 | 2024-09-12 | 39480
2407379 | Ng Boon Kiat (Daniel) | 22860 | 0 | Chean Bang | R-PV | Cash + Credit Card Instalment | Invoice Completed | Payment Completed | 22860 | 22860 | 2024-07-11 | 500 | 2024-07-11 | 500 | 2024-10-24 | 22360 | 2024-10-24 | 22360
2407380 | How Yee Seun | 38000 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 38000 | 38000 | 2024-07-13 | 500 | 2024-07-13 | 500 | 2024-08-26 | 37500 | 2024-08-26 | 37500
2407381 | Lau Ah Leng | 36680 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 36680 | 36680 | 2024-07-13 | 500 | 2024-07-13 | 500 | 2024-10-23 | 36180 | 2024-10-23 | 36180
2407382 | Leong Tack Ming | 29840 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 29840 | 29840 | 2024-07-15 | 500 | 2024-07-15 | 500 | 2025-03-22 | 29340 | 2025-03-22 | 29340
2407383 | Charles Lew Chow Leng | 39980 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 39980 | 39980 | 2024-07-15 | 500 | 2024-07-15 | 500 | 2024-09-13 | 39480 | 2024-09-13 | 39480
2407384 | Loh Fook Khew | 36800 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 36800 | 36800 | 2024-09-26 | 500 | 2024-09-26 | 500 | 2024-09-26 | 36300 | 2024-09-26 | 36300
2407385 | Cheong Chin Meng | 45600 | 0 | Chean Bang | R-PV | Self finance | Invoice Completed | Payment Completed | 45600 | 45600 | 2024-07-15 | 500 | 2024-07-15 | 500 | 2024-09-13 | 43100 | 2024-09-13 | 43100 | 2024-12-13 | 2000 | 2025-01-27 | 2000
2310035 | Advantic Nutraceuticals | 188000 | 0 | Tham | C&I-PV | Self finance | Invoice Completed | 3rd payment | 188000 | 103400 | 2025-05-16 | 84600 | 2025-05-19 | 84600 | 2025-06-30 | 84600 |  |  | 2025-10-16 | 18800 | 2025-10-24 | 18800
2403088 | Chua Tong Hin Hardware Sdn Bhd | 98000 | 0 | Tham | C&I-PV | Self finance | Invoice Completed | Payment Completed | 98000 | 98000 | 2024-11-06 | 9800 | 2024-11-06 | 9800 | 2024-12-05 | 34300 | 2024-12-18 | 34300 | 2025-01-24 | 44100 | 2025-05-27 | 44100 | 2025-04-29 | 9800 | 2025-05-27 | 9800
2407157 | NMSY Capital Sdn Bhd (Mohd Nasir) | 52000 | 0 | Patricia | C&I-PV | Self finance | Invoice Completed | Payment Completed | 52000 | 52000 | 2024-07-09 | 500 | 2024-07-09 | 500 | 2024-09-03 | 49500 | 2024-11-26 | 49500 | 2024-12-13 | 2000 | 2025-10-28 | 2000
2312116 | Chua Ling Ling | 32540 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 32540 | 32540 | 2024-06-30 | 500 | 2024-06-30 | 500 | 2024-10-23 | 32040 | 2024-10-23 | 32040
2407388 | Yeo Chen Kok | 34600 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 34600 | 34600 | 2024-09-20 | 500 | 2024-09-20 | 500 | 2024-09-20 | 32100 | 2024-09-20 | 32100 | 2024-12-26 | 2000 | 2024-12-26 | 2000
2407386 | Amirluddin bin Awang | 38000 | 0 | Chean Bang | R-PV | Self finance | Invoice Completed | Payment Completed | 38000 | 38000 | 2024-07-21 | 500 | 2024-07-21 | 500 | 2024-09-24 | 35500 | 2024-09-25 | 35500 | 2024-10-14 | 2000 | 2024-10-14 | 2000
2403158 | Ong Gin Chin | 23500 | -1404 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 22096 | 22096 | 2024-10-21 | 500 | 2024-10-21 | 500 | 2024-10-21 | 21000 | 2024-10-22 | 21000 | 2024-11-06 | 596 | 2024-11-19 | 596
2404220 | Ng Seow Fong | 23500 | -1404 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 22096 | 22096 | 2024-10-16 | 500 | 2024-10-16 | 500 | 2024-10-16 | 21000 | 2024-10-16 | 21000 | 2024-11-06 | 596 | 2024-11-13 | 596
2403202 | Chuah Teah Soo | 31000 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 31000 | 31000 | 2024-09-27 | 500 | 2024-09-27 | 500 | 2024-09-27 | 28500 | 2024-09-27 | 28500 | 2024-09-27 | 2000 | 2024-10-04 | 2000
2407392 | Ecila Sim Ju-Inn | 36680 | -2340 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 34340 | 34340 | 2024-10-17 | 500 | 2024-10-17 | 500 | 2024-10-17 | 33840 | 2024-10-24 | 33840
2404232 | Wong Yoke Chon | 25000 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 25000 | 25000 | 2024-06-25 | 500 | 2024-06-25 | 500 | 2024-10-23 | 22500 | 2024-10-23 | 22500 | 2024-10-26 | 2000 | 2024-10-26 | 2000
2407397 | Foo Su Hoong | 39600 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 39600 | 39600 | 2024-07-25 | 500 | 2024-07-25 | 500 | 2024-10-24 | 39100 | 2024-10-24 | 39100
2404250 | Wan Johan Bin Rahim | 50320 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 50320 | 50320 | 2024-07-27 | 500 | 2024-07-27 | 500 | 2024-11-12 | 47820 | 2024-12-20 | 47820 | 2024-12-20 | 2000 | 2024-12-20 | 2000
2407399 | Koo Woon Kee | 31000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 31000 | 31000 | 2024-10-22 | 500 | 2024-10-22 | 500 | 2024-10-22 | 28500 | 2024-10-22 | 28500 | 2024-12-26 | 2000 | 2024-12-29 | 2000
2407394 | Nor Aini binti Mat Saman (Nazrul Latif) | 24100 | 0 | Patricia | R-PV | Self finance | Invoice Completed | Payment Completed | 24100 | 24100 | 2024-07-31 | 500 | 2024-07-31 | 500 | 2024-09-17 | 21600 | 2024-09-17 | 21600 | 2024-11-18 | 2000 | 2024-11-18 | 2000
2407397-1 | Teo Kai Yun | 39600 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 39600 | 39600 | 2024-08-02 | 500 | 2024-08-02 | 500 | 2024-12-09 | 37100 | 2024-12-09 | 37100 | 2024-12-31 | 2000 | 2025-01-02 | 2000
2312114 | Chua Teng Teng | 31000 | 0 | Tham | R-PV | Self finance | Invoice Completed | Payment Completed | 31000 | 31000 | 2024-06-15 | 500 | 2024-06-15 | 500 | 2024-08-08 | 28500 | 2024-08-08 | 28500 | 2024-12-26 | 2000 | 2024-12-30 | 2000
2401123 | Lee Yoon Huat | 36500 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 36500 | 36500 | 2024-06-26 | 500 | 2024-06-26 | 500 | 2024-10-23 | 36000 | 2024-10-23 | 36000
2404207 | Tan Boon Siang (Han Father) | 26240 | -1404 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 24836 | 24836 | 2024-05-20 | 500 | 2024-05-20 | 500 | 2024-12-31 | 24336 | 2025-01-16 | 24336
2408402 | Tee Cheong Tuan | 43000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 43000 | 43000 | 2024-11-15 | 500 | 2024-11-15 | 500 | 2024-11-15 | 42500 | 2024-11-15 | 42500
2407372 | Dato Tay Tong Ben | 37600 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 37600 | 37600 | 2024-08-05 | 500 | 2024-08-05 | 500 | 2024-09-27 | 37100 | 2024-09-27 | 37100
2405298 | Lim Choon Huat | 35960 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 35960 | 35960 | 2024-10-01 | 500 | 2024-10-01 | 500 | 2024-10-01 | 35460 | 2024-10-01 | 35460
2408404 | Ong Ling Gee | 24680 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 24680 | 24680 | 2024-08-08 | 500 | 2024-08-08 | 500 | 2024-10-29 | 24180 | 2024-10-29 | 24180
2408401 | Kuek Soon Yeam | 22500 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 22500 | 22500 | 2024-08-08 | 500 | 2024-08-08 | 500 | 2024-10-30 | 20000 | 2024-10-30 | 20000 | 2024-12-26 | 2000 | 2024-12-27 | 2000
2408398 | Yap Siok Ching | 36680 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 36680 | 36680 | 2024-10-22 | 500 | 2024-10-22 | 500 | 2024-10-22 | 36180 | 2024-11-15 | 36180
2408415 | Shahrin Merican | 45600 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 45600 | 45600 | 2024-10-22 | 500 | 2024-10-22 | 500 | 2024-10-22 | 43100 | 2024-10-29 | 43100 | 2024-11-19 | 2000 | 2024-11-14 | 2000
2408425 | Chua Shen Huat | 43100 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 43100 | 43100 | 2024-10-22 | 500 | 2024-10-22 | 500 | 2024-10-22 | 42600 | 2024-10-22 | 42600
2406334 | Yap Kee Leong | 37600 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 37600 | 37600 | 2024-08-27 | 500 | 2024-08-27 | 500 | 2024-12-17 | 37100 | 2024-12-17 | 37100
2407371 | Tiong Nguong Kiong | 32800 | 0 | Chean Bang | R-PV | Cash | Invoice Completed | Payment Completed | 32800 | 32800 | 2024-10-24 | 500 | 2024-10-24 | 500 | 2024-10-24 | 30300 | 2024-10-24 | 30300 | 2024-12-26 | 2000 | 2024-12-23 | 2000
2408409 | Lua Peck Lay | 27700 | 0 | Patricia | R-PV | Cash | Invoice Completed | 3rd payment | 27700 | 25700 | 2024-10-08 | 500 | 2024-10-08 | 500 | 2024-10-08 | 12600 | 2024-10-08 | 12600 | 2024-10-17 | 12600 | 2024-11-22 | 12600 | 2024-12-26 | 2000
2408411 | Akhman Aidi Putra | 24100 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 24100 | 24100 | 2024-08-15 | 500 | 2024-08-15 | 500 | 2024-10-01 | 21600 | 2024-10-01 | 21600 | 2024-10-15 | 2000 | 2024-10-15 | 2000
2408408 | Chiang Yoke Har | 50600 | 0 | Patricia | R-PV | Cash + Credit Card Instalment | Invoice Completed | Payment Completed | 50600 | 50600 | 2024-08-15 | 500 | 2024-08-15 | 500 | 2024-10-14 | 50100 | 2024-10-14 | 50100
2408025 | Handal Green Mobility Sdn Bhd (ICE Gallery @ Pantai Sentral) | 55300 | 0 | Simon | EV Charger | Cash | Invoice Completed | Payment Completed | 55300 | 55300 | 2024-10-28 | 55300 | 2024-11-06 | 55300
2408431 | Lor Yean Yean | 30000 | 0 | Tham | R-PV | 0 | Invoice Completed | Payment Completed | 30000 | 30000 | 2024-08-11 | 500 | 2024-08-11 | 500 | 2025-03-11 | 29500 | 2025-03-27 | 29500
2408432 | Lin Mok Kwai Yin | 23800 | 0 | Chean Bang | R-PV | 0 | Invoice Completed | Payment Completed | 23800 | 23800 | 2024-09-11 | 500 | 2024-09-11 | 500 | 2024-12-09 | 21300 | 2025-04-10 | 21300 | 2025-04-10 | 2000 | 2025-04-10 | 2000
2408407 | Kwong Wui Ee | 29700 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 29700 | 29700 | 2024-09-04 | 500 | 2024-09-04 | 500 | 2024-11-04 | 29200 | 2024-11-28 | 29200
2409441 | Cheu Chow Sew @ Chew Chow Sew | 38000 | 0 | Chean Bang | R-PV | Cash | Invoice Completed | Payment Completed | 38000 | 38000 | 2024-11-08 | 500 | 2024-11-08 | 500 | 2024-11-09 | 35500 | 2024-11-09 | 35500 | 2024-12-03 | 2000 | 2024-12-03 | 2000
2408433 | Ng Ek Hoo | 24000 | 0 | Chean Bang | R-PV | Cash | Invoice Completed | Payment Completed | 24000 | 24000 | 2024-09-02 | 500 | 2024-09-02 | 500 | 2024-11-25 | 21500 | 2024-11-25 | 21500 | 2024-12-26 | 2000 | 2024-12-23 | 2000
2409445 | Phang Kar Teck | 22500 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 22500 | 22500 | 2024-09-10 | 500 | 2024-09-10 | 500 | 2025-04-09 | 22000 | 2025-06-13 | 22000
2408434 | Lim Ye Soon | 38600 | 0 | Chean Bang | R-PV | Cash | Invoice Completed | Payment Completed | 38600 | 38600 | 2024-11-13 | 500 | 2024-11-13 | 500 | 2024-11-13 | 36100 | 2024-11-13 | 36100 | 2025-01-26 | 2000 | 2025-01-26 | 2000
2409442 | Lee Chiou Horng | 33000 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 33000 | 33000 | 2024-09-07 | 500 | 2024-09-07 | 500 | 2025-04-05 | 32500 | 2025-04-05 | 32500
2409443 | Dato Lim Zhen Peng | 47360 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 47360 | 47360 | 2024-09-09 | 500 | 2024-09-09 | 500 | 2025-01-01 | 46860 | 2025-01-01 | 46860
2408417 | Mohmad Nazeri bin Abdul Wahab | 36500 | 0 | Tham | R-PV | Cash | Invoice Completed | 1st payment | 36500 | 500 | 2024-09-05 | 500 | 2024-09-05 | 500 | 2025-09-18 | 34000 |  |  | 2025-11-13 | 2000
2409440 | Tan Say Kheng | 25520 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 25520 | 25520 | 2024-09-04 | 500 | 2024-09-04 | 500 | 2024-11-25 | 25020 | 2024-11-25 | 25020
2405273 | Leong Ah Seng | 44600 | 7500 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 52100 | 52100 | 2024-08-29 | 500 | 2024-08-29 | 500 | 2024-12-31 | 42100 | 2025-01-03 | 42100 | 2025-04-04 | 2000 | 2025-04-24 | 2000 | [8 empty] | 2024-12-26 | 7500 | 2025-01-03 | 7500
2308064 | Low Yin Jun | 35000 | 0 | Simon | R-PV | Cash | Invoice Completed | Payment Completed | 35000 | 35000 | 2024-07-16 | 500 | 2024-07-16 | 500 | 2025-05-27 | 34500 | 2025-05-27 | 34500
2409447 | Chan Chee Tuck | 22200 | 0 | Chean Bang | R-PV | Cash | Invoice Completed | Payment Completed | 22200 | 22200 | 2024-09-10 | 500 | 2024-09-10 | 500 | 2024-12-02 | 19700 | 2024-12-02 | 19700 | 2025-04-09 | 2000 | 2025-04-09 | 2000
2409444 | Tuan Noraizan Bt Tuan Long | 28700 | 0 | Chean Bang | R-PV | Cash | Invoice Completed | Payment Completed | 28700 | 28700 | 2024-09-11 | 500 | 2024-09-11 | 500 | 2025-02-10 | 26200 | 2025-02-11 | 26200 | 2025-08-05 | 2000 | 2025-08-05 | 2000
2407368 | Noor Izzah Akmal Bt Mohd Nordin | 38600 | 0 | Chean Bang | R-PV | Cash | Invoice Completed | Payment Completed | 38600 | 38600 | 2024-11-11 | 500 | 2024-11-11 | 500 | 2024-11-11 | 36100 | 2024-11-18 | 36100 | 2025-01-06 | 2000 | 2025-01-07 | 2000
2409446 | Guok Diong Chong | 28500 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 28500 | 28500 | 2024-09-10 | 500 | 2024-09-10 | 500 | 2024-11-22 | 26000 | 2024-11-22 | 26000 | 2025-04-04 | 2000 | 2025-04-14 | 2000
2404249 | Tan Kheng Guan | 47600 | 0 | Tham | R-PV | 0 | 1st invoice | 1st payment | 500 | 500 | 2024-09-09 | 500 | 2024-09-09 | 500
2408424-1 | Low Bok Tek | 46100 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 46100 | 46100 | 2024-12-09 | 500 | 2024-12-09 | 500 | 2024-12-09 | 43600 | 2024-12-17 | 43600 | 2025-01-06 | 2000 | 2025-01-07 | 2000
2408424-2 | Low Bok Tek | 46100 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 46100 | 46100 | 2024-12-09 | 500 | 2024-12-09 | 500 | 2024-12-09 | 43600 | 2024-12-31 | 43600 | 2025-01-06 | 2000 | 2025-01-07 | 2000
2405284 | Amirul Hakim bin Omar | 23500 | 0 | Tham | R-PV | 0 | Invoice Completed | Payment Completed | 23500 | 23500 | 2024-09-11 | 500 | 2024-09-11 | 500 | 2024-12-17 | 21000 | 2025-05-08 | 21000 | 2025-04-04 | 2000 | 2025-05-08 | 2000
2409448 | Pang Chong Han | 31622 | 0 | Simon | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 31622 | 31622 | 2024-09-10 | 500 | 2024-09-10 | 500 | 2025-03-26 | 31122 | 2025-03-26 | 31122
2408400 | Oh Chai Ean | 43300 | 0 | Chean Bang | R-PV | Cash | Invoice Completed | Payment Completed | 43300 | 43300 | 2024-09-11 | 500 | 2024-09-11 | 500 | 2025-03-01 | 40800 | 2025-03-01 | 40800 | 2025-05-20 | 2000 | 2025-05-20 | 2000
2409449-1 | Nurul Ain Binti Yahaya | 30000 | 0 | Chean Bang | R-PV | Cash+Credit Card Instalment | Invoice Completed | Payment Completed | 30000 | 30000 | 2024-09-11 | 500 | 2024-09-11 | 500 | 2024-12-10 | 29500 | 2025-01-02 | 29500
2409452 | Yio Pee Ban | 29700 | 0 | Chean Bang | R-PV | Cash | Invoice Completed | Payment Completed | 29700 | 29700 | 2024-11-12 | 500 | 2024-11-12 | 500 | 2024-11-12 | 27200 | 2024-11-12 | 27200 | 2024-12-13 | 2000 | 2024-12-13 | 2000
2409449 | Tan Hock Seng | 24908 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 24908 | 24908 | 2024-09-26 | 500 | 2024-09-26 | 500 | 2024-11-22 | 24408 | 2024-11-22 | 24408
2409448-1 | Claris Lim Jink Niee (Lim Chin Horng) | 34600 | 0 | Tham | R-PV | 0 | Invoice Completed | Payment Completed | 34600 | 34600 | 2024-09-20 | 500 | 2024-09-20 | 500 | 2024-12-12 | 32100 | 2024-12-13 | 32100 | 2025-01-07 | 2000 | 2025-01-10 | 2000
2406343 | Dato Sim Keng Piao | 30000 | 0 | Tham | R-PV | 0 | Invoice Completed | Payment Completed | 30000 | 30000 | 2024-09-27 | 500 | 2024-09-27 | 500 | 2024-12-06 | 27500 | 2024-12-06 | 27500 | 2024-12-09 | 2000 | 2024-12-09 | 2000
2409455 | Muhamad Syamil bin Zulkafli | 22800 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 22800 | 22800 | 2024-09-26 | 500 | 2024-09-26 | 500 | 2024-11-20 | 22300 | 2024-11-20 | 22300
2410064 | Zarita binti Saliman | 23940 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 23940 | 23940 | 2024-10-08 | 500 | 2024-10-08 | 500 | 2024-12-02 | 21440 | 2024-12-02 | 21440 | 2025-04-04 | 2000 | 2025-04-10 | 2000
2405305 | Chan Woei Jye | 32000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 32000 | 32000 | 2024-10-23 | 500 | 2024-10-23 | 500 | 2025-03-07 | 31500 | 2025-03-07 | 31500
2409456 | Low Hong Chin | 30000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 30000 | 30000 | 2024-10-18 | 500 | 2024-10-18 | 500 | 2024-12-26 | 27500 | 2025-01-08 | 27500 | 2025-04-04 | 2000 | 2025-07-04 | 2000
2410461 | Low Hong Choon | 23500 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 23500 | 23500 | 2024-10-04 | 500 | 2024-10-04 | 500 | 2024-12-26 | 21000 | 2025-01-08 | 21000 | 2025-04-04 | 2000 | 2025-07-04 | 2000
2409029 | Handal Green Mobility Sdn Bhd (Mazda Kuantan Showroom) | 2643 | 0 | Simon | EV Charger | Cash | Invoice Completed | Pending 1st Payment | 2643 | 0 | 2024-11-13 | 2643
2410032 | Handal Green Mobility Sdn Bhd (United Point Mall, Kuala Lumpur) | 38470 | 0 | Simon | EV Charger | Cash | Invoice Completed | Payment Completed | 38470 | 38470 | 2024-10-28 | 19235 | 2024-11-06 | 19235 | 2024-01-10 | 19235 | 2025-01-28 | 19235
2407167-1 | Econframe Marketing Sdn Bhd (Kilang 1 & 3) | 233000 | 0 | Tham | C&I-PV | Cash | Invoice Completed | 3rd payment | 233000 | 163370 | 2024-09-24 | 23300 | 2024-09-24 | 23300 | 2024-11-25 | 81550 | 2024-12-13 | 81550 | 2025-01-24 | 58250 | 2025-02-05 | 58520 | 2025-04-29 | 69900
2407167-2 | Econframe Marketing Sdn Bhd (Kilang 4) | 71000 | 0 | Tham | C&I-PV | Cash | Invoice Completed | 2nd payment | 71000 | 31950 | 2024-09-24 | 7100 | 2024-09-24 | 7100 | 2024-11-25 | 24850 | 2024-12-14 | 24850 | 2025-04-29 | 39050
2407167-3 | Econframe Marketing Sdn Bhd (Kilang 20) | 136000 | 0 | Tham | C&I-PV | Cash | Invoice Completed | 2nd payment | 136000 | 61200 | 2024-09-24 | 13600 | 2024-09-24 | 13600 | 2024-11-25 | 47600 | 2024-12-15 | 47600 | 2025-04-29 | 74800
2408174 | Zimandy Construction Sdn Bhd (Bandar Tenggara) | 269900 | 0 | Tham | C&I-PV | Cash | Invoice Completed | 2nd payment | 269900 | 121455 | 2025-04-03 | 26990 | 2025-06-19 | 26990 | 2025-08-06 | 94465 | 2025-08-14 | 94465 | 2025-11-03 | 148445
2408179 | Pelita Hijrah Sdn Bhd | 320000 | 0 | Tham | C&I-PV | Cash | Invoice Completed | Payment Completed | 320000 | 320000 | 2024-10-31 | 32000 | 2024-10-31 | 32000 | 2024-12-16 | 112000 | 2025-01-07 | 112000 | 2025-01-24 | 80000 | 2025-02-05 | 80000 | 2025-04-29 | 96000 | 2025-10-29 | 96000
2409185 | Kim Chong Mechanical Services Sdn Bhd | 73000 | 0 | Tham | C&I-PV | Cash | Invoice Completed | Payment Completed | 73000 | 73000 | 2024-10-04 | 7300 | 2024-10-04 | 7300 | 2024-11-25 | 25550 | 2024-11-26 | 25550 | 2025-01-24 | 40150 | 2025-02-04 | 40150
2410196 | Unilink Machinery Sdn Bhd | 73000 | 0 | Tham | C&I-PV | Cash | Invoice Completed | Payment Completed | 73000 | 73000 | 2024-11-02 | 7300 | 2024-11-02 | 7300 | 2025-04-03 | 65700 | 2025-04-07 | 65700
2410474 | Koe Ban Seng | 37600 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 37600 | 37600 | 2024-11-01 | 500 | 2024-11-01 | 500 | 2024-12-06 | 35100 | 2024-12-18 | 35100 | 2025-03-04 | 2000 | 2025-03-04 | 2000
2410468 | Teo Boon Ling | 36600 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 36600 | 36600 | 2024-10-25 | 500 | 2024-10-25 | 500 | 2025-04-28 | 34100 | 2025-07-01 | 34100 | 2025-09-11 | 2000 | 2025-09-11 | 2000
2409450 | David Hie Wen Jian | 23500 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 23500 | 23500 | 2024-10-25 | 500 | 2024-10-25 | 500 | 2024-12-18 | 21000 | 2024-12-18 | 21000 | 2025-04-04 | 2000 | 2025-04-10 | 2000
2411488 | Tan Kong Ling | 32000 | 0 | Chean Bang | R-PV | Cash | Invoice Completed | Payment Completed | 32000 | 32000 | 2024-11-02 | 500 | 2024-11-02 | 500 | 2024-12-17 | 29500 | 2024-12-17 | 29500 | 2025-06-02 | 2000 | 2025-06-02 | 2000
2411487 | Lim Daw Woei | 42200 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 42200 | 42200 | 2024-11-05 | 500 | 2024-11-05 | 500 | 2025-01-18 | 41700 | 2025-01-18 | 41700
2410476 | Choong Chin Fong | 23500 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 23500 | 23500 | 2024-11-03 | 500 | 2024-11-03 | 500 | 2025-01-03 | 21000 | 2025-01-05 | 21000 | 2025-04-04 | 2000 | 2025-07-28 | 2000
2407376 | Teoh Eng Siong | 37768 | 0 | Chean Bang | R-PV | Credit Card Instalment | Invoice Completed | 2nd payment | 37768 | 30400 | 2024-07-17 | 500 | 2024-07-17 | 400 | 2024-09-01 | 37268 | 2024-09-01 | 30000
2410482 | Teo Thian Keong | 28500 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 28500 | 28500 | 2024-10-31 | 500 | 2024-11-02 | 500 | 2025-02-06 | 28000 | 2025-02-06 | 28000
2410471 | Chua Lu Chuan | 47600 | 0 | Chean Bang | R-PV | Cash | 1st invoice | 1st payment | 500 | 500 | 2024-10-11 | 500 | 2024-10-11 | 500
2411489 | Quah Ewe Lee | 39980 | 0 | Tham | R-PV | 0 | Invoice Completed | Payment Completed | 39980 | 39980 | 2024-11-26 | 500 | 2024-11-26 | 500 | 2025-01-17 | 39480 | 2025-01-17 | 39480
2411486 | Lim Chee Keong | 36600 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 36600 | 36600 | 2024-12-02 | 500 | 2024-12-02 | 500 | 2025-02-21 | 36100 | 2025-02-21 | 36100
2411500 | Ho Maw Chun | 37600 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 37600 | 37600 | 2024-12-02 | 500 | 2024-12-02 | 500 | 2025-02-21 | 37100 | 2025-03-09 | 37100
2410034 | Handal Green Mobility Sdn Bhd (Pulse Grande Hotel) | 4150 | 0 | Chean Bang | EV Charger | Cash | Invoice Completed | Payment Completed | 4150 | 4150 | 2025-03-12 | 4150 | 2025-03-25 | 4150
2411494 | Pang Kim Soon | 60000 | 0 | Chean Bang | R-PV | Cash | Invoice Completed | Payment Completed | 60000 | 60000 | 2024-11-26 | 500 | 2024-11-26 | 500 | 2025-02-11 | 57500 | 2025-05-31 | 57500 | 2025-05-31 | 2000 | 2025-05-31 | 2000
2411496 | Teong Lian Aik | 29000 | 289 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 29289 | 29289 | 2024-12-09 | 500 | 2024-12-09 | 500 | 2025-01-17 | 26789 | 2025-01-21 | 26789 | 2025-04-04 | 2000 | 2025-04-10 | 2000
2404224 | Vijayalakshmi a/p Krishnaswamy (Tan Sri Rama Iyer) | 45600 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 45600 | 45600 | 2024-11-28 | 500 | 2024-11-28 | 500 | 2025-02-18 | 45100 | 2025-02-18 | 45100
2411491 | Low Kim Keong | 38420 | 0 | Chean Bang | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 38420 | 38420 | 2024-12-05 | 500 | 2024-12-05 | 500 | 2025-02-28 | 37920 | 2025-02-28 | 37920
2411490 | Chear Eng Soon | 21500 | 0 | Chean Bang | R-PV | Cash | 2nd invoice | 2nd payment | 19500 | 19500 | 2024-12-05 | 500 | 2024-12-05 | 500 | 2024-12-31 | 19000 | 2025-01-02 | 19000
2412504 | Thiong Jeng Ell | 31616 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 31616 | 31616 | 2024-12-05 | 500 | 2024-12-05 | 500 | 2025-01-11 | 27500 | 2025-02-15 | 27500 | 2025-02-15 | 3616 | 2025-02-15 | 3616
2412503 | Lian Hock Seng | 38600 | 0 | Chean Bang | R-PV | Cash | Invoice Completed | Payment Completed | 38600 | 38600 | 2024-12-13 | 500 | 2024-12-13 | 500 | 2025-01-09 | 36100 | 2025-01-09 | 36100 | 2025-08-04 | 2000 | 2025-08-04 | 2000
2410033 | Handal Green Mobility Sdn Bhd (Kuantan City Mall) | 55000 | 0 | Chean Bang | EV Charger | Cash | Invoice Completed | Payment Completed | 55000 | 55000 | 2025-03-12 | 55000 | 2025-03-25 | 55000
2412505 | Dong Mee Hong | 42860 | 0 | Patricia | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 42860 | 42860 | 2024-12-13 | 500 | 2024-12-17 | 500 | 2025-02-28 | 42360 | 2025-02-28 | 42360
2412509 | Muck Bei lee (Le Lodge Mansion) | 50000 | 0 | Chean Bang | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 50000 | 50000 | 2024-12-31 | 500 | 2024-12-31 | 500 | 2025-01-20 | 49500 | 2025-01-21 | 49500
2412515 | Liew Mun Meng | 44600 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 44600 | 44600 | 2024-12-21 | 500 | 2024-12-21 | 500 | 2025-02-17 | 40600 | 2025-02-18 | 40600 | 2025-03-05 | 3500 | 2025-03-12 | 3500
2410462 | Yee Mei Ling | 23500 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 23500 | 23500 | 2024-12-23 | 500 | 2024-12-23 | 500 | 2025-03-24 | 23000 | 2025-03-25 | 23000
2412516 | Chareon Phromsuwan | 37160 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 37160 | 37160 | 2024-12-24 | 500 | 2024-12-24 | 500 | 2025-03-07 | 36660 | 2025-03-07 | 36660
2412521 | Christopher A De Souza | 39560 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 39560 | 39560 | 2025-01-02 | 500 | 2025-01-02 | 500 | 2025-03-04 | 39060 | 2025-03-04 | 39060
2412524 | Teng Lee Xung | 34000 | 0 | Chean Bang | R-PV | Cash | Invoice Completed | Payment Completed | 34000 | 34000 | 2024-12-30 | 500 | 2024-12-30 | 500 | 2024-12-30 | 31500 | 2025-03-23 | 31500 | 2025-03-23 | 2000 | 2025-03-23 | 2000
2412513 | Ganapathy Srihari a/l Rama Iyer | 29000 | 0 | Tham | R-PV | Cash | 2nd invoice | 2nd payment | 27000 | 27000 | 2025-01-09 | 500 | 2025-01-09 | 500 | 2025-09-23 | 26500 | 2025-09-23 | 26500
2501038 | Florence Poon | 2000 | 0 | Simon | EV Charger | Cash | Invoice Completed | Payment Completed | 2000 | 2000 | 2025-01-21 | 1000 | 2025-01-21 | 1000 | 2025-01-25 | 1000 | 2025-01-25 | 1000
2501532 | Prasert Phromsuwan | 27000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 27000 | 27000 | 2025-01-24 | 500 | 2025-01-24 | 500 | 2025-03-12 | 26500 | 2025-03-12 | 26500
2501544 | Gan Tek Chuan | 44000 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 44000 | 44000 | 2025-02-07 | 500 | 2025-02-07 | 500 | 2025-03-17 | 41500 | 2025-03-17 | 41500 | 2025-04-15 | 2000 | 2025-04-15 | 2000
2502548 | Wong Kok Wai | 42000 | 0 | Chean Bang | R-PV | Cash | Invoice Completed | Payment Completed | 42000 | 42000 | 2025-02-07 | 500 | 2025-02-07 | 500 | 2025-03-24 | 39500 | 2025-03-25 | 39500 | 2025-11-09 | 2000 | 2025-11-09 | 2000
2501545 | Lee Tian Look | 21800 | 0 | Chean Bang | R-PV | Cash | Invoice Completed | Payment Completed | 21800 | 21800 | 2025-02-13 | 500 | 2025-02-13 | 500 | 2025-04-15 | 19300 | 2025-04-15 | 19300 | 2025-05-31 | 2000 | 2025-05-31 | 2000
2311088 | Lee Chean Chung | 27000 | 0 | Chean Bang | R-PV | Cash | 1st invoice | 1st payment | 500 | 500 | 2025-02-12 | 500 | 2025-02-12 | 500
2502216 | Low Yi Chin | 37000 | 0 | Chean Bang | C&I-PV | Cash | Invoice Completed | Payment Completed | 37000 | 37000 | 2025-02-13 | 500 | 2025-02-13 | 500 | 2025-07-17 | 34500 | 2025-08-27 | 34500 | 2025-08-30 | 2000 | 2025-08-30 | 2000
2502553 | Salim Majid Zain Bin Abdul Majid | 42000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 42000 | 42000 | 2025-02-14 | 500 | 2025-02-14 | 500 | 2025-03-24 | 41500 | 2025-03-24 | 41500
2502552 | Anandan a/l Balakrishnan | 31000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 31000 | 31000 | 2025-02-14 | 500 | 2025-02-14 | 500 | 2025-04-07 | 30500 | 2025-04-07 | 30500
2412519 | Liew Swee Fah | 21500 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 21500 | 21500 | 2025-02-12 | 500 | 2025-02-12 | 500 | 2025-04-08 | 19000 | 2025-04-08 | 19000 | 2025-06-04 | 2000 | 2025-06-04 | 2000
2502547 | Chong Chee Hoo | 32840 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 32840 | 32840 | 2025-02-22 | 500 | 2025-02-24 | 500 | 2025-04-03 | 32340 | 2025-04-03 | 32340
2502541 | Boo Kee Meng | 21500 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 21500 | 21500 | 2025-02-16 | 500 | 2025-02-17 | 500 | 2025-03-18 | 19000 | 2025-03-18 | 19000 | 2025-05-17 | 2000 | 2025-05-17 | 2000
2502556 | Gan Chong Sing | 22500 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 22500 | 22500 | 2025-02-17 | 500 | 2025-02-17 | 500 | 2025-03-17 | 20000 | 2025-03-17 | 20000 | 2025-04-15 | 2000 | 2025-04-15 | 2000
2502551 | Tan Seng Shen | 35000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 35000 | 35000 | 2025-02-17 | 500 | 2025-02-17 | 500 | 2025-03-10 | 32500 | 2025-03-12 | 32500 | 2025-05-28 | 2000 | 2025-05-29 | 2000
2502546 | Jordan Tan Heng Xiang | 22500 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 22500 | 22500 | 2025-02-17 | 500 | 2025-02-17 | 500 | 2025-03-08 | 20000 | 2025-03-08 | 20000 | 2025-04-30 | 2000 | 2025-04-30 | 2000
2502559 | Wong Peng Soon | 28000 | 0 | Chean Bang | R-PV | Cash | Invoice Completed | Payment Completed | 28000 | 28000 | 2025-02-18 | 500 | 2025-02-18 | 500 | 2025-03-23 | 25500 | 2025-03-23 | 25500 | 2025-04-02 | 2000 | 2025-04-03 | 2000
2501537 | Chan My Ling | 33800 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 33800 | 33800 | 2025-02-13 | 500 | 2025-02-17 | 500 | 2025-03-28 | 33300 | 2025-03-28 | 33300
2502550 | Ricky Goh Hoon Kan | 37500 | 0 | Chean Bang | R-PV | Cash | 1st invoice | 1st payment | 35500 | 35500 | 2025-09-22 | 35500 | 2025-09-22 | 35500
2502543 | Chow Leong Choon | 22000 | 0 | Ong | R-PV | Cash | Invoice Completed | Payment Completed | 22000 | 22000 | 2025-02-13 | 500 | 2025-02-18 | 500 | 2025-03-16 | 19500 | 2025-03-17 | 19500 | 2025-04-09 | 2000 | 2025-04-09 | 2000
2502560 | Lim Sooi Poh | 35000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 35000 | 35000 | 2025-02-20 | 500 | 2025-02-20 | 500 | 2025-04-10 | 32500 | 2025-04-11 | 32500 | 2025-06-30 | 2000 | 2025-07-01 | 2000
2408411-1 | Eng Khai Shu | 43000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 43000 | 43000 | 2025-02-25 | 500 | 2025-02-26 | 500 | 2025-03-26 | 40500 | 2025-03-27 | 40500 | 2025-05-27 | 2000 | 2025-05-27 | 2000
2502569 | Chew Beng Hock | 29228 | 0 | Ong | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 29228 | 29228 | 2025-02-24 | 500 | 2025-02-24 | 500 | 2025-04-03 | 28728 | 2025-04-03 | 28728
2502565 | Yeo Shu Jin | 21500 | 0 | Simon | R-PV | Cash | 1st invoice | Pending 1st Payment | 19500 | 0 | 2025-04-29 | 19500
2502549 | Har Hock Lee | 35000 | 0 | Patricia | R-PV | Cash | 2nd invoice | 2nd payment | 33000 | 15500 | 2025-02-25 | 500 | 2025-02-25 | 500 | 2025-07-25 | 32500 | 2025-07-25 | 15000
2405286 | Wong Wai Hung | 41000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 41000 | 41000 | 2025-02-28 | 500 | 2025-02-28 | 500 | 2025-04-10 | 40500 | 2025-04-21 | 40500
2501527 | Kuan Guan Chong | 31000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 31000 | 31000 | 2025-02-19 | 500 | 2025-02-19 | 500 | 2025-04-22 | 30500 | 2025-04-22 | 30500
2501529 | Kuan Kian Yang | 29000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 29000 | 29000 | 2025-03-02 | 500 | 2025-03-04 | 500 | 2025-04-22 | 28500 | 2025-04-22 | 28500
2502581 | Loh Chee Kuan | 22340 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 22340 | 22340 | 2025-03-01 | 500 | 2025-03-02 | 500 | 2025-04-04 | 21840 | 2025-04-04 | 21840
2501540 | Mohd Rushdi Bin Haji Abu Bakar | 23429 | 0 | Patricia | R-PV | Cash + CC Instalment | Invoice Completed | Payment Completed | 23429 | 23429 | 2025-01-21 | 500 | 2025-01-21 | 500 | 2025-04-11 | 22929 | 29//4/2025 | 22929
2502571 | Ting Kam Peng | 32840 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 32840 | 32840 | 2025-03-02 | 500 | 2025-03-04 | 500 | 2025-04-11 | 32340 | 2025-04-11 | 32340
2502568 | Lim See Peng | 25280 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 25280 | 25280 | 2025-02-28 | 500 | 2025-02-28 | 500 | 2025-06-12 | 24780 | 2025-06-12 | 24780
2404258 | Chan Yee Wan | 27000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 27000 | 27000 | 2025-03-06 | 500 | 2025-03-06 | 500 | 2025-04-22 | 26500 | 2025-04-22 | 26500
2503588 | Lee Xue Cheng | 22500 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 22500 | 22500 | 2025-03-06 | 500 | 2025-03-06 | 500 | 2025-05-27 | 20000 | 2025-05-30 | 20000 | 2025-05-30 | 2000 | 2025-05-30 | 2000
2502561 | Dennis Lee Jia Seng | 38000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 38000 | 38000 | 2025-03-07 | 500 | 2025-03-07 | 500 | 2025-05-02 | 37500 | 2025-05-02 | 37500
2503590 | Teh Wee Loon | 39680 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 39680 | 39680 | 2025-03-07 | 500 | 2025-03-07 | 500 | 2025-04-30 | 39180 | 2025-04-30 | 39180
2502570 | Tang Wei Keong | 27000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 27000 | 27000 | 2025-03-07 | 500 | 2025-03-07 | 500 | 2025-06-30 | 26500 | 2025-07-01 | 26500
2502573 | Wong Jun Kit | 26000 | 0 | Simon | R-PV | Cash | Invoice Completed | Payment Completed | 26000 | 26000 | 2025-03-06 | 500 | 2025-03-06 | 500 | 2025-04-24 | 23500 | 2025-04-24 | 23500 | 2025-05-07 | 2000 | 2025-05-07 | 2000
2503593 | Rashid Bin Darlan | 24548 | 0 | Patricia | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 24548 | 24548 | 2025-03-10 | 500 | 2025-03-10 | 500 | 2025-04-24 | 24048 | 2025-04-24 | 24048
2501211 | Great Beauty Furniture Sdn Bhd | 54000 | 0 | Chean Bang | C&I-PV | Cash | 1st invoice | 1st payment | 5400 | 5400 | 2025-02-18 | 5400 | 2025-02-27 | 5400
2502589 | Chin Kok Leng | 26000 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 26000 | 26000 | 2025-03-07 | 500 | 2025-03-07 | 500 | 2025-03-24 | 25500 | 2025-03-27 | 25500
2403090 | Mei Shun Fang Manufacturing Sdn Bhd | 898000 | 8500 | Tham | C&I-PV | Cash | 5th invoice | 5th payment | 816700 | 812450 | 2025-04-14 | 94050 | 2025-04-24 | 94050 | 2025-05-28 | 4250 |  |  | 2025-05-30 | 314300 | 2025-06-06 | 314300 | 2025-09-04 | 224500 | 2025-09-22 | 224500 | 2025-11-03 | 179600 | 2025-11-18 | 179600
2502557 | Chin Yee Fa | 28000 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 28000 | 28000 | 2025-03-11 | 500 | 2025-03-11 | 500 | 2025-05-06 | 25500 | 2025-05-06 | 25500 | 2025-09-08 | 2000 | 2025-09-09 | 2000
2503594 | Wong Teck Keng | 22500 | 0 | Patricia | R-PV | Cash | 2nd invoice | 2nd payment | 20500 | 20500 | 2025-03-11 | 500 | 2025-03-11 | 500 | 2025-04-22 | 20000 | 2025-04-23 | 20000
2503597 | Bhajan Singh a/l S Bachan Singh | 31000 | 0 | Chean Bang | R-PV | Cash | Invoice Completed | Payment Completed | 31000 | 31000 | 2025-03-11 | 500 | 2025-03-11 | 500 | 2025-04-25 | 28500 | 2025-04-25 | 28500 | 2025-05-21 | 2000 | 2025-05-21 | 2000
2502588 | Khadillah binti Hassan | 26600 | 1000 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 27600 | 27600 | 2025-03-10 | 120 | 2025-03-12 | 120 | 2025-04-28 | 24480 | 2025-05-13 | 24480 | 2025-05-13 | 2000 | 2025-07-17 | 2000 | [8 empty] | 2025-06-30 | 1000 | 2025-07-17 | 1000
2502040 | ST Rosyam Mall (Plus Xnergy Services Sdn Bhd) | 92000 | 400 | Simon | EV Charger | Cash | Invoice Completed | Pending 1st Payment | 92400 | 0 | 2025-03-12 | 46000 |  |  | 2025-03-17 | 46000 | [14 empty] | 2025-04-15 | 400
2503595 | Lim Zhi Jie | 35000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 35000 | 35000 | 2025-03-14 | 500 | 2025-03-14 | 500 | 2025-07-31 | 34500 | 2025-07-31 | 34500
2503586 | Safinaz Binti Mohd Sharif | 21500 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 21500 | 21500 | 2025-03-14 | 500 | 2025-03-19 | 500 | 2025-04-23 | 19000 | 2025-04-23 | 19000 | 2025-06-24 | 2000 | 2025-06-29 | 2000
2503604 | Kong Chun Seng | 27000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 27000 | 27000 | 2025-03-17 | 500 | 2025-03-17 | 500 | 2025-04-21 | 26500 | 2025-04-21 | 26500
2503598 | Lew Yuen Tang | 27000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 27000 | 27000 | 2025-03-17 | 500 | 2025-03-17 | 500 | 2025-04-29 | 26500 | 2025-04-29 | 26500
2503609 | Yau Hwee Tien | 35000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 35000 | 35000 | 2025-03-19 | 500 | 2025-03-19 | 500 | 2025-05-27 | 32500 | 2025-08-05 | 32500 | 2025-08-05 | 2000 | 2025-08-05 | 2000
2503610 | Datuk Abdul Rani | 43000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 43000 | 43000 | 2025-03-24 | 500 | 2025-03-24 | 500 | 2025-04-16 | 40500 | 2025-04-16 | 40500 | 2025-04-17 | 2000 | 2025-04-17 | 2000
2503611 | Augustine Kok Hwai Nam | 23500 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 23500 | 23500 | 2025-03-26 | 500 | 2025-03-27 | 500 | 2025-04-24 | 23000 | 2025-04-24 | 23000
2501524 | Jeremy Koo Wui Ken | 27000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 27000 | 27000 | 2025-03-28 | 500 | 2025-03-28 | 500 | 2025-04-28 | 26500 | 2025-04-28 | 26500
2503617 | Vinny Len Siew Meng | 41000 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 41000 | 41000 | 2025-03-26 | 500 | 2025-03-26 | 500 | 2025-04-20 | 38500 | 2025-04-20 | 38500 | 2025-08-29 | 2000 | 2025-08-29 | 2000
2503601 | William Song Jian Tat | 29000 | 0 | Tham | R-PV | Cash | 1st invoice | 1st payment | 500 | 500 | 2025-03-26 | 500 | 2025-03-28 | 500
2503619 | Haslina binti Othman | 21500 | 0 | Patricia | 0 | Cash | 1st invoice | 1st payment | 500 | 500 | 2025-03-30 | 500 | 2025-03-30 | 500
2504623 | Choy Poh Chu | 21500 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 21500 | 21500 | 2025-04-03 | 500 | 2025-04-03 | 500 | 2025-04-19 | 21000 | 2025-05-10 | 21000
2503589 | Chong Shiuh Dyi | 21500 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 21500 | 21500 | 2025-04-09 | 500 | 2025-04-09 | 500 | 2025-05-30 | 19000 | 2025-05-30 | 19000 | 2025-06-03 | 2000 | 2025-06-03 | 2000
2504633 | Yong Chee Seng | 21500 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 21500 | 21500 | 2025-04-11 | 500 | 2025-04-11 | 500 | 2025-06-12 | 21000 | 2025-06-12 | 21000
2504636 | Nur Salinahany binti Hanafiah | 41000 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 41000 | 41000 | 2025-04-11 | 500 | 2025-04-11 | 500 | 2025-05-06 | 38500 | 2025-05-07 | 38500 | 2025-08-27 | 2000 | 2025-08-27 | 2000
2406152 | Chara Sdn Bhd | 155000 | 0 | Simon | C&I-PV | Cash | Invoice Completed | Payment Completed | 155000 | 155000 | 2025-05-19 | 69750 | 2025-06-06 | 69750 | 2025-06-30 | 38750 | 2025-07-07 | 38750 | 2025-09-29 | 46500 | 2025-10-09 | 46500
2504640 | Ng Mong Ping | 26000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 26000 | 26000 | 2025-04-17 | 500 | 2025-04-18 | 500 | 2025-05-27 | 25500 | 2025-05-28 | 25500
2504638 | Lai Boon Liong | 27000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 27000 | 27000 | 2025-04-17 | 500 | 2025-04-17 | 500 | 2025-05-27 | 26500 | 2025-05-27 | 26500
2504652 | Khairul Hisham Bin Mohamed | 27500 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 27500 | 27500 | 2025-04-19 | 500 | 2025-04-19 | 500 | 2025-05-15 | 25000 | 2025-08-01 | 25000 | 2025-08-18 | 2000 | 2025-08-18 | 2000
2504647 | Tan Hock Cheng | 21500 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 21500 | 21500 | 2025-04-20 | 500 | 2025-04-21 | 500 | 2025-05-28 | 19000 | 2025-05-28 | 19000 | 2025-05-28 | 2000 | 2025-05-30 | 2000
2504658 | Phang Yeong Chin | 22500 | 0 | Ong | R-PV | Cash | 2nd invoice | 2nd payment | 20500 | 20500 | 2025-04-22 | 500 | 2025-04-22 | 500 | 2025-05-07 | 20000 | 2025-05-07 | 20000
2503614 | Yap Weoi Kee | 0 | 0 | Simon | 0 | Cash | 1st invoice | 1st payment | 500 | 500 | 2025-04-23 | 500 | 2025-04-23 | 500
2504643 | Lee Sui Lian | 46700 | 0 | Patricia | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 46700 | 46700 | 2025-04-17 | 500 | 2025-04-24 | 500 | 2025-05-26 | 46200 | 2025-07-25 | 46200
2504663 | Too Seng Eng | 22500 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 22500 | 22500 | 2025-04-23 | 500 | 2025-04-23 | 500 | 2025-05-29 | 20000 | 2025-05-29 | 20000 | 2025-06-06 | 2000 | 2025-06-06 | 2000
2504671 | Anthony Phua Kin Loong | 41000 | 0 | Patricia | R-PV | Cash | 1st invoice | 1st payment | 500 | 500 | 2025-04-30 | 500 | 2025-04-30 | 500
2506644 | Chang Kok Sang (Chang Vun Yu) | 21000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 21000 | 21000 | 2025-04-26 | 500 | 2025-04-26 | 500 | 2025-06-20 | 20500 | 2025-06-24 | 20500
2505675 | Tee Hup Soon | 42170 | 0 | Patricia | R-PV | Credit Card Instalment | 1st invoice | 1st payment | 500 | 500 | 2025-05-05 | 500 | 2025-05-05 | 500
2502564 | Muhammad Arif Stephen bin Abddullah | 43000 | 0 | Simon | R-PV | Cash | 1st invoice | 1st payment | 500 | 500 | 2025-05-06 | 500 | 2025-05-06 | 500
2504664 | Law Meng Siong | 41000 | 0 | Patricia | R-PV | Cash | 1st invoice | 1st payment | 500 | 500 | 2025-04-28 | 500 | 2025-04-28 | 500
2504651 | Teh Bat Kuan (Teh Eng Lim) | 35000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 35000 | 35000 | 2025-05-09 | 500 | 2025-05-09 | 500 | 2025-06-25 | 32500 | 2025-06-25 | 32500 | 2025-07-21 | 2000 | 2025-07-21 | 2000
2504049 | Ayer Keroh R&R (Southbound) - Green EV Charge Sdn Bhd | 45015 | 0 | Simon | EV Charger | Cash | 1st invoice | Pending 1st Payment | 22507.5 | 0 | 2025-05-09 | 22507.5
2505686 | Lai Kwee Far | 21500 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 21500 | 21500 | 2025-05-13 | 500 | 2025-05-13 | 500 | 2025-06-05 | 18900 | 2025-07-21 | 18900 | 2025-11-03 | 2100 | 2025-11-03 | 2100
2503603 | Dr Balbinder Singh a/l Gurbaksh Singh | 43400 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 43400 | 43400 | 2025-05-13 | 500 | 2025-05-13 | 500 | 2025-07-29 | 42900 | 2025-07-29 | 42900
2302004 | Ong Ah Chai | 27500 | 0 | Chean Bang | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 27500 | 27500 | 2025-05-11 | 500 | 2025-05-11 | 500 | 2025-06-21 | 27000 | 2025-06-21 | 27000
2503225 | Weller Air-Cond Parts Enterprise Sdn Bhd | 198800 | 0 | Tham | C&I-PV | Cash | Invoice Completed | Payment Completed | 198800 | 198800 | 2025-05-28 | 19880 | 2025-06-10 | 19880 | 2025-07-21 | 69580 | 2025-07-28 | 69580 | 2025-08-27 | 89460 | 2025-09-04 | 89460 | 2025-09-24 | 19880 | 2025-11-14 | 19880
2403185 | Wan Kong Wing | 21500 | -1416 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 20084 | 20084 | 2025-05-14 | 500 | 2025-05-15 | 500 | 2025-06-26 | 19584 | 2025-06-26 | 19584
2410194 | Berjayapak Sdn Bhd | 395000 | 0 | Tham | C&I-PV | Cash | 3rd invoice | 2nd payment | 276500 | 177750 | 2025-08-15 | 39500 | 2025-08-29 | 39500 | 2025-09-24 | 138250 | 2025-10-16 | 138250 | 2025-11-13 | 98750
2504669 | Zohairen Bin Mhamad Sori | 29000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 29000 | 29000 | 2025-05-13 | 500 | 2025-05-14 | 500 | 2025-09-22 | 28500 | 2025-09-22 | 28500
2504660 | Roshahni Binti Mhammad | 34000 | 0 | Chean Bang | R-PV | Cash | Invoice Completed | 3rd payment | 34000 | 32500 | 2025-05-16 | 500 | 2025-05-16 | 500 | 2025-10-03 | 31500 | 2025-10-03 | 30000 | 2025-10-28 | 2000 | 2025-10-28 | 2000
2410191 | Jowee Trading Sdn Bhd | 150000 | 0 | Tham | C&I-PV | Cash | Invoice Completed | 2nd payment | 150000 | 67500 | 2025-06-16 | 15000 | 2025-07-31 | 15000 | 2025-07-31 | 52500 | 2025-08-13 | 52500 | 2025-09-04 | 67500 |  |  | 2025-10-28 | 15000
2505695 | Nur Salwahani Bt Muhammad | 27000 | 0 | Patricia | R-PV | Cash | 1st invoice | 1st payment | 500 | 500 | 2025-05-16 | 500 | 2025-05-16 | 500
2505672 | Tham Wai Hong | 27000 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 27000 | 27000 | 2025-05-15 | 500 | 2025-05-15 | 500 | 2025-06-06 | 25000 | 2025-06-10 | 25000 | 2025-06-19 | 1500 | 2025-06-19 | 1500
2505684 | Ng Heng Hock | 30000 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 30000 | 30000 | 2025-05-19 | 500 | 2025-05-19 | 500 | 2025-06-13 | 10000 | 2025-06-13 | 10000 | 2025-07-20 | 19500 | 2025-07-20 | 19500
2505697 | Chong Yee Sam | 21500 | 0 | Patricia | R-PV | Cash | 1st invoice | 1st payment | 500 | 500 | 2025-05-20 | 500 | 2025-05-20 | 500
2505688 | Heng Mooi Sing | 40000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 40000 | 40000 | 2025-05-20 | 500 | 2025-05-20 | 500 | 2025-06-24 | 37500 | 2025-07-01 | 37500 | 2025-06-27 | 2000 | 2025-08-05 | 2000
2505682 | Lee Soo Kean | 36620 | 0 | Patricia | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 36620 | 36620 | 2025-05-20 | 500 | 2025-05-20 | 500 | 2025-07-17 | 36120 | 2025-07-17 | 36120
2505699 | Kiren Kaur A/P Bhajan Singh | 33000 | 0 | Chean Bang | R-PV | Cash | 1st invoice | 1st payment | 500 | 500 | 2025-05-21 | 500 | 2025-05-21 | 500
2503612 | Low Bok Tek | 0 | 0 | Tham | R-PV | 0 | Invoice Completed | Payment Completed | 0 | 0
2505680 | Chiang Hock Chiong | 41000 | 0 | Patricia | R-PV | Cash | 1st invoice | Pending 1st Payment | 500 | 0 | 2025-05-22 | 500
2503607 | Goh Boon Leng | 29000 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 29000 | 29000 | 2025-05-21 | 500 | 2025-05-21 | 500 | 2025-07-30 | 28500 | 2025-07-30 | 28500
2505711 | Lee Len Foong | 25500 | 0 | Chean Bang | R-PV | Cash | 1st invoice | 1st payment | 500 | 500 | 2025-05-27 | 500 | 2025-05-27 | 500
2505713 | Yap Swee Piau | 41000 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 41000 | 41000 | 2025-05-27 | 500 | 2025-05-27 | 500 | 2025-06-30 | 38500 | 2025-08-06 | 38500 | 2025-08-06 | 2000 | 2025-08-17 | 2000
2505714 | Kong King Wai | 22500 | 0 | Tham | R-PV | Cash | 1st invoice | 1st payment | 500 | 500 | 2025-05-28 | 500 | 2025-05-28 | 500
2405306 | Leong Ah Seng | 43000 | 7000 | Tham | R-PV | Cash | Invoice Completed | 1st payment | 50000 | 500 | 2025-05-29 | 500 | 2025-05-29 | 500 | 2025-07-24 | 42500 | [14 empty] | 2025-07-24 | 7000
2505705 | Lee Kee Chew | 21500 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 21500 | 21500 | 2025-05-30 | 500 | 2025-05-30 | 500 | 2025-06-26 | 21000 | 2025-06-26 | 21000
2505717 | Sia Wee Leng | 42000 | 0 | Tham | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 42000 | 42000 | 2025-05-30 | 500 | 2025-05-30 | 500 | 2025-07-21 | 41500 | 2025-07-21 | 41500
2505699-1 | Leong Wai Wung | 32000 | 0 | Tham | R-PV | Cash | 1st invoice | 1st payment | 500 | 500 | 2025-05-30 | 500 | 2025-06-04 | 500
2505719 | Lim Jun Hong | 27000 | 0 | Tham | R-PV | Cash | 2nd invoice | 2nd payment | 25000 | 25000 | 2025-06-04 | 1000 | 2025-06-04 | 1000 | 2025-07-31 | 24000 | 2025-07-31 | 24000
2505687 | Thayananthan A/L Lokanatan | 30000 | 0 | Patricia | R-PV | Cash | 2nd invoice | 2nd payment | 27000 | 20000 | 2025-05-27 | 500 | 2025-05-27 | 500 | 2025-06-06 | 26500 | 2025-08-17 | 19500
2505718 | Koh Kheat Kian | 23500 | 0 | Chean Bang | R-PV | Cash | Invoice Completed | Payment Completed | 23500 | 23500 | 2025-06-07 | 1000 | 2025-06-07 | 1000 | 2025-08-01 | 20500 | 2025-08-01 | 20500 | 2025-08-25 | 2000 | 2025-08-25 | 2000
2506726 | Poh Pun Hong | 22000 | 0 | Ong | R-PV | Cash + CC Instalment | Invoice Completed | Payment Completed | 22000 | 22000 | 2025-06-08 | 10000 | 2025-06-08 | 10000 | 2025-06-30 | 12000 | 2025-07-29 | 12000
2506735 | Lee Meng Fui | 19000 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 19000 | 19000 | 2025-06-08 | 1000 | 2025-06-09 | 1000 | 2025-06-30 | 16000 | 2025-07-09 | 16000 | 2025-07-11 | 2000 | 2025-07-11 | 2000
2506734 | Leow Siew Lian (Tee Hong Yee) | 25500 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 25500 | 25500 | 2025-06-09 | 1000 | 2025-06-09 | 1000 | 2025-06-30 | 24500 | 2025-07-11 | 24500
2505708 | Mohd Shariff | 20500 | 0 | Tham | R-PV | Cash | 1st invoice | 1st payment | 500 | 500 | 2025-06-10 | 500 | 2025-06-10 | 500
2506744 | Gan Chin Sam | 32500 | 0 | Tham | R-PV | Cash | 2nd invoice | 2nd payment | 30500 | 30500 | 2025-06-09 | 1000 | 2025-06-09 | 1000 | 2025-07-27 | 29500 | 2025-07-27 | 29500
2506727 | Tan Lee Khing | 28300 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 28300 | 28300 | 2025-06-09 | 1000 | 2025-06-09 | 1000 | 2025-07-28 | 25300 | 2025-07-28 | 25300 | 2025-09-08 | 2000 | 2025-09-08 | 2000
2505054 | DK Senza Residence | 59345 | 0 | Simon | EV Charger | 0 | 1st invoice | 1st payment | 29672.5 | 29672.5 | 2025-08-21 | 29672.5 | 2025-10-03 | 29672.5
2506752 | Ng Cheng Hoe | 22500 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 22500 | 22500 | 2025-06-13 | 1000 | 2025-06-13 | 1000 | 2025-08-09 | 21500 | 2025-08-09 | 21500
2501523 | Chen Kim Hock | 44880 | 0 | Tham | R-PV | Cash | 1st invoice | 1st payment | 500 | 500 | 2025-06-13 | 500 | 2025-06-13 | 500
2506748 | Teh Foo Hock | 22500 | 0 | Patricia | R-PV | Cash | 1st invoice | 1st payment | 1000 | 1000 | 2025-06-16 | 1000 | 2025-06-16 | 1000
2505709 | Tan Heng Lian | 39000.4 | 0 | Patricia | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 39000.4 | 39000.4 | 2025-06-16 | 1000 | 2025-06-16 | 1000 | 2025-08-01 | 38000.4 | 2025-08-01 | 38000.4
2501531 | Mohamad Hafizi Bin Abdul Rahman | 30500 | 0 | Patricia | R-PV | Cash | 1st invoice | 1st payment | 1000 | 1000 | 2025-06-16 | 1000 | 2025-06-16 | 1000
2506757 | Chai Cheong Sing | 21500 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 21500 | 21500 | 2025-06-17 | 1000 | 2025-06-17 | 1000 | 2025-09-24 | 18500 | 2025-08-05 | 18500 | 2025-09-22 | 2000 | 2025-09-22 | 2000
2505259 | Liew Wen Qi | 45000 | 0 | Patricia | C&I-PV | Cash | Invoice Completed | Payment Completed | 45000 | 45000 | 2025-06-16 | 4500 | 2025-06-16 | 4500 | 2025-07-22 | 15750 | 2025-07-22 | 15750 | 2025-08-31 | 24750 | 2025-08-31 | 24750
2506758 | Goh Boon Meng | 39500 | 0 | Patricia | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 39500 | 39500 | 2025-06-18 | 1000 | 2025-06-18 | 1000 | 2025-10-02 | 38500 | 2025-10-02 | 38500
2506762 | Megat Mohd Nashrul Bin Ahmad Zulkepli | 32500 | 0 | Patricia | R-PV | Cash | 1st invoice | 1st payment | 1000 | 1000 | 2025-06-20 | 1000 | 2025-06-20 | 1000
2506753 | Lim Geok Suan | 27500 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 27500 | 27500 | 2025-06-19 | 1000 | 2025-06-19 | 1000 | 2025-08-06 | 26500 | 2025-08-06 | 26500
2506768 | Yap Lee Yan | 27000 | 0 | Patricia | R-PV | Cash | 2nd invoice | 2nd payment | 25000 | 25000 | 2025-06-20 | 1000 | 2025-06-20 | 1000 | 2025-08-08 | 24000 | 2025-08-08 | 24000
2506761 | Lee Swee Li | 34000 | 0 | Patricia | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 34000 | 34000 | 2025-06-23 | 1000 | 2025-06-23 | 1000 | 2025-09-16 | 33000 | 2025-09-16 | 33000
2506779 | Koo Hing Yew | 20500 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 20500 | 20500 | 2025-06-23 | 1000 | 2025-06-23 | 1000 | 2025-08-12 | 17500 | 2025-08-15 | 17500 | 2025-09-03 | 2000 | 2025-09-03 | 2000
2506781 | Teng Lily | 22000 | 0 | Patricia | R-PV | Credit Card Instalment | 2nd invoice | 2nd payment | 18500 | 18500 | 2025-06-22 | 1000 | 2025-06-22 | 1000 | 2025-08-27 | 17500 | 2025-08-27 | 17500
2506782 | Tan Shu Huat | 36100 | 0 | Patricia | R-PV | Cash + CC Instalment | Invoice Completed | Payment Completed | 36100 | 36100 | 2025-06-22 | 1000 | 2025-06-22 | 1000 | 2025-08-22 | 25000 | 2025-08-22 | 25000 | 2025-09-12 | 10100 | 2025-09-12 | 10100
2506746 | Tan Wan Ngee | 24000 | 0 | Patricia | R-PV | Cash | 1st invoice | 1st payment | 1000 | 1000 | 2025-06-23 | 1000 | 2025-06-23 | 1000
2506780 | Yeo Khai Boon | 23800 | 0 | Patricia | R-PV | Cash | 2nd invoice | 2nd payment | 21800 | 21800 | 2025-06-21 | 1000 | 2025-06-21 | 1000 | 2025-11-13 | 20800 | 2025-11-12 | 20800
2506778 | Teo Lun Wei | 20500 | 0 | Patricia | R-PV | Cash | 1st invoice | 1st payment | 1000 | 1000 | 2025-06-23 | 1000 | 2025-06-23 | 1000
2506745 | Lee Ban Hong | 32500 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 32500 | 32500 | 2025-06-15 | 1000 | 2025-06-15 | 1000 | 2025-08-05 | 29500 | 2025-08-22 | 29500 | 2025-08-23 | 2000 | 2025-08-23 | 2000
2506789 | Wu Sio Yunn | 27130 | 0 | Patricia | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 27130 | 27130 | 2025-06-24 | 1000 | 2025-06-24 | 1000 | 2025-08-19 | 10000 | 2025-08-20 | 10000 | 2025-08-22 | 16130 | 2025-08-22 | 16130
2404254 | Meor Farizal Bin Ramli | 19500 | 0 | Chean Bang | R-PV | Cash | Invoice Completed | Payment Completed | 19500 | 19500 | 2025-06-25 | 1000 | 2025-06-25 | 1000 | 2025-08-17 | 16000 | 2025-08-17 | 16000 | 2025-09-01 | 2500 | 2025-09-01 | 2500
2506732 | Chai Shwu Yi (Tan Lewin) | 20500 | 0 | Simon | R-PV | Cash | 2nd invoice | 1st payment | 18500 | 1000 | 2025-06-25 | 1000 | 2015-06-25 | 1000 | 2025-08-21 | 17500
2506767 | Lee Lee Tan @ Tan Lee Lee | 20500 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 20500 | 20500 | 2025-06-25 | 1000 | 2025-06-25 | 1000 | 2025-09-12 | 19500 | 2025-09-12 | 19500
2506759 | Yim Kai Mun | 27000 | 0 | Patricia | R-PV | Cash | 2nd invoice | 2nd payment | 25000 | 25000 | 2025-06-25 | 1000 | 2025-06-25 | 1000 | 2025-08-04 | 24000 | 2025-08-05 | 24000
2506794 | Ahmad Fadhil Bin Alias | 25000 | 0 | Patricia | R-PV | Cash | 2nd invoice | 2nd payment | 23000 | 23000 | 2025-06-26 | 1000 | 2025-06-26 | 1000 | 2025-10-02 | 22000 | 2025-10-07 | 22000
2506798 | Lew Sieow Shih | 20500 | 0 | Patricia | R-PV | Cash | 1st invoice | 1st payment | 1000 | 1000 | 2025-06-25 | 1000 | 2025-06-25 | 1000
2506773 | Leiw Chew Choi | 32500 | 0 | Patricia | R-PV | Cash | 1st invoice | 1st payment | 1000 | 1000 | 2025-06-26 | 1000 | 2025-06-26 | 1000
2506789-1 | Lim Kim Kiew | 20500 | 0 | Chean Bang | R-PV | Cash | Invoice Completed | Payment Completed | 20500 | 20500 | 2025-06-25 | 1000 | 2025-06-25 | 1000 | 2025-08-06 | 17500 | 2025-08-06 | 17500 | 2025-09-02 | 2000 | 2025-09-03 | 2000
2506786 | Lim Chee Seng | 30500 | 0 | Tham | R-PV | Cash | Invoice Completed | Payment Completed | 30500 | 30500 | 2025-06-29 | 1000 | 2025-06-29 | 1000 | 2025-08-22 | 29500 | 2025-08-22 | 29500
2505260 | Canning Garden Baptist Church | 95000 | 0 | Patricia | C&I-PV | Cash | 2nd invoice | 2nd payment | 42750 | 42750 | 2025-06-26 | 9500 | 2025-07-25 | 9500 | 2025-09-30 | 33250 | 2025-10-06 | 33250
2506799 | Lee Cheow Ban | 30500 | 0 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 30500 | 30500 | 2025-06-25 | 1000 | 2025-06-25 | 1000 | 2025-08-06 | 29500 | 2025-08-06 | 29500
2506276 | Tew Ah Sing @ Teo Ah Sing | 40000 | -1000 | Chean Bang | R-PV | Cash | Invoice Completed | Payment Completed | 39000 | 39000 | 2025-06-28 | 4000 | 2025-06-28 | 4000 | 2025-08-27 | 14000 | 2025-09-09 | 14000 | 2025-10-31 | 18000 | 2025-11-03 | 18000 | 2025-11-03 | 3000 | 2025-11-03 | 3000
2506785 | Mohd Nurazuwan Bin Radzi | 34500 | 0 | Patricia | R-PV | Cash | 1st invoice | 1st payment | 1000 | 1000 | 2025-06-29 | 1000 | 2025-06-29 | 1000
2506801 | Lim Joo Eng | 39500 | 0 | Patricia | R-PV | Credit Card Instalment | 1st invoice | 1st payment | 1000 | 1000 | 2025-06-29 | 1000 | 2025-06-29 | 1000
2503223 | Insultec Duragate Sdn Bhd | 117500 | 0 | Tham | C&I-PV | Cash | 2nd invoice | 2nd payment | 52875 | 52875 | 2025-08-08 | 11750 | 2025-08-28 | 11750 | 2025-09-26 | 41125 | 2025-10-07 | 41125
2506802 | Hung Wen Hao | 31500 | 0 | Patricia | R-PV | Cash | Pending 1st Invoice | Pending 1st Payment | 0 | 0
2412510 | How Toon Huah | 34000 | 0 | Chean Bang | R-PV | Credit Card Instalment | Invoice Completed | Payment Completed | 34000 | 34000 | 2025-06-30 | 1000 | 2025-07-05 | 1000 | 2025-08-27 | 33000 | 2025-08-27 | 33000
2504051 | G. Semanggol R&R (Northbound) - Green EV Charge Sdn Bhd | 250000 | 0 | Simon | EV Charger | Cash | Pending 1st Invoice | Pending 1st Payment | 0 | 0
2505056 | TMG Mall Tanjung Lumpur (Handal Green Mobility) | 43000 | 0 | Chean Bang | EV Charger | Cash | Invoice Completed | 1st payment | 43000 | 21500 | 2025-08-08 | 21500 | 2025-08-19 | 21500 | 2025-08-29 | 21500
2507833 | Yee Main Way | 46000 | 0 | Patricia | R-PV | Cash + CC Instalment | Invoice Completed | Payment Completed | 46000 | 46000 | 2025-08-05 | 6900 | 2025-08-05 | 6900 | 2025-10-16 | 39100 | 2025-10-17 | 39100
2409030 | TMG Mall Bandar Indera Mahkota (Handal Green Mobility) | 58000 | 0 | Chean Bang | EV Charger | Cash | Invoice Completed | 1st payment | 58000 | 29000 | 2025-08-13 | 29000 | 2025-08-19 | 29000 | 2025-08-29 | 29000
2507059 | TMG Mall IM16 (Handal Green Mobility) | 53000 | 0 | Chean Bang | EV Charger | Cash | Invoice Completed | 1st payment | 53000 | 26500 | 2025-08-13 | 26500 | 2025-08-19 | 26500 | 2025-08-29 | 26500
2507060 | TMG Mall Temerloh (Handal Green Mobility) | 55500 | 0 | Chean Bang | EV Charger | Cash | Invoice Completed | 1st payment | 55500 | 27750 | 2025-08-13 | 27750 | 2025-08-19 | 27750 | 2025-08-29 | 27750
2508858 | Chan Weng Leong | 49000 | 1593 | Patricia | R-PV | Cash | Invoice Completed | Payment Completed | 50593 | 50593 | 2025-09-24 | 10000 | 2025-08-26 | 10000 | 2025-09-12 | 10000 | 2025-09-12 | 10000 | 2025-10-11 | 15000 | 2025-10-11 | 15000 | 2025-10-30 | 14000 | 2025-10-30 | 14000 |  |  |  |  | 2025-10-30 | 1593 | 2025-10-30 | 1593
2507062 | Tapah R&R (Southbound) - Green EV Charge Sdn Bhd | 324360 | 0 | Simon | EV Charger | Cash | 1st invoice | 1st payment | 153000 | 153000 | 2025-09-09 | 153000 | 2025-09-22 | 153000
2509863 | Goh Soon Teck | 27000 | 0 | Patricia | R-PV | Cash | 1st invoice | 1st payment | 1000 | 1000 | 2025-10-27 | 1000 | 2025-09-29 | 1000
2507840 | Chew Kok leong | 63000 | 0 | Patricia | R-PV | Cash + CC Instalment | 1st invoice | 1st payment | 6300 | 6300 | 2025-10-27 | 6300 | 2025-09-29 | 6300
2508857 | Chong Horng Tat | 49800 | 0 | Ong | R-PV | Cash | 2nd invoice | 2nd payment | 44800 | 44800 | 2025-10-10 | 4980 | 2025-10-10 | 4980 | 2025-11-17 | 39820 | 2025-11-13 | 39820
2305008 | Yeap Chooi Hock | 63773.58 | 0 | Patricia | C&I-PV | Cash + CC Instalment | 1st invoice | 1st payment | 6226.41 | 6226.41 | 2025-10-28 | 6226.41 | 2025-10-28 | 6226.41
2508856 | Eddie Leong Kai Sheng | 73500 | 0 | Ong | R-PV | Cash | 1st invoice | 1st payment | 7350 | 7350 | 2025-10-28 | 7350 | 2025-10-28 | 7350
2510877 | Wang Pay Chen | 28500 | 0 | Patricia | R-PV | Cash | 1st invoice | 1st payment | 1000 | 1000 | 2025-11-03 | 1000 | 2025-11-03 | 1000
2511887 | Lee Hang Meng | 29000 | 0 | Patricia | R-PV | Cash | 1st invoice | 1st payment | 1000 | 1000 | 2025-11-09 | 1000 | 2025-11-09 | 1000
2305019 | Soe Yew Seng | 60000 | 0 | Simon | R-PV | Cash | 1st invoice | 1st payment | 1000 | 1000 | 2025-10-30 | 1000 | 2025-10-30 | 1000
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 5000 | 5000 | 2026-07-01 | 5000 | 2026-07-02 | 5000
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 500000 | 500000 | 2026-07-01 | 500000 | 2026-07-02 | 500000
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 50000 | 50000 | 2026-07-01 | 50000 | 2026-07-02 | 50000
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0

## Insurance Tracker
[10 empty] | 1st Year |  |  | 2nd Year |  |  | 3rd Year |  |  | 4th Year
Project No | Client Name | I/C | Installation Address | Phone Number | Email | Project Value | Category | System Capacity | Insurance Warranty | Insurance Provider | Policy Number | Date of Policy | Insurance Provider | Policy Number | Date of Policy | Insurance Provider | Policy Number | Date of Policy | Insurance Provider | Policy Number | Date of Policy
2303005 | Wong Kim Mei | 731013-10-5784 | No. 24, Jalan Seri Muka 36/27A, Taman Menegun Indah, 41000 Klang, Selangor. | 016-335 4884 | wongkimmei73@gmail.com | 32000 | R-PV | 8.05 | 5 years | MSIG | KN-11241957-ARH | 2023-12-05 | Allianz | 24AKG0004435-00 | 2024-11-28
2303006 | Ang Ching Ming | 931003-10-6105 | 1, Jalan Ulek Mayang 2C/KU5, Bandar Bukit Raja, 41050 Klang, Selangpr | 017-9666099 | cmang_02@outlook.com | 40000 | R-PV | 12.65 | 1 year | Allianz | 25AKG0000970-00 | 2025-04-03
2304016 | Tan Sei Choon | 650818-06-5287 | 2, Lorong Bukit Setongkol Perdana 52, Taman Fairmont Jaya, 25200 Kuantan, Pahang. | 016-922 3868 | tesoon12@gmail.com | 31000 | R-PV | 8.05 | 5 years | MSIG | KN-11241950-ARH | 2023-12-05 | Allianz | 24AKG0004436-00 | 2024-11-28
2305021 | Ho Hon Kit | 670422-10-5607 | No 32, Jalan Puteri 12/7, Bandar Puteri, 47100 Puchong, Selangor. | 012-3979968 | hkho@trident-x.com | 20000 | R-PV | 4.65 | 5 years | MSIG | KN-11241942-ARH | 2023-12-05 | Allianz | 24AKG0004431-00 | 2024-11-28
2305026 | Stanley Ang Leng Chuan | 751007-10-5671 | 5, Jalan Bidara 9, Bandar Botanic, 41200 Klang, Selangor. | 016-6767999 | stanleyang9@gmail.com | 40000 | R-PV | 12.65 | 1 year | MSIG | KN-11241931-ARH | 2023-12-05 | N/A |  |  | N/A |  |  | N/A
2306033 | Foo Tuang Lee | 741128-01-5075 | No 20, Jln Pelangi 15, Tmn Pelangi, 86000 Kluang, Johor | 016-2368221 | ericfoo8888@gmail.com | 16000 | R-PV | 4.65 | N/A | N/A | N/A |  | N/A | N/A |  | N/A |  |  | N/A
2306037 | Tan Hong Guan | 680512-07-5359 | No 6, Pinggir Bukit Segar 2, Tmn Bkt Segar, 56100 Cheras, Kuala Lumpur | 012-4380246 | hongguan.tan@gmail.com | 36575 | R-PV | 10.925 | N/A | N/A | N/A |  | N/A | N/A |  | N/A |  |  | N/A
2307040 | Law Soo Chin | 640407-07-5713 | 6, Jalan BS 3/8, Taman Bukit Serdang, 43300 Seri Kembangan, Selangor. | 016-2013221 | lawsc123@hotmail.com | 40000 | R-PV | 12.65 | 3 years | MSIG | KN-11241903-ARH | 2023-12-05 | Allianz | 24AKG0004425-00 | 2024-11-28
2305011 | Kossan FRP Marketing (M) Sdn Bhd | - | PT 2019, Jln Keretapi Lama Off, Jln Kapar, BT 4 3/4, Kg Rantau Panjang, 42100 Klang, Selangor | - | - | 242000 | C&I-PV | 283.945 | N/A | N/A | N/A |  | N/A | N/A |  | N/A |  |  | N/A
2304007 | MTJ Development Sdn Bhd (Intercontinental KL) | - | No 165, Jln Ampang, 50450 Kuala Lumpur, WP Kuala Lumpur | - | - | 188800 | C&I-PV | 51.75 | 3 years | Tokio Marine | GAS-G0154270-WB-AGY-24 | 2024-11-29
2307042 | Dato' Sri Ng Chong Keong | 650309-08-5407 | 9, Lorong Tok Sira 4, Taman Melor, 25050 Kuantan, Pahang. | 016-9907409 | ng_xinnee@hotmail.com | 50000 | R-PV | 16.1 | 5 years | MSIG | KN-11241896-ARH | 2023-12-05 | Allianz | 24AKG0004426-00 | 2024-11-28
2308058 | Cheong Yik Yin | 950710-14-6004 | No. 18, Jalan Setia Utama U13/39D, Setia Alam, Seksyen U13, 40170 Shah Alam, Selangor. | 016-6530107 | yikyin_cheong@hotmail.com | 30000 | R-PV | 6.9 | 3 years | MSIG | KN-11241868-ARH | 2023-12-05 | Allianz | 24AKG0004430-00 | 2024-11-28
2308062 | Lim Chin Joo | 6905020-02-5211 | 8, Jln BK 6A/2A, Bandar Kinrara, 47100 Puchong, Selangor Darul Ehsan | 012-6151020 | chinjoolim@gmail.com | 42300 | R-PV | 12.65 | 3 years | Allianz | 24AKG0003782-00 | 2024-10-03
2309068 | Kee Siew Chuan (Ngo Woon Wah) | 730119-08-5342 | No 12-A, Lrg Bukit Setongkol Jaya 32, Bkt Setongkol, 25200, Kuantan, Pahang Darul Makmur | 019-9631028 | siewchuan639@gmail.com | 28500 | R-PV | 6.9 | 5 years | Allianz | 24AKG0003783-00 | 2024-10-03
2310078 | Lee Nyok Cheng | 581227-05-5427 | No. 1, Lorong IM 1/62, Perumahan Indera Mahkota 1, 25200 Kuantan, Pahang. | 016-9221189 | songlee1188@gmail.com | 52000 | R-PV | 16.1 | 5 years | MSIG | KN-11241886-ARH | 2024-12-05 | Allianz | 24AKG0004427-00 | 2024-11-28
2310083 | Ong Eng Guan | 451011-02-5493 | No. 9 Lorong Im 11/12, Mahkota Heights, 25200 Kuantan, Pahang Darul Makmur | 012-9853289 | daniel_8632@yahoo.com | 31000 | R-PV | 8.05 | 5 years | Allianz | 24AKG0003784-00 | 2024-10-03
2310084 | Chia Le Chin | 730219-06-5090 | No 11, Lorong Im 11/12, Mahkota Heights, 25200 Kuantan, Pahang Darul Makmur | 013-9318778 | health_trading@yahoo | 34000 | R-PV | 8.05 | 5 years | Allianz | 24AKG0003787-00 | 2024-10-03
2305024 | Beh Poh Loh | 890620-06-5065 | No 10, Lorong Peramu Jaya 1/3, Perumahan Peramu Jaya 1, 26060 Kuantan, Pahang Darul Makmur | 016-9862270 | graybackboy@hotmail.com | 42500 | R-PV | 12.65 | 5 years | Allianz | 24AKG0003788-00 | 2024-10-03
2307052 | Ngoh Win Nee | 851017-06-5456 | No 49, Lrg Tiram Jaya 5, Perumahan Tiram Jaya, 25200 Kuantan, Pahang | 012-9860700 | winneengoh@gmail.com | 22100 | R-PV | 4.6 | 5 years | Project Cancelled
2304010 | Tung Seng Chang | 720703-10-5665 | 18, Jalan Setia Perdana U13/29C, Setia Alam, 40170 Shah Alam, Selangor | 019-2933333 | tungsc6@gmail.com | 20650 | R-PV | 13.625 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2308065 | Pua Hock Meng | 830524-06-5271 | No. 18, Lorong Peramu Jaya 1/2, Perumahan Peramu Jaya 1, 26060 Kuantan, Pahang Darul Makmur | 019-9956536 | prinze.pua@gmail.com | 33000 | R-PV | 8.625 | 5 years | Allianz | 25AKG0000971-00 | 2025-04-03
2306009 | Dato Arif Stephen bin Abdullah | 0 | Lot 12193, Jalan Felcra Semungkis, Batu 14 Hulu Langat, 43100 Hulu Langat, Selangor Darul Ehsan | 0 | 0 | 720000 | R-BESS | 85.1 | 0 | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2303003 | Greenlast Housing Development Sdn Bhd | - | Lot 1-5, Jalan Semambu,Kawasan Perindustrian Semambu, Kuantan Pahang 25350 Malaysia | - | - | 80000 | C&I-PV | 23 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2311040 | DBTS Industries Sdn Bhd | - | Lot 2199, Jalan Nuri, Kampung Batu 9 Kebun Baru, 42500 Telok Panglima Garang, Selangor | - | - | 91000 | C&I-PV | 93 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2308007 | EV Connection Sdn Bhd (The Pines Melaka) | 0 | 33, Jalan Tun Sri Lanang, 75100 Melaka | 0 | 0 | 93380 | EV Charger | 0 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2311094 | Ching Kok Keong | 670428-11-5021 | Lot 10997, Jln Kenanga, Kg Sura Jeti, 23000 Dungun, Terengganu Darul Iman | 017-9767388 | ckkcsk6666@gmail.com | 37000 | R-PV | 9.775 | 3 years | Allianz | 24AKG0003789-00 | 2024-10-03
2311095 | Chu Yin Siong | 620818-11-5371 | No 11, Jln Paka, Tmn Bunga Raya, 23000 Dungun, Terengganu Darul Iman | 019-9836811 | cca6668@gmail.com | 44600 | R-PV | 12.65 | 3 years | Allianz | 24AKG0003790-00 | 2024-10-03
2311039 | DC Handal EV Charging Hub | - | - | - | - | 280080 | C&I-PV | 370.055 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2311012 | EV Connection Sdn Bhd (IOI Citymall, Putrajaya) | - | - | - | - | 109000 | EV Charger | 0 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2311089 | Susan Lau Shiew Hung | 821226-13-5150 | 27, Jalan SS 22A/8, Damansara Jaya, 47400 Petaling Jaya, Selangor Darul Ehsan | 012-2777019 | san99lau@gmail.com | 37500 | R-PV | 11.5 | 3 years | Allianz | 24AKG0003791-00 | 2024-10-03
2312118 | Dr Suntheresan A/L Ganapathy | 680926-02-5351 | No 27, Jalan Aman Elemen 3, Bandar Tropicana Aman, 42500 Telok Panglima Garang, Selangor Darul Ehsan | 019-2262119 | sunthe26@gmail.com | 54930 | R-PV | 13.8 | 3 years | Allianz | 24AKG0003792-00 | 2024-10-03
2309070 | Saiful Lizan Bin Ibrahim | 731112-06-5749 | 16, Jalan Suadamai 6/2, Bandar Tun Hussein Onn, 43200 Cheras, Selangor Darul Ehsan | 019-2611759 | gunner2490@yahoo.com | 48902 | R-PV | 13.8 | 3 years | Allianz | 24AKG0003793-00 | 2024-10-03
2310075 | Chong Fong Chin(Jessie) | 861207-33-5276 | No 11, Lrg Bkt Setongkol Perdana 29, Perkpgn Bkt Setongkol, Tmn Bukit Setongkol, 25200 Kuantan, Pahang Darul Makmur | 019-9351188 | jessie.cfc@gmail.com | 45600 | R-PV | 14.625 | 0 | Project Cancelled
2310076 | Loo Thiam Seng | 560426-07-5479 | 61, Jln Tasik Indah 2, Tmn Tasik Indah, 51200 WP Kuala Lumpur | 019-2263229 | tsloo1956@gmail.com | 24000 | R-PV | 8.26 | 3 years | Allianz | 25AKG0001669-00 | 2025-05-29
2310085 | Chew Mei May | 721025-10-5598 | 67, Jln BK 5B/5A, Bdr Kinrara, 47180 Puchong, Selangor Darul Ehsan | 012-2203402 | meimaychew@gmail.com | 47786 | R-PV | 12.075 | 3 years | Allianz | 24AKG0003795-00 | 2024-10-03
2312113 | Razman Bin Samsudin | 760713-71-5025 | No.8, Jalan SS20/25, Damansara Utama, 47400 Petaling Jaya, Selangor | 019-3371313 | razmanbinsamsudin@gmailcom | 44000 | R-PV | 13.8 | 3 years | Allianz | 25AKG0001709-00 | 2025-05-29
2401121 | Chen Ah Hin | 480824-10-5119 | Lot 1325-79B, Jalan Jinjang Damai 7, JinJang Utara, 52000 Kuala Lumpur | 019-3281707 | chen2.luma@gmail.com | 40000 | R-PV | 11.7 | 3 years | Allianz | 24AKG0003796-00 | 2024-10-03
2401124 | Lim Kok Teong | 790418-07-5747 | 3 Jalan Kenyalang 11/4E, PJU 5, Kota Damansara, 47810 Petaling Jaya, Selangor Darul Ehsan | 019-4134865 | cmjasonlim311@gmail.com | 53708 | R-PV | 17.55 | 3 years | Allianz | 24AKG0003797-00 | 2024-10-03
2401131 | Chan Po Kok (JC Chan KEB) | 830506-14-6019 | 16, Jalan Sunville 4, Taman Sunville, 43000 Kajang, Selangor Darul Ehsan | 017-8786050 | cpokok0506@hotmail.com | 29500 | R-PV | 8.19 | 3 years | Allianz | 24AKG0003798-00 | 2024-10-03
2401137 | Lim Kok Liang | 830112-02-5169 | 1, Jalan Metafasa, U16/160. Elmina West, Seksyen U16, 40160, Shah Alam , Selangor Darul Ehsan | 016-2173777 | steelmerchantssb@gmail.com | 40900 | R-PV | 11.7 | 3 years | Allianz | 24AKG0003799-00 | 2024-10-03
2401147 | Susan Sung Fong Thieng | 691205-12-5030 | 37, Southlake Terraces, Jalan Denai Selatan 5, Desa Parkcity. 52200 Kuala Lumpur | 012-2393003 | susansung37@gmail.com | 40440 | R-PV | 11.7 | 3 years | Allianz | 24AKG0003800-00 | 2024-10-03
2403165 | Lee Boon Huet | 720825-05-5109 | 31, Jln Cassia 4, Bdr Botanic, 41200 Klang, Selangor Darul Ehsan | 012-2045618 | blee@fp-group.com | 24600 | R-PV | 7.02 | 3 years | Allianz | 24AKG0003801-00 | 2024-10-03
2403167 | Ng Yunn Chong | 620205-08-6037 | 97, Jalan Selasar Rokam 11, Kampung Sri Ampang, 31350 Ipoh, Perak Darul Ridzuan | 012-5127295 | ngyunnchong123@gmail.com | 47500 | R-PV | 17.55 | 3 years | Allianz | 24AKG0003802-00 | 2024-10-03
2403170 | Wong Hoon Sang | 630220-10-7149 | 75, Jalan Uranus U5/122B, Seksyen U5, 40150 Shah Alam. Selangor Darul Ehsan | 014-9159789 | wonghoonsang@gmail.com | 35600 | R-PV | 10.53 | 3 years | Allianz | 24AKG0003803-00 | 2024-10-03
2403177 | Nor Aini binti Mohd Ashari | 731105-08-6402 | No 61, Jln Sigma U6/16A, Sek U6 (Taman Subang Permata), 40150 Subang, Selangor Darul Ehsan | 011-28584486 | norazam4446@yahoo.com.sg | 20000 | R-PV | 4.68 | 3 years | Allianz | 24AKG0003804-00 | 2024-10-03
2403189 | Lai Kim Soon (Stella) | 910301-06-5675 | No 36, Lrg Seri Teruntum 13, Tmn Sri Teru, Tanah Putih, 25200 Kuantan. Pahang Darul Makmur | 011-55090155 | miiao_maomao520@hotmail.com | 27500 | R-PV | 7.02 | 3 years | Allianz | 24AKG0003805-00 | 2024-10-03
2403190 | Tan Poh Poh | 710625-08-5224 | 6, Lrg Seri Setali, 115 Off Jln Air Putih, Air Putih, 25300 Kuantan, Pahang Darul Makmur | 012-9831939 | may014215@gmail.com | 21000 | R-PV | 7.02 | 3 years | Allianz | 24AKG0003806-00 | 2024-10-03
2403197 | Leau Koo Sien (Eric) | 740722-06-5097 | No 12A, Lorong Pelindung 95, Perumahan Pelindung, 25050 Kuantan, Pahang Darul makmur | 019-9270778 | Leaueric@gmail.com | 48600 | R-PV | 16.38 | 3 years | Project Cancelled
2403197-1 | Koon Kok Leong | 741008-01-5759 | No 80, Lrg Delima 5/KS6, Bdr Parklands, Pandamar, 42000 Klang, Selangor Darul Ehsan | 012-3988909 | klkoon8882@gmail.com | 27237.2 | R-PV | 7.02 | 3 years | Allianz | 24AKG0003807-00 | 2024-10-03
2404206 | Wong Wai Kwong | 790114-06-5467 | No 55, Lrg Im 1/41, Tmn Putra Aman, 25200 Bandar Indera Mahkota, Pahang Darul Makmur | 016-9233066 | ww_kwong@yahoo.com.sg | 31000 | R-PV | 8.19 | 3 years | Allianz | 24AKG0003808-00 | 2024-10-03
2404226 | Jimmy Kok Aik Lim | 621013-11-5109 | 3 Jalan Telawi 7, Bangsar Baru, Bangsar,59100 Kuala Lumpur, WP Kuala Lumpur | 012-3709905 | lytan63@hotmail.com | 25100 | R-PV | 7.02 | 3 years | Allianz | 24AKG0003809-00 | 2024-10-03
2401063 | Weller Air-Cond Parts Enterprise Sdn Bhd | 0 | Lot 8324, Kg Makau Bt 1, 43100 Hulu Langat, Selangor | 0 | 0 | 82000 | C&I-PV | 26.91 | 3 years | Tokio Marine | GAS-G0167581-WB-AGY-25 | 2025-08-21
2401069 | Enviri Industries Sdn Bhd | 0 | PT71179, Jalan Lapis 2, 42100 Klang, Selangor | 0 | 0 | 668000 | C&I-PV | 290.4 | 3 years
2402079 | Intergreen Holdings Sdn Bhd | 0 | Pusat Perdagangan Amcorp, 3, Jalan Timur, Seksyen 9, 46000 Petaling Jaya, Selangor | 0 | 0 | 194600 | C&I-PV | 46.8 | 3 years
2402080 | CK Fresh Sdn Bhd | 0 | Lot 8393, Jln Air Hitam, Kelapa Sawit, 81000 Kulai, Johor | 0 | 0 | 120000 | C&I-PV | 43.29 | 3 years
2312120 | Ling Duon Kwan | 780817-13--5437 | No 58, Jln TP 1/3, Tiara Putra, 47000 Sungai Buloh, Selangor Darul Ehsan | 012-3799638 | duncanling@yahoo.com | 27500 | R-PV | 7.605 | 3 years | Allianz | 24AKG0003810-00 | 2024-10-03
2311092 | Tham Chee Man | 590601-06-5153 | 33, Jalan Flora 3, Saujana Utama, 47000 Sungai Buloh, Selangor Darul Ehsan | 017-9034540 | thamcheongsheng@gmail.com | 22000 | R-PV | 5.75 | 3 years | Allianz | 24AKG0003811-00 | 2024-10-03
2404230 | Yap Bee Im Marianne | 831021-14-6242 | No 8, Jln Hijau Alam U9/14C, Cahaya SPK, Sek U9, 40150 Shah Alam, Selangor Darul Ehsan | 012-3050288 | marianneyap21@gmail.com | 32500 | R-PV | 8.775 | 3 years | Allianz | 24AKG0003812-00 | 2024-10-03
2401133 | Cheong Sau Ling | 740823-02-5825 | 15, Jalan Kemuning Bayu 33/32L, Kemuning Utama,40400 Shah Alam, Selangor Darul Ehsan | 013-7274135 | lingling822@hotmail.my | 34460 | R-PV | 8.775 | 3 years | Allianz | 24AKG0003813-00 | 2024-10-03
2403171 | Sim Keng Chor | 470725-01-5629 | 8, Lorong Kemaris 6, Bangsar Baru, 59100 Kuala Lumpur, WP Kuala Lumpur | 012-2789488 | simson@unitrade.com.my | 52400 | R-PV | 17.55 | 3 years | Allianz | 24AKG0003815-00 | 2024-10-03
2403176 | Nor Hana binti Supiran @ Soviran | 801003-08-5944 | Lot 84327, Lorong Merbau 1, Kampung Melayu, 68000 Ampang, Selangor Darul Ehsan | 019-3170725 | hanatrading78@yahoo.com | 30500 | R-PV | 6.435 | 3 years | Allianz | 24AKG0003816-00 | 2024-10-03
2404229 | Ng Lay Ping | 700919-10-5236 | Lot 27838, Jln BRP 2/2C, Bkt Rahman Putra, 40160 Sungai Buloh, Selangor Darul Ehsan | 012-3999903 | lpng_lew@yahoo.com | 41600 | R-PV | 14.625 | 3 years | Allianz | 24AKG0003817-00 | 2024-10-03
2404211 | Nor Fadillah | 630327-04-5398 | 17, Jalan Laman Jasmin 5A, Laman Jasmin, 71800 Nilai Negeri Sembilan Darul Khusus | 016-2477797 | drnorfadillah@gmail.com | 49600 | R-PV | 17.55 | 3 years | Allianz | 24AKG0003818-00 | 2024-10-03
2404111 | Budi Jelas Sdn Bhd | 0 | PT 12887, Kaw Asan Perindustrian LKNP Benus, 28700 Bentong, Pahang | 0 | 0 | 81000 | C&I-PV | 26.91 | 3 years | Tokio Marine | GAS-G0167670-WB-AGY-25 | 2025-08-21
2404219 | Billy Teoh Wee Wei | 830811-07-5405 | No 5082, Lrg Bagan Vista, Jln Telaga Air, 12200 Butterworth Pulau Pinang | 012-4215656 | billyteoh19@hotmail.com | 52000 | R-PV | 17.55 | 3 years | Allianz | 24AKG0003819-00 | 2024-10-03
2404214 | Teo En Chie | 910530-01-6505 | 18, Jalan Senibong 1, Teluk Senibong, 81750 Masai, Johor Darul Takzim | 010-8820636 | enchie@live.com.my | 48200 | R-PV | 15.795 | 3 years | Allianz | 24AKG0003820-00 | 2024-10-03
2403102 | Sleep Matics (Asia) Sdn Bhd | 0 | Lot 37133, Kg Baru Sg Buloh, 47000 Sungai Buloh, Selangor | 0 | 0 | 744800 | C&I-PV | 374.4 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2312059 | CHL Foam Industries Sdn Bhd | 0 | Lot 37174, Kg Baru Sg Buloh, 47000 Sungai Buloh, Selangor | 0 | 0 | 690300 | C&I-PV | 345.15 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2404255 | Ong Pui Fen | 760801-04-5180 | 51, Jalan USJ 2/5H, USJ 2, 47600 Subang Jaya, Selangor Darul Ehsan | 016-2100039 | tattmun@gmail.com | 30260 | R-PV | 7.605 | 3 years | Allianz | 24AKG0003821-00 | 2024-10-03
2404242 | Chua Boon Seng | 750927-06-5137 | No 1B, Lrg Seri Kuantan 28/1, Kuantan Garden, 25300 Kuantan, Pahang Darul Makmur | 018-9094538 | cboonhuang@gmail.com | 35000 | R-PV | 10.53 | 3 years | Allianz | 24AKG0003822-00 | 2024-10-03
2405272 | Chan Hui Li | 700521-06--5318 | No 111, Lrg Air Putih 21, Jln Air Putih, Tmn Dahlia Astana, 25350 Kuantan, Pahang Darul Makmur | 012-2392000 | conniechan2105@yahoo.com | 32180 | R-PV | 9.36 | 3 years | Allianz | 24AKG0003823-00 | 2024-10-03
2405266 | Goh Wee Bang (Goh Swee Teng) | 750605-10-5255 | No 12A, Jln Cokmar 2 K, Tmn Mutiara Bkt Raja, 41050 Klang, Selangor Darul Ehsan | 012-2313922 | vbangoh1975@gmail.com | 41000 | R-PV | 13.455 | 3 years | Allianz | 24AKG0003824-00 | 2024-10-03
2405280 | Teoh Kah Ming | 880326-14-5807 | No 5, Jln Kemuning Indah 32/141J, Kemuning Utama, 40460 Shah Alam, Selangor Darul Ehsan | 012-6777309 | kahming.teoh@gmail.com | 34600 | R-PV | 9.36 | 3 years | Allianz | 24AKG0003825-00 | 2024-10-03
2405294 | Gan Wei Kuan | 0 | 0 | 0 | 0 | 25100 | 0 | 7.02 | 3 years | Project Cancelled
2405296 | Haiu Chan Lai | 670120-11-5324 | 41, Jln Daun Inai 7, Sunway SPK Damansara, 52200 Kuala Lumpur, WP Kuala Lumpur | 012-3760333 | jacquelinehaiu@gmail.com | 32000 | R-PV | 8.775 | 3 years | Allianz | 25AKG0000972-00 | 2025-04-03
2405307 | Shreeram Nadarajah | 760726-14-5391 | 123, Jalan Terasek 1, Bangsar Baru, Bangsar, 59100 Kuala Lumpur, WP Kuala Lumpur | 019-2619729 | shreeram.nadarajah@gmail.com | 28000 | R-PV | 8.19 | 1 year | Allianz | 24AKG0003826-00 | 2024-10-03 | N/A | N/A |  | N/A |  |  | N/A
2404227 | Datin Tai Bee Choon | 760817-01-5584 | No 16, Jln Setia Tropika 15/1, Tmn Setia Tropika, 81200 Johor Bahru. Johor Darul Takzim | 013-8222255 | datoivan@ungguhgroup.com | 52400 | R-PV | 17.55 | 3 years | Allianz | 25AKG0000973-00 | 2025-04-03
2405315 | Yeap Say Woei | 800117-02-5697 | 10, Bukit Dumbar Residences, Lorong Batu Gajah, 11600 Jelutong, Pulau Pinang | 012-4776246 | saywoei@yahoo.com | 40000 | R-PV | 13.455 | 3 years | Allianz | 24AKG0003839-00 | 2024-10-03
2405319 | Tan Zhi Cheng | 840518-09-5203 | 15, Jalan BK 2/7, Bandar Kinrara, 47180 Puchong, Selangor Darul Ehsan | 016-4010372 | tzcheng07@gmail.com | 26240 | R-PV | 7.02 | 3 years | Allianz | 24AKG0003827-00 | 2024-10-03
2405288 | Teh Siew Eng | 531030-08-5440 | No 49, Jln Kasipillay, 51200 Kuala Lumpur, WP Kuala Lumpur | 012-2290951 | fattychuah@gmail.com | 41840 | R-PV | 12.285 | 3 years | Allianz | 24AKG0003828-00 | 2024-10-03
2404256 | Lai Chun Wai | 711015-14-5159 | No 31, Lrg Sri Kuantan 55, Tmn Timur, 25150 Kuantan, Pahang Darul Makmur | 012-3879932 | chunwai103@gmail.com | 33100 | R-PV | 8.775 | 3 years | Allianz | 25AKG0000974-00 | 2025-04-03
2406323 | Tay Poh Chai | 730209-04-5037 | 53, Jalan Saujana Duta 7, Saujana Duta, Seremban 2 Heights, 70300 Seremban, Negeri Sembilan Darul Khusus | 019-6616826 | alextaypohchai@hotmail.com | 40000 | R-PV | 14.04 | 3 years | Allianz | 24AKG0003829-00 | 2024-10-03
2406336 | Alex How Chee Keong | 770202-14-5437 | Unit 16, Zenia Jalan Residen 2, Desa Parkcity, 52200 Kuala Lumpur, WP Kuala Lumpur | 012-3453457 | keongko@hotmail.com | 31000 | R-PV | 11.7 | 1 year | Allianz | 24AKG0003830-00 | 2024-10-03 | N/A | N/A |  | N/A |  |  | N/A
2406340 | How Mei Cheng | 811203-14-5656 | 2-134, Jalan Udang Ketak, Taman Sri Segambut, 52000 Kuala Lumpur, WP Kuala Lumpur | 012-2012123 | joe_hmc@hotmail.com | 24100 | R-PV | 7.02 | 3 years | Allianz | 24AKG0003831-00 | 2024-10-03
2406355 | Windy Ng | 820717-01-5204 | 13, Jalan U13/53H, Eco Ardence, Seksyen U13, 40170 Shah Alam, Selangor Darul Ehsan | 017-7753119 | yellowwindy@hotmail.com | 27000 | R-PV | 9.36 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2406357 | Zainuddin Zin | 590911-06-5319 | 8, Lrg Kg Panching 10, Kg Panching, 26090 Kuantan, Pahang Darul Makmur | 019-9774850 | zainudinzin@gmail.com | 38000 | R-PV | 12.285 | 5 years | Allianz | 24AKG0003832-00 | 2024-10-03
2405019 | Handal Green Mobility Sdn Bhd (Encore Melaka) | - | No 3, Jalan KSB - Impression 8, Impression City @ Kota Syahbandar, 75200 Melaka | - | - | 90800 | EV Charger | 0 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2406358 | Kwan Li Shan | 800718-08-5978 | Lot 387509, Laluan Sri Ampang 2, Kampung Sri Ampang, 31350 Ipoh, Perak Darul Ridzuan | 012-5142483 | lishankwan@gmail.com | 30000 | R-PV | 9.36 | 3 years | Allianz | 24AKG0003842-00 | 2024-10-03
2407360 | Liau Hui Kiem | 780419-10-5734 | 20, Jalan Setia Damai U13/15F, Setia Alam 40170 Shah Alam, Selangor Darul Ehsan | 019-2338688 | hkliau8688@gmail.com | 45020 | R-PV | 14.04 | 3 years | Allianz | 24AKG0003833-00 | 2024-10-03
2407364 | Mohd Nasir Man | 640103-09-5029 | No B3075, Jln Beserah, Tmn Multiply, 25300 Kuantan, Pahang Darul Makmur | 012-9003767 | mnasirman17@gmail.com | 25000 | R-PV | 8.19 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2407375 | Tan Ger Ber | 560608-01-6090 | 10, Jalan Kenyalang 11/15G, Seksyen 11, Kota Damansara, 47810, Petaling Jaya, Selangor Darul Ehsan | 012-5273664 | tangerber@gmail.com | 39980 | R-PV | 14.04 | 3 years | Allianz | 24AKG0003834-00 | 2024-10-03
2407379 | Ng Boon Kiat (Daniel) | 840903-01-5679 | No 4, Jalan KS 14/12, Kota Sultan Ahmad Shah, 25200 Kuantan, Pahang | 012-6121112 | danielngbk84@gmail.com | 22860 | R-PV | 5.265 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2407380 | How Yee Seun | 840202-06-5008 | 32A, Jalan Aman Arahsia 7, Bandar Tropicana Aman, 42500 Telok Panglima Garang, Selangor Darul Ehsan | 012-9370766 | yeesuen02@yahoo.com | 38000 | R-PV | 12.87 | 3 years | Allianz | 24AKG0003835-00 | 2024-10-03
2407381 | Lau Ah Leng | 550425-02-5403 | 19, Jln Kenyalang 11/15I, Seksyen 11, Kota Damansara, 47810 Petaling Jaya, Selangor Darul Ehsan | 019-3128863 | allan@gmail.com | 36680 | R-PV | 12.285 | 3 years | Allianz | 25AKG0000975-00 | 2025-04-03
2407382 | Leong Tack Ming | 530501-05-5607 | 3, Jalan SS 22/24, Damansara jaya. 47400 Petaling Jaya, Selangor | 012-2011132 | 0 | 29840 | R-PV | 8.775 | 3 years | Allianz | 25AKG0001008-00 | 2025-04-03
2407383 | Charles Lew Chow Leng | 620529-07-5406 | 6, Jalan Kenyalang 11/15A, Seksyen 11, Kota Damansara, 47810 Petaling Jaya, Selangor Darul Ehsan | 012-3999189 | clew62@gmail.com | 39980 | R-PV | 14.04 | 3 years | Allianz | 24AKG0003836-00 | 2024-10-03
2407384 | Loh Fook Khew | 560512-08-5307 | 8, Jalan Kenyalang 11/15A, Seksyen 11, Kota Damansara, 47810 Petaling Jaya, Selangor Darul Ehsan | 012-3351801 | chinmei_fashion@hotmail.com | 36800 | R-PV | 12.285 | 3 years | Allianz | 24AKG0003837-00 | 2024-10-03
2407385 | Cheong Chin Meng | 730422-06-5301 | 145, Jln Bkt Setongkol 3, Tmn Muhibah FAS, Bukit Setongkol, 25200 Kuantan, Pahang Darul Makmur | 012-9103893 | ioienterprisektn@gmail.com | 45600 | R-PV | 15.21 | 3 years | Allianz | 24AKG0003843-00 | 2024-10-03
2310035 | Advantic Nutraceuticals | 0 | 0 | 0 | 0 | 188000 | C&I-PV | 87.84 | 3 years
2403088 | Chua Tong Hin Hardware Sdn Bhd | 0 | Lot 37679, Jln 3/37A, Tmn Bukit Maluri Kepong, 52100 Kuala Lumpur | 0 | 0 | 98000 | C&I-PV | 37.44 | 3 years | Tokio Marine | GAS-G0167589-WB-AGY-25 | 2025-08-21
2407157 | NMSY Capital Sdn Bhd (Mohd Nasir) | 0 | N-1332, G Floor, Jln Tg Lumpur, 26060 Kuantan, Pahang | 0 | 0 | 52000 | C&I-PV | 18.72 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2312116 | Chua Ling Ling | 760115-14-5448 | 132A, Jln Desa Residen, Desa Parkcity, 52200 Kuala Lumpur, WP Kuala Lumpur | 011-11428999 | llchua00@hotmail.com | 32540 | R-PV | 11.7 | 1 year | Allianz | 25AKG0000976-00 | 2025-04-03
2407388 | Yeo Chen Kok | 830625-07-5049 | 10, Jln Hujan Emas 11, Overseas Union Garden, 58200 Kuala Lumpur, WP Kuala Lumpur | 012-9283828 | yeochenkok@gmail.com | 34600 | R-PV | 12.285 | 3 years | Allianz | 25AKG0000977-00 | 2025-04-03
2407386 | Amirluddin bin Awang | 671111-11-5079 | No 8, Lorong Im 11/10, Mahkota Heights, 25200 Kuantan, Pahang Darul Makmur | 012-7992686 | tidzariah@gmail.com | 38000 | R-PV | 12.285 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2403158 | Ong Gin Chin | 600218-01-5432 | 9, Jalan Anggerik Liparis 31/152, Kota Kemuning, 40460 Shah Alam, Selangor Darul Ehsan | 016-2792625 | cyschin@hotmail.com | 23500 | R-PV | 7.02 | 3 years | Allianz | 25AKG0000978-00 | 2025-04-03
2404220 | Ng Seow Fong | 790812-14-5854 | 21, Jalan Suria 6, Taman Suria, 43000 Kajang, Selangor Darul Ehsan | 012-2624548 | esther@unitrade.com.my | 23500 | R-PV | 7.02 | 3 years | Allianz | 25AKG0000979-00 | 2025-04-03
2403202 | Chuah Teah Soo | 500224-08-5017 | No 11, PT 28561, Jalan Bukit Indah, Taman Bukit Indah, 27600 Raub, Pahang Darul Makmur | 019-9867505 | sykt_pern_chuah@yahoo.com.my | 31000 | R-PV | 10.53 | 3 years | Allianz | 24AKG0003841-00 | 2024-10-03
2407392 | Ecila Sim Ju-Inn | 781228-14-5762 | 49, Jalan Duta Villa 1, Setia Alam, 40170 Shah Alam, Selangor Darul Ehsan | 019-6668520 | juinn@unitrade.com.my | 36680 | R-PV | 11.7 | 3 years | Allianz | 25AKG0000980-00 | 2025-04-03
2404232 | Wong Yoke Chon | 740422-08-5002 | 368, Jalan Tasek Permai, Kampung Tasek Permai, 68000 Ampang, Selangor Darul Ehsan | 016-2081788 | traceywong92@gmail.com | 25000 | R-PV | 7.02 | 3 years | Allianz | 25AKG0000981-00 | 2025-04-03
2407397 | Foo Su Hoong | 640115-10-5474 | 3, Jln Kenyalang 11/15D, Seksyen 11, Kota Damansara, 47810 Petaling Jaya, Selangor Darul Ehsan | 012-3739780 | suhoongfoo@gmail.com | 39600 | R-PV | 15.21 | 3 years | Allianz | 25AKG0000982-00 | 2025-04-03
2404250 | Wan Johan Bin Rahim | 860724-43-6847 | 12A, Jalan Setia Tropika U13/20B, Setia Alam, 40170 Shah Alam, Selangor Darul Ehsan | 012-3906522 | aminrahim@msn.com | 50320 | R-PV | 17.55 | 3 years | Allianz | 25AKG0000983-00 | 2025-04-03
2407399 | Koo Woon Kee | 540804-10-6087 | 50B, Jln Merah Mawar Tujuh U9/6G, Cahaya SPK, Sek U9, 40150 Shah Alam, Selangor Darul Ehsan | 012-2426698 | koowoonkee@gmail.com | 31000 | R-PV | 10.53 | 3 years | Allianz | 25AKG0000984-00 | 2025-04-03
2407394 | Nor Aini binti Mat Saman (Nazrul Latif) | 760923-08-6124 | No 49, Lorong Pinggiran Putra 3/122, Pinggiran Putra 3, 26060 Kuantan, Pahang | 019-9598431 | 0 | 24100 | R-PV | 7.02 | 3 years | Allianz | 24AKG0003844-00 | 2024-10-03
2407397-1 | Teo Kai Yun | 950515-05-5334 | 138, Lorong Warisan Villa 2/3, Taman Warisan Villa, 71800 Nilai, Negeri Sembilan Darul Khusus | 012-2531773 | allyssa_pinky@hotmail.com | 39600 | R-PV | 15.21 | 3 years | Allianz | 25AKG0000985-00 | 2025-04-03
2312114 | Chua Teng Teng | 771115-14-5820 | 130, Jln Desa Residen, Desa Parkcity, 52200 Kuala Lumpur, WP Kuala Lumpur | 012-3354488 | ttchua77@hotmail.com | 31000 | R-PV | 11.7 | 1 year | Allianz | 24AKG0003838-00 | 2024-10-03 | N/A | N/A |  | N/A |  |  | N/A
2401123 | Lee Yoon Huat | 780620-05-5273 | No 18, Jln Jalil Perkasa 19, Tmn Esplanad, 57100 Bukit Jalil, WP Kuala Lumpur | 016-2226469 | thomas119@hotmail.com | 36500 | R-PV | 12.285 | 3 years | Allianz | 25AKG0000986-00 | 2025-04-03
2404207 | Tan Boon Siang (Han Father) | 610216-02-5417 | 360, Tmn Saga Jln Alor Mengkudu, 05400 Alor Setar, Kedah Darul Aman | 017-4732831 | boon.siang@hotmail.com | 26240 | R-PV | 7.02 | 3 years | Allianz | 24AKG0003840-00 | 2024-10-03
2408402 | Tee Cheong Tuan | 621029-06-5273 | No 3, Jln BK 6A/2A, Bandar Kinrara, 47100 Puchong, Selangor | 012-3290810 | tuantee2010@gmail.com | 43000 | R-PV | 12.87 | 3 years | Allianz | 25AKG0000987-00 | 2025-04-03
2407372 | Dato Tay Tong Ben | 900522-01-5829 | 15, PTD207737, Jalan Danga Sutera 12/3, Taman Danga Sutera, 81300 Johor Bahru, Johor Darul Takzim | 016-7132622 | legendtay@hotmail.com | 37600 | R-PV | 14.04 | 3 years | Allianz | 25AKG0000988-00 | 2025-04-03
2405298 | Lim Choon Huat | 820818-01-6265 | 64, Jalan Eko Botani 1/9, Taman Eko Botani, 79100 Iskandar Puteri, Johor Darul Takzim | 012-7731700 | otakibc@gmail.com | 35960 | R-PV | 11.7 | 3 years | Allianz | 25AKG0000989-00 | 2025-04-03
2408404 | Ong Ling Gee | 690508-01-5643 | 57, Jln Melawati Tmn Melawati, 83700 Yong Peng, Johor Darul Takzim | 013-7448833 | onglinggee@yahoo.com | 24680 | R-PV | 7.02 | 3 years | Allianz | 25AKG0000990-00 | 2025-04-03
2408401 | Kuek Soon Yeam | 560722-10-6137 | No 95, Jln Hujan Bubuk, Overseas Union Garden, 58200 Kuala Lumpur, WP Kuala Lumpur | 012-3107766 | danielkuek56@hotmail.com | 22500 | R-PV | 7.02 | 3 years | Allianz | 25AKG0000991-00 | 2025-04-03
2408398 | Yap Siok Ching | 620404-10-6408 | No 33, Lrg Burhanuddin Helmi 1, Tmn Tun Dr Ismail, 60000 Kuala Lumpur, WP Kuala Lumpur | 017-2783248 | ginayap@gmail.com | 36680 | R-PV | 11.7 | 3 years | Allianz | 25AKG0000992-00 | 2025-04-03
2408415 | Shahrin Merican | 610228-71-5001 | 36, Jalan Lanai Kiara, Taman Sri Hartamas, 50480 Kuala Lumpur | 012-2967681 | sitiomar19@yahoo.com | 45600 | R-PV | 17.55 | 3 years | Allianz | 25AKG0000993-00 | 2025-04-03
2408425 | Chua Shen Huat | 600508-11-5247 | PT PT 26137, Jln USJ 3D/6, USJ Avenue, 47500 Subang Jaya, Selangor | 013-2767764 | shchua60@hotmail.com | 43100 | R-PV | 14.04 | 3 years | Allianz | 24AKG0000994-00 | 2025-04-03
2406334 | Yap Kee Leong | 640318-10-6143 | Jalan Klang Batu 16, Kampung Tambak Jawa, 45800 Jeram, Selangor | 019-6642542 | klyap1964@hotmail.com | 37600 | R-PV | 14.04 | 3 years | Allianz | 25AKG0000995-00 | 2025-04-03
2407371 | Tiong Nguong Kiong | 560304-01-5435 | No 8, Jln Mawar 6, Tmn Mawar, 28300 Triang, Pahang | 012-6628908 | meeting1210@gmail.com | 32800 | R-PV | 10.53 | 5 years | Allianz | 25AKG0000997-00 | 2025-04-03
2408409 | Lua Peck Lay | 680419-11-5184 | No 25, Lrg Kubang Buaya 78, 25050 Kuantan, Pahang | 012-9218033 | luapecklay@yahoo.com | 27700 | R-PV | 9.945 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2408411 | Akhman Aidi Putra | 850804-06-5063 | No 7, Lrg Seberang Balok Aman 22, Kg Seberang Balok, 26100 Kuantan, Pahang | 017-3054551 | mr_akhman85@yahoo.com | 24100 | R-PV | 7.02 | 3 years | Allianz | 25AKG0000998-00 | 2025-04-03
2408408 | Chiang Yoke Har | 620610-06-5002 | 2, Lrg Bukit Setongkol 45, Tmn Cenderawasih Indah, 25200 Kuantan, Pahang | 019-9896028 | yhchiang62@gmail.com | 50600 | R-PV | 17.55 | 3 years | Allianz | 25AKG0000999-00 | 2025-04-03
2408025 | Handal Green Mobility Sdn Bhd (ICE Gallery @ Pantai Sentral) | - | No 2, Jalan Pantai Sentral 1, Pantai Sentral, 59200 Kuala Lumpur | - | - | 55300 | EV Charger | 0 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2408431 | Lor Yean Yean | 600919-03-5372 | Lot 2206, Jln Bkt Losong Kg Losong Atap Zin, 21000 Kuala Terengganu | 012-9873293 | keemajujaya@gmail.com | 30000 | R-PV | 9.36 | 3 years | Allianz | 25AKG0001000-00 | 2025-04-03
2408432 | Lin Mok Kwai Yin | 521023-06-5194 | 24, Lrg Seri Setali 17, Taman Tunas Baru, 25300 Kuantan, Pahang | 013-9310848 | datoedd@gmail.com | 23800 | R-PV | 8.19 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2408407 | Kwong Wui Ee | 760907-06-5366 | No. 8, Lorong Bukit Setongkol Perdana 10, Perumahan Bukit Setongkol Perdana, 25200 Kuantan, Pahang | 012-9500330 | wuiee@hotmail.com | 29700 | R-PV | 9.36 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2409441 | Cheu Chow Sew @ Chew Chow Sew | 550726-06-5257 | Lot 690-B PPRT, Jln Paka, Kg Batu 50, 23000 Dungun Terengganu | 019-982 4668 | pnhuphin@gmail.com | 38000 | R-PV | 12.87 | 3 years | Allianz | 25AKG0001002-00 | 2025-04-03
2408433 | Ng Ek Hoo | 500712-06-5197 | 41, Lrg Sekilau 64, Jalan Hj Ahmad, 25300 Kuantan | 010-2198138 | sping26@hotmail.com | 24000 | R-PV | 5.85 | 3 years | Allianz | 25AKG0001003-00 | 2025-04-03
2409445 | Phang Kar Teck | 560510-01-6383 | B4308, Jln Hj Ahmad, Tmn Rasa Sayang, 25300 Kuantan, Pahang | 019-9862354 | centralphang@gmail.com | 22500 | R-PV | 7.02 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2408434 | Lim Ye Soon | 870920-06-5675 | Lot 7822, Lrg SJ 6-3, Tmn Emas - Sri Jaya, 26500 Maran, Pahang | 017-2152133 | limyesoon@gmail.com | 38600 | R-PV | 14.04 | 3 years | Allianz | 25AKG0001004-00 | 2025-04-03
2409442 | Lee Chiou Horng | 820611-07-5743 | 38, Jalan Udang Gantung, Taman Cuepacs, Segambut, 52000 Kuala Lumpur, | 016-2030140 | alch51@yahoo.com | 33000 | R-PV | 9.44 | 3 years | Allianz | 25AKG0001670-00 | 2025-05-29
2409443 | Dato Lim Zhen Peng | 910607-01-5085 | 15, Jalan Sentral 23/2, Taman Nusa Sentral, 79100 Iskandar Puteri, Johor | 017-6885686 | lindasushen@gmail.com | 47360 | R-PV | 17.55 | 3 years | Allianz | 25AKG0001006-00 | 2025-04-03
2408417 | Mohmad Nazeri bin Abdul Wahab | 670812-10-6015 | 2, Jalan Merbuk 7/23, Taman Bentara, 42500 Telok Panglima Garang, Selangor | 017-2051100 | 0 | 36500 | R-PV | 17.55 | 3 years
2409440 | Tan Say Kheng | 810115-10-5115 | 22, Jalan Jelok Impian 4, Taman Jelok Impian, 43000 Kajang, Selangor | 012-3850884 | tansaykheng@hotmail.com | 25520 | R-PV | 7.02 | 3 years | Allianz | 25AKG0001012-00 | 2025-04-03
2405273 | Leong Ah Seng | 570405-71-5931 | 22A, Jln PJU 3/12, Tropicana Indah, 47410 Petaling Jaya, Selangor | 012-2809511 | alicia@rossi.com.my | 44600 | R-PV | 17.55 | 3 years | Allianz | 25AKG0001009-00 | 2025-04-03
2308064 | Low Yin Jun | 910313-07-5138 | 16, Jalan CV 4B/1, Selangor Cyber Valley, 63300 Cyberjaya. Selangor Darul Ehsan | 019-3797922 | yinjunlow@gmail.com | 35000 | R-PV | 11.7 | 3 years | Allianz | 25AKG0001671-00 | 2025-05-29
2409447 | Chan Chee Tuck | 830427-06-5499 | No 43, Lorong Sri Jaya 7/4, Taman Sri Jaya Indah, 26500 Maran, Pahang | 011-51393543 | xiaoying2501@gmail.com | 22200 | R-PV | 7.02 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2409444 | Tuan Noraizan Bt Tuan Long | 750714-11-5284 | Lot 339, Kg Raja Baran, Chendering, 21080 Kuala Terengganu, Terengganu | 019-4705537 | tuan_noraizan@arb.com.my | 28700 | R-PV | 9.36 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2407368 | Noor Izzah Akmal Bt Mohd Nordin | 871023-06-5530 | Lot 104149, Lrg Pak Mahat, Kg Kempadang, 26060 Kuantan. Pahang | 010-7058844 | izzahnordeen87@gmail.com | 38600 | R-PV | 12.87 | 3 years | Allianz | 25AKG0001010-00 | 2025-04-03
2409446 | Guok Diong Chong | 640715-08-5235 | 85, Jln BU 11/6, Bandar Utama, 47800 Petaling Jaya, Selangor | 012-2685691 | dc.guok@gmail.com | 28500 | R-PV | 9.36 | 3 years | Allianz | 25AKG0001011-00 | 2025-04-03
2404249 | Tan Kheng Guan | 550603-11-5293 | PT 19441, Jln Jakar, 24000 Cukai, Terengganu | 017-9083355 | kianhui89@gmail.com | 47600 | R-PV | 17.55 | 3 years
2408424-1 | Low Bok Tek | 580321-08-5097 | 18, Lrg 20 Tmn Lake View, 34000 Taiping, Perak | 019-4799999 | btcap@hotmail.com | 46100 | R-PV | 17.55 | 3 years | Allianz | 25AKG0001013-00 | 2025-04-03
2408424-2 | Low Bok Tek | 530321-08-5097 | 18, Lrg 20 Tmn Lake View, 34000 Taiping, Perak | 019-4799999 | btcap@hotmail.com | 46100 | R-PV | 17.55 | 3 years | Allianz | 25AKG0001014-00 | 2025-04-03
2405284 | Amirul Hakim bin Omar | 940311-10-5273 | 1, Jalan Beting Dua 8/13B, Seksyen 8, 40000 Shah Alam, Selangor | 010-3825802 | akembsp5@gmail.com | 23500 | R-PV | 7.02 | 3 years | Allianz | 25AKG0001015-00 | 2025-04-03
2409448 | Pang Chong Han | 860301-43-5893 | 12, Jln Gamelan 1E, Bdr Bukit Raja, 41050 Klang, Selangor | 016-9704005 | chonghan1386@hotmail.com | 31622 | R-PV | 8.26 | 3 years | Allianz | 25AKG0001007-00 | 2025-04-03
2408400 | Oh Chai Ean | 830417-08-5066 | A7468, Jln Galing Kecil, 25250 Kuantan,Pahang | 019-9128777 | wcyyoong123@gmail.com | 43300 | R-PV | 17.55 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2409449-1 | Nurul Ain Binti Yahaya | 861226-23-5908 | No 24, Jalan KS 5/18, 25200 Kuantan, Pahang | 011-19423302 | nurulainyahaya@gmail.com | 30000 | R-PV | 9.36 | 3 years | Allianz | 25AKG0001016-00 | 2025-04-03
2409452 | Yio Pee Ban | 810215-06-5157 | 135, Jln Bkt Setongkol 3, Tmn Muhibah Fasa 2, Bukit Setongkol, 25200 Kuantan, Pahang | 019-9142311 | pee.banyio@yahoo.com | 29700 | R-PV | 10.53 | 3 years | Allianz | 25AKG0001017-00 | 2025-04-03
2409449 | Tan Hock Seng | 700111-13-5045 | 107, Jalan Udang Pasir 3, Taman Megah, Kepong, 52100 Kuala Lumpur | 012-2383954 | tan.hockseng111@gmail.com | 24908 | R-PV | 7.02 | 3 years | Allianz | 25AKG0001018-00 | 2025-04-03
2409448-1 | Claris Lim Jink Niee (Lim Chin Horng) | 020529-10-1062 | No 16, Jln Setia Nusantara U13/22T, Bandar Eco Setia, Setia Alam, 40170 Shah Alam, Selangor | 016-2176116 | clarislim2002@hmail.com | 34600 | R-PV | 11.7 | 3 years | Allianz | 25AKG0001019-00 | 2025-04-03
2406343 | Dato Sim Keng Piao | 810623-05-5361 | 632, Jalan Sri Pulai 34, Taman Sri Pulai 3, 70400 Seremban, Negeri Sembilan | 012-3599293 | piew831@gmail.com | 30000 | R-PV | 9.36 | 3 years | Allianz | 25AKG0001020-00 | 2025-04-03
2409455 | Muhamad Syamil bin Zulkafli | 850401-11-5337 | 15, Lrg Im 6/6 Indera Kayangan, Indera Mahkota, 25200 Kuantan, Pahang | 013-7196919 | syamale1985@gmail.com | 22800 | R-PV | 7.02 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2410064 | Zarita binti Saliman | 720113-01-5002 | Lot 1183, Jalan Felcra, Kampung Batu 14, 43100 Hulu Langat, Selangor | 012-8888661 | capt.arifstephen@yahoo.com | 23940 | R-PV | 7.605 | 3 years | Allianz | 25AKG0001021-00 | 2025-04-03
2405305 | Chan Woei Jye | 750414-01-6647 | No 7, Jln Anggerik Eria Tujuh 31/109G, Kota Kemuning, Seksyen 31, 40460 Shah Alam, Selangor | 016-2100036 | cwoei_jye@hotmail.com | 32000 | R-PV | 10.53 | 3 years | Allianz | 25AKG0001022-00 | 2025-04-03
2409456 | Low Hong Chin | 791203-01-5725 | 9, Jalan Panorama 2, Taman Kota Panorama, 83700 Yong Peng | 013-3533328 | aiping8113@gmail.com | 30000 | R-PV | 11.115 | 3 years | Allianz | 25AKG0001023-00 | 2025-04-03
2410461 | Low Hong Choon | 830209-01-6269 | No 21, Jln Bayu 8, Tmn Sri Bayu, 83700 Yong Peng, Johor | 012-5103669 | aiping8113@gmail.com | 23500 | R-PV | 7.02 | 3 years | Allianz | 25AKG0001024-00 | 2025-04-03
2409029 | Handal Green Mobility Sdn Bhd (Mazda Kuantan Showroom) | - | A557, Jalan Padang lalang, Padang Lalang Industrial Area, Kuantan, Pahang | - | - | 2643 | EV Charger | 0 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2410032 | Handal Green Mobility Sdn Bhd (United Point Mall, Kuala Lumpur) | - | 10, Jalan Lang Emas, Segambut, 51200 Kuala Lumpur | - | - | 38470 | EV Charger | 0 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2407167-1 | Econframe Marketing Sdn Bhd (Kilang 1 & 3) | - | No 1, Jln Sg Rasa 27 A Off, Jln Dato Mohd Sidin, 41300 Klang, Selangor | 0 | 0 | 233000 | C&I-PV | 109.395 | 3 years | Tokio Marine | GAS-G0167024-WB-AGY-25 | 2025-08-13
2407167-2 | Econframe Marketing Sdn Bhd (Kilang 4) | - | Lot 4, Jln Sg Rasa 27 A Off, Jln Dato Mohd Sidin, 41300 Klang,Selangor | 0 | 0 | 71000 | C&I-PV | 26.91 | 3 years | Tokio Marine | GAS-G0167029-WB-AGY-25 | 2025-08-13
2407167-3 | Econframe Marketing Sdn Bhd (Kilang 20) | - | Lot 63272, Lrg Sg Rasau 27A, 41300 Klang, Selangor | 0 | 0 | 136000 | C&I-PV | 67.275 | 3 years | Tokio Marine | GAS-G0167028-WB-AGY-25 | 2025-08-13
2408174 | Zimandy Construction Sdn Bhd (Bandar Tenggara) | - | 0 | 0 | 0 | 269900 | C&I-PV | 120.95 | 3 years
2408179 | Pelita Hijrah Sdn Bhd | - | Lot 71104-A, Jln Teratai, Kg Paya Jaras Hilir, 40160 Sungai Buloh, Selangor | 0 | 0 | 320000 | C&I-PV | 107.64 | 3 years | Tokio Marine | GAS-G0167685-WB-AGY-25 | 2025-08-21
2409185 | Kim Chong Mechanical Services Sdn Bhd | - | 3-KB 12, Jalan KPB 18. Kawasan Perindustrian Balakong, 43300 Seri Kembangan, Selangor | 0 | 0 | 73000 | C&I-PV | 26.55 | 3 years | Tokio Marine | GAS-G0167683-WB-AGY-25 | 2025-08-21
2410196 | Unilink Machinery Sdn Bhd | 0 | PT 85915, Jln KPG Tok Muda, Kapar, 42200 Klang. Selangor | 0 | 0 | 73000 | C&I-PV | 26.55 | 3 years | Tokio Marine | GAS0167754-WB-AGY-25 | 2025-08-21
2410474 | Koe Ban Seng | 621130-12-5429 | 8, Jln Kenyalang 11/15C, Seksyen 11, Kota Damansara, 47810 Petaling Jaya, Selangor | 012-3983893 | koebanseng@yahoo.com | 37600 | R-PV | 14.04 | 3 years | Allianz | 25AKG0001025-00 | 2025-04-03
2410468 | Teo Boon Ling | 760505-06-5312 | 1, Jalan Daun Imai 10, Sunway SPK Damansara, 52200 Kuala Lumpur | 019-2221381 | boonlingteo@yahoo.com | 36600 | R-PV | 11.7 | 3 years
2409450 | David Hie Wen Jian | 890928-10-5553 | 52, Jln BU 1/9, Bandar Utama, 47800 Petaling Jaya, Selangor | 012-3756770 | hiedavid89@gmail.com | 23500 | R-PV | 7.02 | 3 years | Allianz | 25AKG0001026-00 | 2025-04-03
2411488 | Tan Kong Ling | 661024-08-5861 | No 2, Lrg SJ 6-3, Tmn Emas-Sri Jaya, 26500 Maran, Selangor | 013-9365933 | ysy0723@hotmail.com | 32000 | R-PV | 10.53 | 3 years | Allianz | 25AKG0001027-00 | 2025-04-03
2411487 | Lim Daw Woei | 660927-01-5907 | 6, Jalan Kenyalang 11/15H, Seksyen 11, Kota Damansara, 47810 Petaling Jaya, Selangor | 012-3321852 | jolimdw@gmail.com | 42200 | R-PV | 15.21 | 3 years | Allianz | 25AKG0001028-00 | 2025-04-03
2410476 | Choong Chin Fong | 801219-01-5419 | 42, Jalan Setia 9/11, Taman Setia Indah, 81100 Johor Bahru | 013-7679113 | berny9113bc@gmail.com | 23500 | R-PV | 7.02 | 3 years | Allianz | 25AKG0001029-00 | 2025-04-03
2407376 | Teoh Eng Siong | 801211-08-5615 | No 46, Lorong Sri Jaya 7/4, Taman Sri Jaya Indah, 26500 Maran, Pahang | 019-9153886 | teoh114@gmail.com | 37768 | R-PV | 10.53 | 5 years | Allianz | 25AKG0001030-00 | 2025-04-03
2410482 | Teo Thian Keong | 870218-23-5523 | 31, Jalan SS 22/30, Petaling, 47400 Petaling Jaya, Selangor | 017-7584843 | tianqiang87@gmail.com | 28500 | R-PV | 8.775 | 3 years | Allianz | 25AKG0001031-00 | 2025-04-03
2410471 | Chua Lu Chuan | 420804-10-5133 | No 1, Lrg Seri Kuantan 28/1, Kuantan Garden, 25300 Kuantan, Pahang | 010-3959313 | cboonhuang@gmail.com | 47600 | R-PV | 17.55 | 3 years
2411489 | Quah Ewe Lee | 560319-07-5561 | 11, Jalan Kenyalang 11/15F, Seksyen 11, Kota Damansara, 47810 Petaling Jaya, Selangor | 019-3126618 | qel1888@hotmail.com | 39980 | R-PV | 14.04 | 3 years | Allianz | 25AKG0001032-00 | 2025-04-03
2411486 | Lim Chee Keong | 570825-10-5283 | 5, SD 10/1E, Jln Margosa, Bdr Sri Damansara PJU 9, 52200 Kuala Lumpur, WP Kuala Lumpur | 018-7636292 | lim.jianwen0@gmail.com | 36600 | R-PV | 13.455 | 3 years | Allianz | 25AKG0001033-00 | 2025-04-03
2411500 | Ho Maw Chun | 691208-08-5361 | 16, Jalan Kantan 5/KS6, Bandar Botanic, 41200 Klang, Selangor | 012-3306639 | hmc8925@gmail.com | 37600 | R-PV | 14.16 | 3 years | Allianz | 25AKG0001034-00 | 2025-04-03
2410034 | Handal Green Mobility Sdn Bhd (Pulse Grande Hotel) | - | Taman Putra perdana, Jalan Putra Perdana, Presint 1, 62000 Putrajaya | - | - | 4150 | EV Charger | 0 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2411494 | Pang Kim Soon | 770123-06-5463 | 44, Jalan KS 5/5, Kota Sultan Ahmad Shah, 25200 Kuantan, Pahang | 012-9833998 | ks.kspang@gmail.com | 60000 | R-PV | 17.55 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2411496 | Teong Lian Aik | 550907-08-5791 | 9(5), Regat Tasik Tmn Tasik Permai Fasa, 34000 Taiping, Perak | 012-5381739 | la_teong@yahoo.com | 29000 | R-PV | 9.36 | 3 years | Allianz | 25AKG0001035-00 | 2025-04-03
2404224 | Vijayalakshmi a/p Krishnaswamy (Tan Sri Rama Iyer) | 450528-71-5062 | Lot 310, Jln 3, Tmn Ampang Utama, 68000 Ampang, Selangor | 012-3030154 | ramavijayam10@gmail.com | 45600 | R-PV | 17.7 | 3 years | Allianz | 25AKG0001036-00 | 2025-04-03
2411491 | Low Kim Keong | 821109-06-5309 | 13, Lrg Seri Setali 11 Off Jln Galing Kem, Tmn Sri Galing, 25300 Kuantan, Pahang | 016-9210888 | adwardlow.co@gmail.com | 38420 | R-PV | 11.7 | 3 years | Allianz | 25AKG0001037-00 | 2025-04-03
2411490 | Chear Eng Soon | 840409-01-5489 | PTD 144930, No 7, Jln Pinggiran 3/2, Horizon Hills, 79100 Nusajaya, Johor | 012-7840881 | nick.chear@gmail.com | 21500 | R-PV | 7.02 | 3 years | Allianz | 25AKG0001038-00 | 2025-04-03
2412504 | Thiong Jeng Ell | 790424-06-5465 | Lot 7929, Jln Hock Bee Kg Sri Jaya, 26500 Sri Jaya, Pahang | 013-9355351 | jethiong@hotmail.com | 31616 | R-PV | 9.36 | 5 years | Allianz | 25AKG0001039-00 | 2025-04-03
2412503 | Lian Hock Seng | 781225-06-5185 | 70, Lrg SJ 4-4, Tmn Sri Jaya Indah, 26500 Maran, Pahang | 013-9933228 | hockseng8168@gmail.com | 38600 | R-PV | 14.04 | 5 years | Allianz | 25AKG0001040-00 | 2025-04-03
2410033 | Handal Green Mobility Sdn Bhd (Kuantan City Mall) | - | Jalan Putra Square 6, Putra Square, 25300 Kuantan, Pahang | - | - | 55000 | EV Charger | 0 | N/A | N/A | N/A |  | N/A |  |  | N/A |  |  | N/A
2412505 | Dong Mee Hong | 511231-08-5676 | Lot 7824, Lrg Sj 6-3, Tmn Emas-Sri Jaya, 26500 Maran, Pahang | 012-9371615 | 0 | 42860 | R-PV | 14.04 | 5 years | Allianz | 25AKG0001042-00 | 2025-04-03
2412509 | Muck Bei lee (Le Lodge Mansion) | 861105-33-5208 | No 2, Lrg Air Putih 97, Tmn Sri Air Putih, Air Putih, 25300 Kuantan, Pahang | 012-9533751 | beilee86@gmail.com | 50000 | R-PV | 17.7 | N/A | N/A | N/A |  | N/A |  |  | N/A |  |  | N/A
2412515 | Liew Mun Meng | 641211-08-6159 | 77, Jalan Taming Indah 2, Taman Taming Indah 2, 43000 Kajang, Selangor | 010-5642088 | weinnyliew88@gmail.com | 44600 | R-PV | 17.55 | 3 years | Allianz | 25AKG0001043-00 | 2025-04-03
2410462 | Yee Mei Ling | 680106-07-5302 | 19, Jalan Mas 3/2, Taman Mas 3, 43200 Cheras, Selangor | 019-2233298 | pmcoatings2010@gmail.com | 23500 | R-PV | 7.02 | 3 years | Allianz | 25AKG0001044-00 | 2025-04-03
2412516 | Chareon Phromsuwan | 680901-07-5379 | 7, Jln Kenyalang 11/15C, Seksyen 11, Kota Damansara, 47810, Petaling Jaya, Selangor | 019-3102054 | chareonp@gmail.com | 37160 | R-PV | 12.98 | 3 years | Allianz | 25AKG0001045-00 | 2025-04-03
2412521 | Christopher A De Souza | 600427-10-6373 | 24, Jalan Kenyalang 11/15G, Seksyen 11, Kota Damansara, 47810 Petaling Jaya, Selangor | 012-3328366 | christophera.desouza@gmail.com | 39560 | R-PV | 15.34 | 3 years | Allianz | 25AKG0001046-00 | 2025-04-03
2412524 | Teng Lee Xung | 850803-02-5617 | No 6, Lrg Seri Setali 119, Jln Air Putih, Tmn Semambu, 25350 Kuantan, Pahang | 012-8860611 | danileteng777@gmail.com | 34000 | R-PV | 14.16 | N/A | N/A | N/A |  | N/A |  |  | N/A |  |  | N/A
2412513 | Ganapathy Srihari a/l Rama Iyer | 720101-10-7073 | 68, Jalan Athinahapan, Taman Tun Dr Ismail, 60000 Kuala Lumpur, WP Kuala Lumpur | 012-2000599 | srihari.iyer@gmail.com | 29000 | R-PV | 10.03 | 3 years
2501038 | Florence Poon | - | 8, Lorong PJU 3/28C, 28 Residency Sunway, Damansara, 47810 Petaling Jaya, Selangor | - | - | 2000 | EV Charger | 0 | N/A | N/A | N/A |  | N/A |  |  | N/A |  |  | N/A
2501532 | Prasert Phromsuwan | 650114-07-5321 | No 37, Jln Setia Damai U13/14E, Seksyen U 13, 40170 Shah Alam, Selangor | 019-2867788 | pphromsuwan@gmail.com | 27000 | R-PV | 9.44 | 3 years | Allianz | 25AKG0001047-00 | 2025-04-03
2501544 | Gan Tek Chuan | 660508-10-5393 | Lot 11013, B26, Jln Hock Bee Kg Sri Jaya, 26500 Sri Jaya, Pahang | 011-53019513 | pekjin123@gmail.com | 44000 | R-PV | 17.7 | 3 years | Allianz | 25AKG0001048-00 | 2025-04-03
2502548 | Wong Kok Wai | 910323-06-5427 | 11, Lrg Sekilau 38, Tmn Sekilau Perdana, 25200 Kuantan, Pahang | 011-16233292 | rambowongkokwai@gmail.com | 42000 | R-PV | 17.7 | 3 years | Allianz | 25AKG0001672-00 | 2025-05-29
2501545 | Lee Tian Look | 610115-06-5321 | 53A Lrg Sj 6-3, Tmn Emas-Sri Jaya, 26500 Maran, Pahang Darul Makmur | 010-2109882 | leeweisen@gmail.com | 21800 | R-PV | 7.08 | 3 years | Allianz | 25AKG0001673-00 | 2025-05-29
2311088 | Lee Chean Chung | 810411-06-5277 | 5, Jalan 6/5, Seksyen 6. 46000 Petaling Jaya, Selangor | 012-9540498 | cheanchung@gmail.com | 27000 | R-PV | 10.62 | 3 years
2502216 | Low Yi Chin | 730830-14-5255 | Lot 4358, Jln Kuantan Kg Sri Jaya, 26500 Sri Jaya, Pahang | 012-2529900 | chipseng.srijaya@yahoo.com.my | 37000 | C&I-PV | 14.16 | 3 years
2502553 | Salim Majid Zain Bin Abdul Majid | 690717-10-5637 | 48, Jalan Lanai Kiara, Taman Sri Haratamas, 50480 Kuala Lumpur, WP Kuala Lumpur | 019-2200333 | salimmaa@gmail.com | 42000 | R-PV | 17.7 | 3 years | Allianz | 25AKG0001056-00 | 2025-04-03
2502552 | Anandan a/l Balakrishnan | 670720-05-5097 | 79, Jalan SS 18/4, SS 18, 47500 Subang Jaya, Selangor | 012-2070181 | dan.anandan@yahoo.com | 31000 | R-PV | 11.8 | 3 years | Allianz | 25AKG0001049-00 | 2025-04-03
2412519 | Liew Swee Fah | 700204-06-5293 | 203, Kg Baru, Sungai Lui, 27600 Raub, Pahang | 011-37587569 | liewsweefah5379@gmail.com | 21500 | R-PV | 7.08 | 3 years | Allianz | 25AKG0001674-00 | 2025-05-29
2502547 | Chong Chee Hoo | 860527-23-6635 | 9, Jalan Eko Botani 1/7, Taman Eko Botani, 79100 Iskandar Puteri, Johor | 012-2556708 | cheehoo1450@gmail.com | 32840 | R-PV | 11.8 | 3 years | Allianz | 25AKG0001050-00 | 2025-04-03
2502541 | Boo Kee Meng | 690901-01-5903 | 6, Jalan Bertam 21, Taman Daya, 81100 Johor Bahru | 016-7255360 | lucasboo123@hotmail.com | 21500 | R-PV | 7.08 | 3 years
2502556 | Gan Chong Sing | 900427-06-5131 | No A53, Jln Hock Bee Kg Sri Jaya, 26500 Sri Jaya, Pahang | 010-2399409 | chongsing90@hotmail.com | 22500 | R-PV | 7.08 | 3 years | Allianz | 25AKG0001051-00 | 2025-04-03
2502551 | Tan Seng Shen | 680116-01-5493 | 20, Jalan BK 6A/2G, Bandar Kinrara, 47180 Puchong, Selangor | 012-2329310 | samtan@insutex.my | 35000 | R-PV | 14.16 | 3 years | Allianz | 25AKG0001675-00 | 2025-05-29
2502546 | Jordan Tan Heng Xiang | 920619-10-5001 | 47, Jln Bungor 7, Bdr Botanic, 41200 Klang, Selangor | 016-3030529 | jordantan.1992@gmail.com | 22500 | R-PV | 7.08 | 3 years | Allianz | 25AKG0001676-00 | 2025-05-29
2502559 | Wong Peng Soon | 570816-10-5679 | 1, Lrg Im 13/7, Jln Sg Lembing (Astana Golf Resort), Indera Mahkota, 25200 Kuantan, Pahang | 012-9832681 | miaoshun@live.com.my | 28000 | R-PV | 9.44 | 3 years | Allianz | 25AKG0001052-00 | 2025-04-03
2501537 | Chan My Ling | 651015-06-5528 | No 2, Jln Mandarina 2, Bkt Manda'rina, 56000 Cheras, WP Kuala Lumpur | 011-16262901 | irenechan2708@gmail.com | 33800 | R-PV | 12.39 | 3 years | Allianz | 25AKG0001057-00 | 2025-04-03
2502550 | Ricky Goh Hoon Kan | K2270382D | 5, Jln Pahang Tmn Canning, 31400 Ipoh, Perak | 017-4380711 | rickygohhk@yahoo.com | 37500 | R-PV | 14.75 | 5 years
2502543 | Chow Leong Choon | 790829-14-5017 | 41, Jln USJ 16/3, Mukim Damansara, 47630 Petaling Jaya, Selangor | 011-33111419 | lcchow2k@yahoo.com | 22000 | R-PV | 7.08 | N/A | N/A | N/A |  | N/A |  |  | N/A |  |  | N/A
2502560 | Lim Sooi Poh | 600828-01-5237 | 17, Double Storey Semi-Detached, Jln Panorama 2, Tmn Kota Panorama, 83700 Yong Peng, Johor | 019-7137352 | c2pxian92@hotmail.com | 35000 | R-PV | 14.16 | 3 years | Allianz | 25AKG0001677-00 | 2025-05-29
2408411-1 | Eng Khai Shu | 880903-14-5138 | 72, WP Kuala Lumpur, Jalan Kasipillay, 51200 Kuala Lumpur, WP Kuala Lumpur | 012-5030513 | celinebellea0903@gmail.com | 43000 | R-PV | 17.7 | 3 years | Allianz | 25AKG0001678-00 | 2025-05-29
2502569 | Chew Beng Hock | 670201-04-5153 | 51, Jln USJ 11/1F, UEP Subang Jaya, 47600 Subang Jaya, Selangor | 017-8779033 | ameliachew76@yahoo.com | 29228 | R-PV | 8.85 | 3 years | Allianz | 25AKG0001679-00 | 2025-05-29
2502565 | Yeo Shu Jin | 820817-10-5821 | 8, Jalan Aman Perdana 8E/KU5, Taman Aman Perdana, 41050 Klang, Selangor | 012-2111891 | sjyeo82@yahoo.com | 21500 | R-PV | 7.67 | 3 years
2502549 | Har Hock Lee | 650217-08-5143 | Lot 5361, Lrg SJ 6-3, Tmn Emas-Sri Jaya, 26500 Maran, Pahang | 013-9304377 | harwanhong99@gmail.com | 35000 | R-PV | 14.16 | 3 years
2405286 | Wong Wai Hung | 760329-14-5793 | 25, Jalan SS 3/86, Taman Universiti, 47300 Petaling Jaya, Selangor | 019-2266120 | w.waihung@gmail.com | 41000 | R-PV | 17.7 | 3 years | Allianz | 25AKG0001680-00 | 2025-05-29
2501527 | Kuan Guan Chong | 551212-03-5215 | 7, Jln Impian 1, Tmn Impian Villa, 27600 Raub, Pahang | 017-9331115 | kuankianyang@hotmail.com | 31000 | R-PV | 11.8 | 3 years | Allianz | 25AKG0001681-00 | 2025-05-29
2501529 | Kuan Kian Yang | 831207-03-5225 | No 93, Jalan Impian 4, Taman Impian Villa, 27600 Raub Pahang | 017-9331115 | kuankianyang@hotmail.com | 29000 | R-PV | 10.62 | 3 years | Allianz | 25KAG0001682-00 | 2025-05-29
2502581 | Loh Chee Kuan | 810227-14-5381 | No 12, Jln Megah 11A, Tmn Megah, 43200 Batu 11 Cheras, Selangor | 012-6269463 | stanleyloh33@gmail.com | 22340 | R-PV | 7.08 | 3 years | Allianz | 25AKG0001683-00 | 2025-05-29
2501540 | Mohd Rushdi Bin Haji Abu Bakar | 730408-06-5049 | No 59, Lrg Seri Damai Aman 52, Jln Gambang, Tmn Seri Damai Aman, 25150 Kuantan, Pahang | 010-5767058 | mohd.rushdi.abu.bakar@gmail.com | 23429 | R-PV | 7.08 | 3 years | Allianz | 25AKG0001684-00 | 2025-05-29
2502571 | Ting Kam Peng | 500414-08-5173 | 13, Jln 13 Jln Klang Lama Bt 5, Tmn Lee Yan Lian, 58200 WP Kuala Lumpur | 019-3211233 | tingkampeng@gmail.com | 32840 | R-PV | 11.8 | 3 years | Allianz | 25AKG0001053-00 | 2025-04-03
2502568 | Lim See Peng | 300102-10-5815 | 16, Jln Kemuning Indah 32/142, Kemuning Utama, Seksyen 32, 40460 Shah Alam, Selangor | 012-3178932 | seepeng.lim@gmail.com | 25280 | R-PV | 7.08 | 3 years
2404258 | Chan Yee Wan | 801016-14-6283 | 52A, Jalan Aman Arahsia 2, Bandar Tropicana Aman, 42500 Telok Panglima Garang, Selangor | 012-2912577 | jason_dasb@hotmail.com | 27000 | R-PV | 9.44 | 3 years | Allianz | 25AKG0001685-00 | 2025-05-29
2503588 | Lee Xue Cheng | 051028-01-1415 | No 70, Jln Bestari 3/1, Tmn Nusa Bestari, 79150 Johor Bahru, Johor | 017-7857783 | xuechenglee1028@gmail.com | 22500 | R-PV | 7.08 | 3 years | Allianz | 25AKG0001686-00 | 2025-05-29
2502561 | Dennis Lee Jia Seng | 970507-01-6675 | No 6, Jln Panorama 7, Tmn Kota Panorama, 83700 Yong Peng, Johor | 016-7139920 | leedennis507@gmail.com | 38000 | R-PV | 15.93 | 3 years | Allianz | 25AKG0001687-00 | 2025-05-29
2503590 | Teh Wee Loon | 830510-10-5973 | 1, Jalan Aman Perdana 11K/KU5, Taman Aman Perdana, 41050 Klang, Selangor | 019-6483333 | tehweeloon@gmail.com | 39680 | R-PV | 14.16 | 3 years | Allianz | 25AKG0001688-00 | 2025-05-29
2502570 | Tang Wei Keong | 780524-14-5949 | No 5, Jln Kemuning Damai 32/147D, Kemuning Utama, Seksyen 32, 40460 Shah Alam, Selangor | 012-2398993 | wktang@synteq.com.my | 27000 | R-PV | 9.44 | 3 years
2502573 | Wong Jun Kit | 801127-10-2417 | No 1, Lrg Mohd Tahir 14A/KS2, Tmn Saujana, Kg Jawa, 41000 Klang, Selangor | 019-3840060 | junkit143@yahoo.com.sg | 26000 | R-PV | 6.49 | 3 years | Allianz | 25AKG0001689-00 | 2025-05-29
2503593 | Rashid Bin Darlan | 680415-01-5223 | No 6, Jalan Sungai Soi Jaya 3, Perumahan Sungai Soi Jaya 2, 26060 Kuantan Pahang | 012-4424191 | rash.darl@gmail.com | 24548 | R-PV | 7.08 | 3 years | Allianz | 25AKG0001690-00 | 2025-05-29
2501211 | Great Beauty Furniture Sdn Bhd | 0 | A 483, Jalan Beserah, Taman Sri Pelindung Satu, 25300 Kuantan, Pahang | 0 | 0 | 54000 | C&I-PV | 26.55 | 3 years
2502589 | Chin Kok Leng | 761030-06-5371 | 11, Lrg Sekilau 42, Jln Hj Ahmad, Tmn Sekilau Perdana, 25200 Kuantan, Pahang | 016-9221033 | cherryq16@gmail.com | 26000 | R-PV | 8.85 | 3 years | Allianz | 25AKG0001054-00 | 2025-04-03
2403090 | Mei Shun Fang Manufacturing Sdn Bhd | 0 | 0 | 0 | 0 | 898000 | C&I-PV | 476.13 | 3 years
2502557 | Chin Yee Fa | 570406-06-5491 | No 19, Lrg Im 11/6, Mahkota Heights, 25200 Kuantan, Pahang | 019-9160668 | cjhao8855@gmail.com | 28000 | R-PV | 9.44 | 3 years | Allianz | 25AKG0001691-00 | 2025-05-29
2503594 | Wong Teck Keng | 770530-14-5591 | 161, Jln USJ 9/1, UEP Subang Jaya, 47630 Subang Jaya, Selangor | 012-3153960 | teckkeng@gmail.com | 22500 | R-PV | 7.08 | 3 years | Allianz | 25AKG0001692-00 | 2025-05-29
2503597 | Bhajan Singh a/l S Bachan Singh | 520529-01-5595 | 1, Lrg Kubang Buaya 7, 25250 Kuantan, Pahang | 013-9276292 | bhajan1952@gmail.com | 31000 | R-PV | 10.62 | 3 years | Allianz | 25AKG0001693-00 | 2025-05-29
2502588 | Khadillah binti Hassan | 680623-06-5006 | D367, Jln Bukit Setongkol, Pkg Cenderawasih, 25200 Kuantan, Pahang | 012-9222442 | fenthagrow@gmail.com | 26600 | R-PV | 8.85 | 3 years | Allianz | 25AKG0001694-00 | 2025-05-29
2502040 | ST Rosyam Mall (Plus Xnergy Services Sdn Bhd) | 0 | 0 | 0 | 0 | 92000 | EV Charger | 0 | N/A | N/A | N/A |  | N/A |  |  | N/A |  |  | N/A
2503595 | Lim Zhi Jie | 991018-01-5615 | 19, Jalan Panoram 2, Taman Kota Panorama, 83700 Yong Peng, Johor | 011-33112738 | Jie_008@hotmail.com | 35000 | R-PV | 14.16 | 3 years | Allianz | 25AKG0001695-00 | 2025-05-29
2503586 | Safinaz Binti Mohd Sharif | 670915-01-5984 | Lot 2298, Jalan Sg. Soi, Kg. Sepat, 25150 Penor, Pahang. | 012-9818637 | safinazsharif67@gmail.com | 21500 | R-PV | 6.49 | 3 years
2503604 | Kong Chun Seng | 950316-14-6321 | No 200, Jalan Colonial 6, Taman Colonial, 27600 Raub, Pahang | 019-9804663 | Chunseng950316@icloud.com | 27000 | R-PV | 9.44 | 3 years | Allianz | 25AKG0001696-00 | 2025-05-29
2503598 | Lew Yuen Tang | 560915-10-5405 | 5, Jalan SS 22A/6, Damansara Jaya, 47400 Petaling Jaya, Selangor | 012-3309688 | pavirelew3@gmail.com | 27000 | R-PV | 9.44 | 3 years | Allianz | 25AKG0001697-00 | 2025-05-29
2503609 | Yau Hwee Tien | 811024-01-5944 | 70, Jalan Kota Impian 2, Taman Kota Impian, 83700 Yong Peng, Johor | 016-7601468 | hweetien@hotmail.com | 35000 | R-PV | 14.16 | 3 years | Allianz | 25AKG0001698-00 | 2025-05-29
2503610 | Datuk Abdul Rani | 730517-08-5321 | No 41, Jalan Frekuensi U16/118, Elmina East, 40160 Shah Alam, Selangor | 017-3777902 | iyadnifaelio@gmail.com | 43000 | R-PV | 17.7 | 3 years | Allianz | 25AKG0001699-00 | 2025-05-29
2503611 | Augustine Kok Hwai Nam | 640823-07-5309 | 68, Jln BU 12/6, Bandar Utama, 47800 Petaling Jaya, Selangor | 012-5017002 | augkok@gmail.com | 23500 | R-PV | 7.67 | 3 years | Allianz | 25AKG0001700-00 | 2025-05-29
2501524 | Jeremy Koo Wui Ken | 810525-14-6833 | 17, Jln BU 11/6, Bandar Utama, 47800 Petaling Jaya, Selangor | 852-52392544 | jeremy6833@gmail.com | 27000 | R-PV | 9.44 | 3 years | Allianz | 25AKG0001701-00 | 2025-05-29
2503617 | Vinny Len Siew Meng | 870530-06-5450 | No 19, Jalan Rinba Jaya 3, Taman Rimba Jaya, 28400 Mentakab, Pahang | 012-2352813 | vinnylen@gmail.com | 41000 | R-PV | 17.7 | 3 years | Allianz | 25AKG0001702-00 | 2025-05-29
2503601 | William Song Jian Tat | 0 | 0 | 0 | 0 | 29000 | R-PV | 9.44 | 3 years
2503619 | Haslina binti Othman | 670604-11-5048 | Lot 367, Jln Tg Lumpur, Kg Peramu, 26060 Kuantan, Pahang | 013-9480768 | ahbagency67@gmail.com | 21500 | 0 | 7.08 | 3 years | Project Cancelled
2504623 | Choy Poh Chu | 751103-06-5104 | No 42, Lrg Im 1/34, Bdr Indera Mahkota, 25200 Kuantan, Pahang | 017-8815769 | pohchuchoy@gmail.com | 21500 | R-PV | 7.08 | 3 years | Allianz | 25AKG0001703-00 | 2025-05-29
2503589 | Chong Shiuh Dyi | 830419-14-5229 | No 143, Jln Bidara 1, Tmn Bidara, 68100 Batu Caves, Selangor | 010-4698765 | wanderingvirocana@gmail.com | 21500 | R-PV | 7.08 | 3 years | Allianz | 25AKG0001704-00 | 2025-05-29
2504633 | Yong Chee Seng | 751025-04-5019 | 41, Jalan Aman Perdana 11K/KU5, Taman Aman Perdana, 41050 Klang, Selangor | 012-3888517 | hoongthyeengineering@gmail.com | 21500 | R-PV | 7.08 | 3 years
2504636 | Nur Salinahany binti Hanafiah | 771124-02-6014 | 36645, Rumah Lot, Jln Lapangan Terbang, 26070 Kuantan | 010-4060484 | hanynajib7577@gmail.com | 41000 | R-PV | 17.7 | 3 years | Allianz | 25AKG0001705-00 | 2025-05-29
2406152 | Chara Sdn Bhd | 0 | 3, Jalan Majistret U1/26, Hicom Glenmarie Industrial Park, 40150 Shah Alam, Selangor | 0 | 0 | 155000 | C&I-PV | 93.17 | N/A | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A | N/A
2504640 | Ng Mong Ping | 730122-01-5257 | 25, Jalan Panorama 7, Taman Kota Panorama, 83700 Yong Peng, Johor | 65-91388191 | mongping.ng@gmail.com | 26000 | R-PV | 9.44 | 3 years
2504638 | Lai Boon Liong | 791205-01-5083 | 1, Jalan Bayu 8, Taman Sri Bayu, 83700 Yong Peng, Johor | 012-4743089 | yap.sk@hotmail.com | 27000 | R-PV | 9.44 | 3 years | Allianz | 25AKG0001706-00 | 2025-05-29
2504652 | Khairul Hisham Bin Mohamed | 850301-06-5635 | 50, Taman PSJ, Lrg Sg Karang Darat 12, PKGN Sg Karang Darat, 26100 Kuantan, Pahang | 019-9709798 | khaimoha3720@gmail.com | 27500 | R-PV | 9.44 | 3 years | Allianz | 25AKG0001707-00 | 2025-05-29
2504647 | Tan Hock Cheng | 700325-01-5145 | No 20, Lrg Air Putih 102, Tmn Air Putih, Air Putih, 25300 Kuantan, Pahang | 019-9310567 | hvacrtan@gmail.com | 21500 | R-PV | 7.08 | 3 years
2504658 | Phang Yeong Chin | 780919-07-5404 | 62A, Jln USJ 12/1, UEP Subang Jaya, 47630 Subang Jaya, Selangor | 012-2965565 | phang_sk13@yahoo.com | 22500 | R-PV | 7.08 | 3 years
2503614 | Yap Weoi Kee | 670103-10-6653 | 52, Jalan SL 4/2, Bandar Sungai Long, 43000 Kajang, Selangor | 019-3100965 | yapweoikee@gmail.com | 0 | 0 | 0 | N/A | N/A | N/A |  | N/A |  |  | N/A |  |  | N/A
2504643 | Lee Sui Lian | 550331-04-5091 | E2010, Jln Mat Kilau, 25100 Kuantan, Pahang | 011-35339431 | kcwlcy0912@gmail.com | 46700 | R-PV | 17.7 | 3 years
2504663 | Too Seng Eng | 690211-06-5017 | No 18, Lrg GE 2 Tmn Gemilang Emas-Sg Jan, 27000 Jeratut Pahang | 013-9816863 | kaixuantoo@gmail.com | 22500 | R-PV | 7.08 | 3 years
2504671 | Anthony Phua Kin Loong | 860406-33-5573 | No 14, Jalan KS 12/8, Kota Sultan Ahmad Shah, 25200 Kuantan, Pahang | 016-9514838 | Anthony.phua.kl@gmail.com | 41000 | R-PV | 17.7 | 3 years
2506644 | Chang Kok Sang (Chang Vun Yu) | 510630-12-5175 | 43, Jln USJ 9/3P, UEP Subang Jaya, 47500 Subang Jaya, Selangor | 019-8606262 | clementchang@harrisons.com.my | 21000 | R-PV | 7.08 | 3 years
2505675 | Tee Hup Soon | 970830-56-5439 | No 2, Lorong Bukit Setongkol Baru 9, Perumahan Bukit Setongkol Baru, 25200 Kuantan, Pahang | 013-8040830 | thssoon@gmail.com | 42170 | R-PV | 15.34 | 3 years
2502564 | Muhammad Arif Stephen bin Abddullah | 621102-10-7661 | Lot-1183A, Jalan Felcra, Kampung Batu 14, 43100 Hulu Langat, Selangor | 012-8888661 | capt.arifstephen@yahoo.com | 43000 | R-PV | 17.7 | 3 years | Allianz | 25AKG0001708-00 | 2025-05-29
2504664 | Law Meng Siong | 680623-06-5049 | Lot 13347, Bt 2 1-2 Jln Triang, 28200 Triang, Pahang | 019-9558682 | tskiansiong@gmail.com | 41000 | R-PV | 17.7 | 3 years
2504651 | Teh Bat Kuan (Teh Eng Lim) | 580406-08-5985 | PT 1467, Regat Th 2, Taman Taiping Harmoni, 34000 Taiping, Perak | 012-52211111 | office.tehtehdev@gmail.com | 35000 | R-PV | 14.16 | 3 years
2504049 | Ayer Keroh R&R (Southbound) - Green EV Charge Sdn Bhd | 0 | 0 | 0 | 0 | 45015 | EV Charger | 0 | 0
2505686 | Lai Kwee Far | 631106-05-5079 | 20, Lrg Kurnia Jaya 3, Pkg Kurnia Jaya 1, 25150 Kuantan, Pahang | 010-9831963 | liewbonnie67@gmail.com | 21500 | R-PV | 7.08 | 3 years
2503603 | Dr Balbinder Singh a/l Gurbaksh Singh | 680315-07-5317 | 41, Jalan Tempinis 1, Taman Lucky, Bangsar, 59100 Kuala Lumpur, WP Kuala Lumpur | 012-2134001 | kgbill15@yahoo.com | 43400 | R-PV | 17.7 | 3 years
2302004 | Ong Ah Chai | 0 | 1, Lrg Galing 18, 25300 Kuantan, Pahang | 0 | 0 | 27500 | R-PV | 8.85 | N/A | N/A | N/A |  | N/A |  |  | N/A |  |  | N/A
2503225 | Weller Air-Cond Parts Enterprise Sdn Bhd | 0 | 0 | 0 | 0 | 198800 | C&I-PV | 97.6 | 3 years
2403185 | Wan Kong Wing | 640707-08-5227 | 21, JLN UNGU U9/29A, CAHAYA SPK, SEK U9, 40150 SHAH ALAM, SELANGOR | 012-3788234 | kwwan07@yahoo.com | 21500 | R-PV | 7.08 | 3 years
2410194 | Berjayapak Sdn Bhd | 0 | 0 | 0 | 0 | 395000 | C&I-PV | 207.08 | 0
2504669 | Zohairen Bin Mhamad Sori | 691107-04-5475 | 59, JLN KELAB UKAY, TMN KELAB UKAY, BKT ANTARABANGSA, 68000 AMPANG, SELANGOR | 014-6269711 | zohairen@gmail.com | 29000 | R-PV | 10.62 | 3 years
2504660 | Roshahni Binti Mhammad | 670308-03-5318 | 6, Lrg Galing 28, 25300 Kuantan, Pahang | 011-55032998 | nanimuhammad67@gmail.com | 34000 | R-PV | 14.75 | N/A | N/A | N/A |  | N/A |  |  | N/A |  |  | N/A
2410191 | Jowee Trading Sdn Bhd | 0 | 0 | 0 | 0 | 150000 | C&I-PV | 53.68 | 3 years
2505695 | Nur Salwahani Bt Muhammad | 780205-11-5670 | No 15, Lrg Im 15/7, Tmn Astana View, 25300 Kuantan, Pahang | 013-9082165 | norsalwahanimuhammad2003@gmail.com | 27000 | R-PV | 9.44 | 3 years
2505672 | Tham Wai Hong | 730725-06-5069 | 7, Lrg Air Putih 51, 25300 Kuantan, Pahang | 012-3666363 | mysamwht@gmail.com | 27000 | R-PV | 8.85 | 3 years
2505684 | Ng Heng Hock | 771118-02-5875 | 1884, Lrg Alor Akar 46, Tmn Impiana, 25300 Kuantan, Pahang | 019-9523822 | xingen150305@gmail.com | 30000 | R-PV | 11.21 | 3 years
2505697 | Chong Yee Sam | 870913-38-5355 | B3394, Lrg Galing 143, Air Putih, 25020 Kuantan, Pahang | 010-4080727 | sam2chong@gmail.com | 21500 | R-PV | 7.08 | 3 years
2505688 | Heng Mooi Sing | 771008-08-7020 | 33, Garden Manor, Sierramas, 47000 Sungai Buloh, Selangor | 012-6510878 | asam1008@hotmail.com | 40000 | R-PV | 16.52 | 3 years
2505682 | Lee Soo Kean | 650615-07-5151 | No 1, Lrg Im 1/61, Tmn Mahkota Ceria, 25200 Kuantan Pahang | 013-9377981 | sklee0665@gmail.com | 36620 | R-PV | 13.42 | 5 years
2505699 | Kiren Kaur A/P Bhajan Singh | 820207-08-5886 | No 11, Lrg Kubang Buaya 7, 25250 Kuantan, Pahang | 012-4056292 | kirenkaurbraich@gmail.com | 33000 | R-PV | 11.8 | 0
2503612 | Low Bok Tek | 580321-08-5097 | 39, Bayu Utara Seri Pilmoor, Jln PJU 1A/20, 43701 Petaling Jaya, Selangor | 019-4799999 | btcap@hotmail.com | 0 | R-PV | 17.7 | 0
2505680 | Chiang Hock Chiong | 680101-03-8297 | 15, Lorong Pelindung 3, Persisiran Residences Bukit Pelindung, 25050 Kuantan, {ahang | 012-9085551 | isaaczack@yahoo.com | 41000 | R-PV | 17.7 | 0
2503607 | Goh Boon Leng | 791028-01-5655 | 116, Jalan 20/7, Taman Paramount, 46300 Petaling Jaya, Selangor | 016-6629044 | boonlg@gmail.com | 29000 | R-PV | 10.62 | 3 years
2505711 | Lee Len Foong | 631030-06-5122 | No 16, Lrg Bukit Setongkol 171, 25200 Kuantan, Pahang | 016-5299174 | EEKIENLOONG96@GMAIL.COM | 25500 | R-PV | 8.26 | 3 years
2505713 | Yap Swee Piau | 890301-14-6351 | No. 9, Jalan KS 12/8, Kota Sultan Ahmad Shah, 25200 Kuantan, Pahang | 016-6905690 | darickyap@gmail.com | 41000 | R-PV | 17.7 | 3 years
2505714 | Kong King Wai | 811005-08-5461 | 22A, Jln Segar Perdana 4/7, Tmn Segar Perdana, 43200 Batu 11 Cheras, Selangor | 017-8775160 | kwkong555@gmail.com | 22500 | R-PV | 7.08 | 3 years
2405306 | Leong Ah Seng | 570405-71-5931 | 22, Jln PJU 3/12, Tropicana Indah, 47410 Petaling Jaya, Selangor | 012-2809511 | alicia@rossi.com.my | 43000 | R-PV | 17.7 | 3 years
2505705 | Lee Kee Chew | 570906-08-6555 | 18, Jalan SS 22/28, Damansara Jaya, 47400 Petaling Jaya, Selangor | 019-3111662 | simonlee1@yahoo.com | 21500 | R-PV | 7.08 | 3 years
2505717 | Sia Wee Leng | 700101-10-7323 | No 3, Jln Rimbunan Melor 9, Laman Rimbunan Kepong, 52100 Kuala Lumpur, WP Kuala Lumpur | 012-3862832 | lgfswl@gmail.com | 42000 | R-PV | 16.52 | 3 years
2505699-1 | Leong Wai Wung | 0 | 0 | 0 | 0 | 32000 | R-PV | 11.8 | 0
2505719 | Lim Jun Hong | 940611-08-5059 | No 7, Jln USJ 3A/8, 47680 Subang Jaya, Selangor | 016-6679002 | limjh.611@gmail.com | 27000 | R-PV | 11.78 | N/A | N/A | N/A |  | N/A |  |  | N/A |  |  | N/A
2505687 | Thayananthan A/L Lokanatan | 880603-06-5259 | No 3, Lrg Im 21/4, Perumahan Taman Indera Mahkota 21, 25200 Kuantan, Pahang | 016-7252108 | avith2309@gmail.com | 30000 | R-PV | 10.03 | N/A | N/A | N/A |  | N/A |  |  | N/A |  |  | N/A
2505718 | Koh Kheat Kian | 800626-06-5187 | 51, Jln Bkt Setongkol 3, Tmn Muhibah Fasa 2, Bukit Setongkol, 25200 Kuantan, Pahang | 012-9502255 | kk5k@yahoo.com | 23500 | R-PV | 7.44 | 3 years
2506726 | Poh Pun Hong | 651214-10-6548 | 11, Jalan Sg 1/14, Taman Sri Gombak, 68100 Batu Caves. Selangor | 012-8856276 | briancmf940921@gmail.com | 22000 | R-PV | 7.44 | 3 years
2506735 | Lee Meng Fui | 770221-06-5395 | 32, Lrg Tiram Aman 3, Perumahan Tiram Aman. 25200 Kuantan, Pahang | 012-9589956 | calvinleemf@gmail.com | 19000 | R-PV | 7.44 | N/A | N/A | N/A |  | N/A |  |  | N/A |  |  | N/A
2506734 | Leow Siew Lian (Tee Hong Yee) | 670130-06-5156 | No 7, Lrg Pelindung Pantai 11 Kg Pelindu, Tmn Pantai Pelindung 26100 Berserah, Pahang | 017-8911268 | zhixuanx23@gmail.com | 25500 | R-PV | 11.16 | N/A | N/A | N/A |  | N/A |  |  | N/A |  |  | N/A
2505708 | Mohd Shariff | 0 | 0 | 0 | 0 | 20500 | R-PV | 7.44 | 0
2506744 | Gan Chin Sam | 580625-05-5241 | 67, Jalan PJU 1A/36, Ara Damansara, 47301 Petaling Jaya, Selangor | 019-3344789 | csamgan@gmail.com | 32500 | R-PV | 14.88 | 3 years
2506727 | Tan Lee Khing | 790523-10-5186 | 2, Lorong Bukit Setongkol Baru 10, Perumahan Bukit Setongkol Baru, 25200 Kuantan, Pahang | 012-2280130 | lee_khing@yahoo.com | 28300 | R-PV | 12.4 | N/A | N/A | N/A |  | N/A |  |  | N/A |  |  | N/A
2505054 | DK Senza Residence | 0 | 0 | 0 | 0 | 59345 | EV Charger | 0 | N/A | N/A | N/A |  | N/A |  |  | N/A |  |  | N/A
2506752 | Ng Cheng Hoe | 881016-43-5205 | No. 5, Jalan Setia Utama U13/39D, Setia Alam, Seksyen U13, 40170 Shah Alam, Selangor | 013-7882286 | nevets8816@gmail.com | 22500 | R-PV | 7.44 | 3 years
2501523 | Chen Kim Hock | 601117-02-5513 | 37A, Jln Jingga 4, Tmn Pelangi, 80400 Johor Bahru, Johor | 014-7774333 | chenyeonhao@gmail.com | 44880 | R-PV | 17.7 | 3 years
2506748 | Teh Foo Hock | 650714-06-5055 | B3410, Lrg Galing 143, Air Putih, 25020 Kuantan, Pahang | 012-9839222 | 0 | 22500 | R-PV | 8.68 | N/A | N/A | N/A |  | N/A |  |  | N/A |  |  | N/A
2505709 | Tan Heng Lian | 780921-06-5117 | 31, Lrg Sri Kuantan 63, Taman Sri Kuantan, 25250 Kuantan, Pahang | 016-9619998 | Kuzo836@gmail | 39000.4 | R-PV | 17.98 | 3 years
2501531 | Mohamad Hafizi Bin Abdul Rahman | 741213-08-6337 | No 25, Lrg Bandar Damansara Kuantan 1/17, Bdr Damansara Kuantan, 26100 Kuantan, Pahang | 019-9569774 | datobulat@gmail.com | 30500 | R-PV | 13.64 | 5 years
2506757 | Chai Cheong Sing | 720125-01-5261 | 13, Lrg Seri Setali 10 Off, Jln Galing Ke, Tmn Sri Galing, 25300 Kuantan, Pahang | 012-7223686 | johnchai72@yahoo.com | 21500 | R-PV | 7.44 | 3 years
2505259 | Liew Wen Qi | 0 | A65 Bwh, Jln Seri Setali 2 Off Jln Air Putih, 25300 Kuantan, Pahang | 012-2691162 | wenqi_liew@hotmail.com | 45000 | C&I-PV | 19.52 | N/A | N/A | N/A |  | N/A |  |  | N/A |  |  | N/A
2506758 | Goh Boon Meng | 681204-06-5137 | No 6, Jln Mawar 6, Tmn Mawar, 28300 Triang, Pahang | 012-2429688 | gbm8869@gmail.com | 39500 | R-PV | 17.98 | 3 years
2506762 | Megat Mohd Nashrul Bin Ahmad Zulkepli | 851019-01-6703 | No 11, Lrg Im 8/24, Bandar Indera Mahkota, Indera Mahkota, 25200 Kuantan, Pahang | 013-6803366 | megat@nexgentechaus.com | 32500 | R-PV | 12.4 | 3 years
2506753 | Lim Geok Suan | 560421-07-5234 | No 65 A, Lrg Sekilau 22, Bkt Sekilau, 25200 Kuantan, Pahang | 012-9093055 | dinamikbudimas@gmail.com | 27500 | R-PV | 11.78 | 3 years
2506768 | Yap Lee Yan | 830913-06-5080 | No 12, Lrg Bukit Ubi 59, Perumahan Galing, 25200 Kuantan, Pahang | 017-9898860 | yenyen6513@gmail.com | 27000 | R-PV | 11.16 | 3 years
2506761 | Lee Swee Li | 730801-05-5074 | B913, Lrg Air Putih 25, Tmn Sentosa, 25350 Kuantan, Pahang | 012-9882982 | jennylee3668@gmail.com | 34000 | R-PV | 13.64 | 3 years
2506779 | Koo Hing Yew | 600610-06-5215 | No. 9, Lorong Im 21/12, Perumahan Taman Indera Mahkota 21, 25200 Kuantan, Pahang | 017-3311266 | koojayaenterprise@gmail.com | 20500 | R-PV | 7.44 | 3 years
2506781 | Teng Lily | 901117-06-5050 | 31, Jln Bkt Setongkol 3, Tmn Muhibah Fasa, Bukit Setongkol 25200 Kuantan,Pahang | 012 - 7887991 | lilyteng_5050@hotmail.com | 22000 | R-PV | 7.44 | 3 years
2506782 | Tan Shu Huat | 760905-06-5397 | 137, Lrg Bkt Setongkol Perdana 52, Tmn Fairmont Jaya, 25200 Kuantan, Pahang | 016-9223663 | singhuatmotortrd@gmail.com | 36100 | R-PV | 14.88 | 3 years
2506746 | Tan Wan Ngee | 760607-06-5364 | No 6, Lorong Pelindung 2, Persisiran Residences Bukit Pelindung, 25050 Kuantan, Pahang | 016 - 9222888 | 0 | 24000 | R-PV | 9.92 | N/A | N/A | N/A |  | N/A |  |  | N/A |  |  | N/A
2506780 | Yeo Khai Boon | 000207-06-0319 | No 9, Jalan KS 5/14, Evergreen III @ Presint 5, Kotasas, 25200 Kuantan, Pahang | 019-7046189 | ahwen000207@hotmail.com | 23800 | R-PV | 9.92 | N/A | N/A | N/A |  | N/A |  |  | N/A |  |  | N/A
2506778 | Teo Lun Wei | 940421-06-5073 | No 26, Lorong Tas Perdana 3, Perumahan Tas Perdana, 25150 Kuantan Pahang | 010 - 7696618 | 0 | 20500 | R-PV | 7.44 | 3 years
2506745 | Lee Ban Hong | 860910-56-6071 | 67, Jalan 2/C, Taman Jati, 48000 Rawang, Selangor | 018-2526174 | hueiya-lee97@hotmail.com | 32500 | R-PV | 14.88 | 3 years
2506789 | Wu Sio Yunn | 680925-06-5044 | D-278, Lrg Bukit Setongkol 211, Tmn Bukit Setongkol, 25200 Kuantan, Pahang | 013-9848650 | irenewsy@hotmail.com | 27130 | R-PV | 9.92 | 3 years
2404254 | Meor Farizal Bin Ramli | 810605-10-6153 | Lot 1433, Jln Merpati Kg Dato Ahmad Said, 30020 Ipoh, Perak | 012-5098235 | wan_8807@yahoo.com.my | 19500 | R-PV | 5.58 | 3 years
2506732 | Chai Shwu Yi (Tan Lewin) | 860913-43-6870 | 3, Jalan Mahligai 2A, Bandar Bukit Raja, 41050 Klang, Selangor | 012-2431712 | c.shwu.yi@gmail.com | 20500 | R-PV | 7.44 | 3 years
2506767 | Lee Lee Tan @ Tan Lee Lee | 681204-10-6242 | 32, Jalan SL 13/3, Bandar Sungai Long, 43000 Kajang Selangor | 012-2293778 | lilyt8793@gmail.com | 20500 | R-PV | 7.44 | 3 years
2506759 | Yim Kai Mun | 531231-05-5387 | 4, Lrg Pelindung 32, Tmn Pelindung, 25250 Kuantan, Pahang | 019 - 9518264 | johnnie.why@gmail.com | 27000 | R-PV | 10.54 | 3 years
2506794 | Ahmad Fadhil Bin Alias | 790130-11-5113 | No 16, Lrg Pelindung Damai 26 Villa, Pelindung Indah, Beserah, 26100 Kuantan, Pahang | 014-5301886 | 0 | 25000 | R-PV | 9.92 | 3 years
2506798 | Lew Sieow Shih | 780528-06-5196 | D975, Jln Kg Jawa, Tmn Sri Berlian, 25200 Kuantan, Pahang | 012 - 9554526 | 0 | 20500 | R-PV | 7.44 | 3 years
2506773 | Leiw Chew Choi | 641010-06-5028 | No 18, Lorong Pelindung 2, Persisiran Residences Bukit Pelindung, 25050 Kuantan, Pahang | 012 - 9856616 | 0 | 32500 | R-PV | 14.88 | 3 years
2506789-1 | Lim Kim Kiew | 620525-11-5212 | 48, Lrg Air Putih 3 Jln Air Puith, Tmn Seri Maju, 25300 Kuantan, Pahang | 019-9629183 | lucaslim930@gmail.com | 20500 | R-PV | 7.44 | 3 years
2506786 | Lim Chee Seng | 721110-14-5287 | NO DST11, JLN JEREJAK, TMN SETAPAK, 53000 WP KUALA LUMPUR | 019-2235411 | vincent7283@gmail.com | 30500 | R-PV | 13.64 | 3 years
2505260 | Canning Garden Baptist Church | - | 3, Lal Lee Kwee Foh, Tmn Canning, 31400 Ipoh, Perak | 05-5468480 | cgbc.ipoh@gmail.com | 95000 | C&I-PV | 48.36 | 3 years
2506799 | Lee Cheow Ban | 690614-06-5011 | No E 1111, Jln Darat Makbar, 25100 Kuantan | 017 - 9353338 | 0 | 30500 | R-PV | 13.64 | 3 years
2506276 | Tew Ah Sing @ Teo Ah Sing | 0 | 0 | 0 | 0 | 40000 | R-PV | 19.84 | 0
2506785 | Mohd Nurazuwan Bin Radzi | 860517-23-6463 | No 3, Lrg Tmn Beserah 28, Tmn Beserah, 26100 Kuantan, Pahang | 016-7794494 | nurazuwan.petrofarm@gmail.com | 34500 | R-PV | 13.64 | 3 years
2506801 | Lim Joo Eng | 520920-10-5796 | 6, Lrg Seri Teruntum 134 Jln Wong Ah Jan, 25100 Kuantan, Pahang | 012-9392331 | gigityng85@yahoo.com | 39500 | R-PV | 17.98 | 3 years
2503223 | Insultec Duragate Sdn Bhd | 0 | 0 | 0 | 0 | 117500 | C&I-PV | 58.9 | 3 years
2506802 | Hung Wen Hao | 980309-10-6169 | No 21, Lorong Sekilau 1/1, Perumahan Bukit Sekilau 1, 25200 Kuantan, Pahang | 011-1166669 | 0 | 31500 | R-PV | 13.64 | 3 years
2412510 | How Toon Huah | 560127-06-5094 | Lot 10991, Lrg Kubang Buaya 77, 25050 Kuantan, Pahang | 012-9883639 | hsmei30@yahoo.com | 34000 | R-PV | 14.88 | 3 years
2504051 | G. Semanggol R&R (Northbound) - Green EV Charge Sdn Bhd | 0 | 0 | 0 | 0 | 250000 | EV Charger | 0 | N/A
2505056 | TMG Mall Tanjung Lumpur (Handal Green Mobility) | 0 | 0 | 0 | 0 | 43000 | EV Charger | 0 | N/A
2507833 | Yee Main Way | 700220-05-5423 | No 19 B, Lrg Galing 23 Off, Jln Hj Ahmad,Tmn Hj Ahmad Mewah, 25300 Kuantan Town, Pahang | 017-9866683 | 0 | 46000 | R-PV | 12.4 | N/A | N/A | N/A |  | N/A |  |  | N/A |  |  | N/A
2409030 | TMG Mall Bandar Indera Mahkota (Handal Green Mobility) | 0 | 0 | 0 | 0 | 58000 | EV Charger | 0 | N/A
2507059 | TMG Mall IM16 (Handal Green Mobility) | 0 | 0 | 0 | 0 | 53000 | EV Charger | 0 | N/A
2507060 | TMG Mall Temerloh (Handal Green Mobility) | 0 | 0 | 0 | 0 | 55500 | EV Charger | 0 | N/A
2508858 | Chan Weng Leong | 810123-10-6089 | 37, Jalan Mulia 9, Taman Mulia, 42700 Banting, Selangor | 016-9689365 | 0 | 49000 | R-PV | 16.12 | 3 years
2507062 | Tapah R&R (Southbound) - Green EV Charge Sdn Bhd | 0 | 0 | 0 | 0 | 324360 | EV Charger | 0 | N/A
2509863 | Goh Soon Teck | 640915-06-5415 | No 51, Jln Bkt Setongkol 8, Tmn Sri Setongkol, 25200 Kuantan, Pahang | 016-9231811 | 0 | 27000 | R-PV | 9.92 | N/A
2507840 | Chew Kok leong | 0 | 376, Jalan Kg. Kolong Pahat, Kg. Kolong Pahat, 26200 Sg. Lembing, Pahang | 0 | 0 | 63000 | R-PV | 15.5 | N/A
2508857 | Chong Horng Tat | 851029-14-6341 | No 92, Mutiara Villa, Jalan Mutiara 6, Mutiara Heights, 43000 Kajang, Selangor | 016-2427853 | 0 | 49800 | R-PV | 8.68 | N/A
2305008 | Yeap Chooi Hock | 621017-08-6085 | No 65, Jalan Sri Jaya 5-1, Taman Bukit SR, 26500 Maran, Pahang | 0 | 0 | 63773.58 | C&I-PV | 17.98 | N/A
2508856 | Eddie Leong Kai Sheng | K5404484K | No 22, Jalan KS 7/1, Kota Sultan Ahmad Shah 7, 25200 Kuantan, Pahang | +65 90629902 | 0 | 73500 | R-PV | 18.6 | N/A
2510877 | Wang Pay Chen | 790603-11-5042 | PT3665, Jalan Apps 1/5, Taman Alam Perdana, 24000 Kemaman, Terengganu | 017-9869863 | 0 | 28500 | R-PV | 9.92 | N/A
2511887 | Lee Hang Meng | 700815-06-5057 | No 23, Lrg Galing 27, Tmn Sri Tahan, 25300 Kuantan, Pahang | 012-9873327 | 0 | 29000 | R-PV | 12.4 | N/A
2305019 | Soe Yew Seng | 680303-10-5531 | No 117, Lebuh Berangan, 42000 Klang, Selangor | 017-3035058 | 0 | 60000 | R-PV | 15.5 | N/A
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## Material Input
Client Name | Insultec Duragate | [7 empty] | Residential | Roof Type
Category | C&I | [7 empty] | C&I | Tiles Roof
Roof Type | Klip Lok Roof | [8 empty] | Metal Deck
Klip Lok Roof
RC Roof
Tile Hook | 0
L-Foot | 0
Klip Lok Clamp | 1796
2.6m rail | 116
5.3m rail | 104
4.7m rail | 232
3.6m rail | 0
Splicer | 284
Mid Clamp | 1460
End Clamp | 336
Grounding Clip | 840
Grounding Lug | 84
Precast Concrete Block | 0
Residential
PV Module Length (P): | 1.134 | m | PV Module Length (L) | 2.278
Purlin Distance | 1.1 | m
Common Rail Length | 2.6 | m
No of module | 0
No. of PV Module in a row | No of Rows | Total no of row | Grounding Lug | Mid-Clamp | End-Clamp | Splicers | Grounding Clip | Total L-Foot | Klip Lok clamp | No of Rail | Total Rail Length
Portrait Arrangement
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Landscape Arrangement
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C&I
PV Module Length (P): | 1.134 | m | PV Module Length (L) | 2.382
Purlin Distance | 1.1 | m
Common Rail Length | 0 | m
No of module | 814
No. of PV Module in a row | No of Rows | Total no of row | Grounding Lug | Mid-Clamp | End-Clamp | Splicers | Grounding Clip | Total L-Foot | Klip Lok clamp | 5.3 | 4.7 | 3.6 | 2.6 | No of Rail | Module Length | Total Rail Length | Remain (each side) (mm)
Portrait Arrangement
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | -0.02 | 0 | 10
Landscape Arrangement
9 | 2 | 18 | 2 | 32 | 8 | 4 | 20 | 40 | 40 | 2 |  |  |  | 2 | 10.366 | 10.6 | 117
9 | 2 | 18 | 2 | 32 | 8 | 4 | 20 | 40 | 40 | 2 |  |  |  | 2 | 10.366 | 10.6 | 117
9 | 2 | 18 | 2 | 32 | 8 | 4 | 20 | 40 | 40 | 2 |  |  |  | 2 | 10.366 | 10.6 | 117
9 | 2 | 18 | 2 | 32 | 8 | 4 | 20 | 40 | 40 | 2 |  |  |  | 2 | 10.366 | 10.6 | 117
9 | 2 | 18 | 2 | 32 | 8 | 4 | 20 | 40 | 40 | 2 |  |  |  | 2 | 10.366 | 10.6 | 117
9 | 2 | 18 | 2 | 32 | 8 | 4 | 20 | 40 | 40 | 2 |  |  |  | 2 | 10.366 | 10.6 | 117
9 | 2 | 18 | 2 | 32 | 8 | 4 | 20 | 40 | 40 | 2 |  |  |  | 2 | 10.366 | 10.6 | 117
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
9 | 2 | 18 | 2 | 32 | 8 | 4 | 20 | 40 | 40 | 2 |  |  |  | 2 | 10.366 | 10.6 | 117
9 | 2 | 18 | 2 | 32 | 8 | 4 | 20 | 40 | 40 | 2 |  |  |  | 2 | 10.366 | 10.6 | 117
9 | 2 | 18 | 2 | 32 | 8 | 4 | 20 | 40 | 40 | 2 |  |  |  | 2 | 10.366 | 10.6 | 117
9 | 2 | 18 | 2 | 32 | 8 | 4 | 20 | 40 | 40 | 2 |  |  |  | 2 | 10.366 | 10.6 | 117
9 | 2 | 18 | 2 | 32 | 8 | 4 | 20 | 40 | 40 | 2 |  |  |  | 2 | 10.366 | 10.6 | 117
9 | 2 | 18 | 2 | 32 | 8 | 4 | 20 | 40 | 40 | 2 |  |  |  | 2 | 10.366 | 10.6 | 117
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
10 | 2 | 20 | 2 | 36 | 8 | 8 | 20 | 44 | 44 |  | 2 |  | 1 | 3 | 11.52 | 12 | 240
|  | 814 | 84 | 1460 | 336 | 284 | 840 | 1796 | 1796 | 104 | 232 | 0 | 116 | 240
Note on I28: user: Assumed 1.2m purlin-to-purlin distance
Note on I53: user: Assumed 1.2m purlin-to-purlin distance
Submit

## Material Input (2) (hidden)
Client Name | Insultec Duragate | [7 empty] | Residential | Roof Type
Category | C&I | [7 empty] | C&I | Tiles Roof
Roof Type | Metal Deck | [8 empty] | Metal Deck
Klip Lok Roof
RC Roof
Tile Hook | 0
L-Foot | 0
Klip Lok Clamp | 0
2.6m rail | 0
5.3m rail | 0
4.7m rail | 0
3.6m rail | 0
Splicer | -80
Mid Clamp | 828
End Clamp | 160
Grounding Clip | 464
Grounding Lug | 40
Precast Concrete Block | 0
Residential
PV Module Length (P): | 1.134 | m | PV Module Length (L) | 2.278
Purlin Distance | 1.1 | m
Common Rail Length | 2.6 | m
No of module | 0
No. of PV Module in a row | No of Rows | Total no of row | Grounding Lug | Mid-Clamp | End-Clamp | Splicers | Grounding Clip | Total L-Foot | Klip Lok clamp | No of Rail | Total Rail Length
Portrait Arrangement
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Landscape Arrangement
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C&I
PV Module Length (P): | 1.134 | m | PV Module Length (L) | 2.382
Purlin Distance | 1.1 | m
Common Rail Length | 0 | m
No of module | 454
No. of PV Module in a row | No of Rows | Total no of row | Grounding Lug | Mid-Clamp | End-Clamp | Splicers | Grounding Clip | Total L-Foot | Klip Lok clamp | 5.3 | 4.7 | 3.6 | 1.8 | 2.6 | 1.3 | No of Rail | Module Length | Total Rail Length | Remain (each side) (mm)
Portrait Arrangement
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | -0.02 | 0 | 10
Landscape Arrangement
12 | 3 | 36 | 3 | 66 | 12 | -6 | 36 | 0 | 78 | [6 empty] | 0 | 13.828 | 0 | -6914
12 | 3 | 36 | 3 | 66 | 12 | -6 | 36 | 0 | 78 | [6 empty] | 0 | 13.828 | 0 | -6914
12 | 3 | 36 | 3 | 66 | 12 | -6 | 36 | 0 | 78 | [6 empty] | 0 | 13.828 | 0 | -6914
12 | 3 | 36 | 3 | 66 | 12 | -6 | 36 | 0 | 78 | [6 empty] | 0 | 13.828 | 0 | -6914
12 | 3 | 36 | 3 | 66 | 12 | -6 | 36 | 0 | 78 | [6 empty] | 0 | 13.828 | 0 | -6914
12 | 3 | 36 | 3 | 66 | 12 | -6 | 36 | 0 | 78 | [6 empty] | 0 | 13.828 | 0 | -6914
12 | 2 | 24 | 2 | 44 | 8 | -4 | 24 | 0 | 52 | [6 empty] | 0 | 13.828 | 0 | -6914
6 | 1 | 6 | 1 | 10 | 4 | -2 | 6 | 0 | 14 | [6 empty] | 0 | 6.904 | 0 | -3452
11 | 2 | 22 | 2 | 40 | 8 | -4 | 24 | 0 | 48 | [6 empty] | 0 | 12.674 | 0 | -6337
11 | 3 | 33 | 3 | 60 | 12 | -6 | 36 | 0 | 72 | [6 empty] | 0 | 12.674 | 0 | -6337
12 | 3 | 36 | 3 | 66 | 12 | -6 | 36 | 0 | 78 | [6 empty] | 0 | 13.828 | 0 | -6914
12 | 3 | 36 | 3 | 66 | 12 | -6 | 36 | 0 | 78 | [6 empty] | 0 | 13.828 | 0 | -6914
12 | 3 | 36 | 3 | 66 | 12 | -6 | 36 | 0 | 78 | [6 empty] | 0 | 13.828 | 0 | -6914
9 | 3 | 27 | 3 | 48 | 12 | -6 | 30 | 0 | 60 | [6 empty] | 0 | 10.366 | 0 | -5183
9 | 2 | 18 | 2 | 32 | 8 | -4 | 20 | 0 | 40 | [6 empty] | 0 | 10.366 | 0 | -5183
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | -0.02 | 0 | 10
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | -0.02 | 0 | 10
|  | 454 | 40 | 828 | 160 | -80 | 464 | 0 | 988 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on I28: user: Assumed 1.2m purlin-to-purlin distance
Note on I53: user: Assumed 1.2m purlin-to-purlin distance
Submit

## Material List
01. Installation Completed
02. Stock Ready
03. Placed Order
Client Name | Procurement Status | System Capacity | Category | Module | Module Quantity | Inverter | Roof Type | Klip Lok Clamp | L-Foot | Tile Hook | 2.6m rail | 5.3m rail | 4.7m rail | 3.6m rail | Splicer | Mid Clamp | End Clamp | Grounding Clip | Grounding Lug | Dongle | Precast Concrete Block | DC Cable (4mmsq) | DC Cable (6mmsq) | PV Connctor (Male) | PV Connctor (Female) | 3P Isolator Switch | 1-phase kWh Meter | 3-phase kWh Meter | PV AC DB | Data Logger | Weather Station | BESS | EV Charger | Optimiser | Remark
Wong Kim Mei | 01. Installation Completed | 8.05 | Residential | Astronergy 575Wp | 14 | Solinteg MHT-8K-25 hybrid | Tiles |  |  | 40 | 14 |  |  |  | 8 | 20 | 16 | 8 | 4 |  |  | 80 |  | 8 | 8 | 1 |  | 1
Ang Ching Ming | 01. Installation Completed | 12.65 | Residential | Astronergy 575Wp | 22 | Solinteg MHT-10K-25 hybrid | Tiles |  |  | 62 | 22 |  |  |  | 16 | 36 | 16 | 18 | 4 |  |  | 80 |  | 8 | 8 | 1 |  | 1
Tung Seng Chang | 01. Installation Completed | 13.625 | Residential |  | 0 | GoodWe GW10K-SDT-20 | Klip-lok | 62 |  | 0 | [5 empty] | 38 | 24 | 19 | 6 |  |  | 80 |  | 8 | 8 | 1 |  | 1 | [6 empty] | 1. Sunpower PV modules to be free-issued by EDCA.
Tan Sei Choon | 01. Installation Completed | 8.05 | Residential | Astronergy 575Wp | 14 | Solinteg MHT-8K-25 hybrid | Tiles |  |  | 40 | 14 |  |  |  | 10 | 22 | 12 | 11 | 3 |  |  | 80 |  | 8 | 8 | 1 |  | 1
Ho Hon Kit | 01. Installation Completed | 4.6 | Residential | Astronergy 575Wp | 8 | Solinteg MHS-3.6K-30 hybrid | Tiles |  |  | 23 | 8 |  |  |  | 4 | 12 | 8 | 6 | 2 |  |  | 80 |  | 5 | 5 | 1 | 1
Foo Tuang Lee | 01. Installation Completed | 4.6 | Residential | Astronergy 575Wp | 8 | Solinteg MHS-3.6K-30 hybrid | Tiles |  |  | 23 | 8 |  |  |  | 4 | 12 | 8 | 6 | 2 |  |  | 80 |  | 5 | 5 | 1 | 1
Stanley Ang Leng Chuan | 01. Installation Completed | 12.65 | Residential | Astronergy 575Wp | 22 | Solinteg MHT-10K-25 hybrid | Tiles |  |  | 68 | 24 |  |  |  | 6 | 22 | 48 | 11 | 12 |  |  | 80 |  | 8 | 8 | 1 |  | 1
Beh Poh Loh | 01. Installation Completed | 12.65 | Residential | Astronergy 575Wp | 22 | GoodWe GW10KN-ET | Klip-lok | 52 |  | 0 | [5 empty] | 36 | 16 | 18 | 4 |  |  | 80 |  | 8 | 8 | 1 |  | 1
Law Soo Chin | 01. Installation Completed | 12.65 | Residential | Astronergy 575Wp | 22 | Solinteg MHT-10K-25 hybrid | Tiles |  |  | 62 | 22 |  |  |  | 4 | 18 | 52 | 9 | 13 |  |  | 80 |  | 8 | 8 | 1 |  | 1
Tan Hong Guan | 01. Installation Completed | 10.925 | Residential | Astronergy 575Wp | 19 | Huawei SUN2000-10KTL | Tiles |  |  | 56 | 20 |  |  |  | 8 | 20 | 36 | 11 | 9 |  |  | 80 |  | 8 | 8 | 1 |  | 1
MTJ Development Sdn Bhd (InterContinental KL) | 01. Installation Completed | 51.75 | C&I | Astronergy 575Wp | 90 | GoodWe GW60KS-MT | RC |  |  | 0 | [11 empty] | 1552.5 | [6 empty] | 1 | 1 |  |  |  |  | 1. WiFi dongle to be included.
Kossan FRP Mktg (Site 1) | 01. Installation Completed | 283.945 | C&I |  | 0 | Huawei SUN2000-100KTL-M1 x 2 nos; Huawei SUN2000-30KTL-M3 x 1 nos | Metal (screw) |  |  | 0 | [11 empty] | 4259.175 | 4259.175 | [5 empty] | 1 | 1 |  |  |  |  | 1. Sunpower PV modules to be free-issued by EDCA. 2. To check if WiFi dongle can be used to replace data logger.
Ngoh Win Nee | 01. Installation Completed | 4.6 | Residential | Astronergy 575Wp | 8 | Solinteg MHS-3.6K-30 hybrid | Tiles |  |  | 23 | 8 |  |  |  | 4 | 12 | 8 | 6 | 2 |  | 0 | 80 |  | 5 | 5 | 1 | 1
Cheong Yik Yin | 01. Installation Completed | 6.9 | Residential | Astronergy 575Wp | 12 | Solinteg MHT-5K-25 hybrid | Tiles |  |  | 34 | 12 |  |  |  | 8 | 16 | 16 | 8 | 4 |  |  | 80 |  | 5 | 5 | 1 |  | 1
Ng Chong Keong | 01. Installation Completed | 16.1 | Residential | Astronergy 575Wp | 28 | Solinteg MHT-12K-25 hybrid | Tiles |  |  | 79 | 28 |  |  |  | 18 | 44 | 24 | 22 | 6 |  |  | 80 |  | 4 | 4 | 1 |  | 1
Pua Hock Meng | 01. Installation Completed | 8.625 | Residential | Astronergy 575Wp | 15 | Solinteg MHT-8K-25 hybrid | Klip-lok | 36 |  | 0 | [5 empty] | 24 | 12 | 12 | 3 |  |  | 80 |  | 4 | 4 | 1 |  | 1
Dato Arif | 01. Installation Completed | 85.1 | Off-grid | Astronergy 575Wp | 148 |  |  |  |  | 0
Lee Nyok Cheng | 01. Installation Completed | 16.1 | Residential | Astronergy 575Wp | 28 | Solinteg MHT-12K-25 hybrid | Tiles |  |  | 79 | 28 |  |  |  | 24 | 48 | 16 | 24 | 4 |  |  | 80 |  | 4 | 4 | 1 |  | 1
Kee Siew Chuan | 01. Installation Completed | 6.9 | Residential | Astronergy 575Wp | 12 | Solinteg MHT-5K-25 hybrid | Tiles |  |  | 34 | 12 |  |  |  | 8 | 20 | 8 | 10 | 2 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Ong Eng Guan | 01. Installation Completed | 8.05 | Residential | Astronergy 575Wp | 14 | Solinteg MHT-8K-25 hybrid | Metal (screw) |  | 40 |  | 14 |  |  |  | 12 | 24 | 8 | 12 | 2 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Chia Le Chin | 01. Installation Completed | 8.05 | Residential | Astronergy 575Wp | 14 | Solinteg MHT-8K-25 hybrid | Metal (screw) |  | 40 |  | 14 |  |  |  | 12 | 24 | 8 | 12 | 2 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Ching Kok Keong | 01. Installation Completed | 9.775 | Residential | Astronergy 575Wp | 17 | Solinteg MHT-8K-25 hybrid | Tiles |  |  | 48 | 17 |  |  |  | 8 | 20 | 30 | 9 | 8 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Chu Yin Shiong | 01. Installation Completed | 12.65 | Residential | Astronergy 575Wp | 22 | Solinteg MHT-10K-25 hybrid | Tiles |  |  | 62 | 22 |  |  |  | 14 | 34 | 20 | 17 | 5 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Lim Chin Joo | 01. Installation Completed | 12.65 | Residential | Astronergy 575Wp | 22 | Huawei SUN2000-12KTL | Tiles |  |  | 62 | 22 |  |  |  | 16 | 38 | 12 | 19 | 3 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Saiful Lizan | 01. Installation Completed | 13.8 | Residential | Astronergy 575Wp | 24 | Solinteg MHT-12K-25 hybrid | Tiles |  |  | 68 | 24 |  |  |  | 12 | 32 | 24 | 16 | 8 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Chew Mei May | 01. Installation Completed | 12.075 | Residential | Astronergy 575Wp | 21 | Solinteg MHT-10K-25 hybrid | Tiles |  |  | 59 | 21 |  |  |  | 10 | 30 | 28 | 14 | 8 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Susan Lau | 01. Installation Completed | 11.5 | Residential | Astronergy 575Wp | 20 | GoodWe GW10K-SDT-20 | Metal (screw) |  | 56 |  | 20 |  |  |  | 14 | 28 | 28 | 14 | 7 |  |  | 80 |  | 2 | 2 |  |  | 1
Tham Chee Man | 01. Installation Completed | 5.75 | Residential | Astronergy 575Wp | 10 | Solinteg MHS-5K-30 hybrid | Tiles |  |  | 28 | 10 |  |  |  | 4 | 12 | 16 | 6 | 4 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Dr. Suntheresan | 01. Installation Completed | 13.8 | Residential | Astronergy 575Wp | 24 | Solinteg MHT-12K-25 hybrid | Tiles |  |  | 68 | 24 |  |  |  | 18 | 36 | 24 | 18 | 6 |  |  | 80 |  | 2 | 2 |  |  | 1
Greenlast Housing Development Sdn Bhd | 01. Installation Completed | 23 | C&I | Astronergy 575Wp | 40 | Goodwe GW20KT-DT | Metal (screw) |  | 112 |  | 40 |  |  |  | 36 | 74 | 12 | 37 | 3 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Chong Fong Chin | 01. Installation Completed | 14.625 | Residential | Astronergy 585Wp | 25 | Solinteg MHT-12K-25 hybrid | Tiles |  |  | 70 | 25 |  |  |  | 18 | 36 | 28 | 18 | 7 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Chen Ah Hin | 01. Installation Completed | 11.7 | Residential | Astronergy 585Wp | 20 | Solinteg MHT-10K-25 hybrid | Tiles |  |  | 56 | 20 |  |  |  | 16 | 32 | 16 | 16 | 4 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Lim Kok Liang | 01. Installation Completed | 11.7 | Residential | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL | Tiles |  |  | 56 | 20 |  |  |  | 10 | 30 | 20 | 15 | 5 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Susan Sung Fong Thieng | 01. Installation Completed | 11.7 | Residential | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL | Tiles |  |  | 56 | 20 |  |  |  | 14 | 30 | 20 | 15 | 5 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Lee Boon Huet | 01. Installation Completed | 7.02 | Residential | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Tiles |  |  | 34 | 12 |  |  |  | 4 | 16 | 16 | 8 | 4 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Ng Yunn Chong | 01. Installation Completed | 17.55 | Residential | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | Tiles |  |  | 78 | 30 |  |  |  | 20 | 42 | 36 | 22 | 11 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Wong Hoon Sang | 01. Installation Completed | 10.53 | Residential | Astronergy 585Wp | 18 | Solinteg MHT-8K-25 hybrid | Tiles |  |  | 47 | 18 |  |  |  | 10 | 26 | 20 | 13 | 5 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Nor Aini | 01. Installation Completed | 4.68 | Residential | Astronergy 585Wp | 8 | Huawei SUN2000-4KTL-L1 | Tiles |  |  | 23 | 8 |  |  |  | 2 | 2 | 13 | 2 | 8 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Lai Kim Soon | 01. Installation Completed | 7.02 | Residential | Astronergy 585Wp | 12 | Solinteg MHS-5K-30 hybrid | Tiles |  |  | 34 | 12 |  |  |  | 6 | 18 | 12 | 9 | 3 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Tan Poh Poh | 01. Installation Completed | 7.02 | Residential | Astronergy 585Wp | 12 | Solinteg MHS-5K-30 hybrid | Tiles |  |  | 34 | 12 |  |  |  | 6 | 18 | 12 | 9 | 3 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Leau Koo Sien (Eric) | 01. Installation Completed | 16.38 | Residential | Astronergy 585Wp | 28 | Solinteg MHT-12K-25 hybrid | Tiles |  |  | 79 | 28 |  |  |  | 24 | 48 | 16 | 24 | 4 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Koon Kok Leong | 01. Installation Completed | 7.02 | Residential | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Tiles |  |  | 34 | 12 |  |  |  | 6 | 18 | 12 | 9 | 3 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Enviri Industries Sdn Bhd | 01. Installation Completed | 290.375 | C&I | Jinko Solar 575Wp | 505 | Huawei SUN2000-100KTL x 2 Huawei SUN2000-36KTL x 1 | Metal (screw) |  | 1140 |  | 0 |  |  |  | 210 | 980 | 110 | 525 | 35 |  |  | 5000 |  | 30 | 30 |  |  |  | 1 | dongle
Weller Air-Cond Parts Enterprise Sdn Bhd | 01. Installation Completed | 26.91 | C&I | Astronergy 585Wp | 46 | Huawei SUN2000-20KTL | Metal (screw) |  | 126 |  | 2 |  |  |  | 0 | 72 | 52 | 50 | 16 |  |  | 295 |  | 4 | 4 |  |  |  |  | dongle
CK Fresh Sdn Bhd | 01. Installation Completed | 43.29 | C&I | Astronergy 585Wp | 74 | Huawei SUN2000-30KTL | Metal (screw) |  | 174 |  | 4 |  |  |  | 22 | 136 | 35 | 84 | 12 |  |  | 1000 |  | 4 | 4 |  |  |  |  | dongle
Intergreen Holdings Sdn Bhd | 01. Installation Completed | 46.8 | Mixed | Astronergy 585Wp | 80 | Huawei SUN2000-12KTL-M5 x 2 Huawei SUN2000-12KTL-MB0 x 1 | Metal (screw) |  | 200 |  | 0 |  |  |  | 35 | 134 | 70 | 102 | 22 |  |  | 1100 |  | 6 | 6 |  |  |  | 1 | dongle |  | LUNA2000-5kW-C0 x1 LUNA2000-5-E0 x1 | Huawei 22kW x 2 | MERC-1300W-P x16 | Rubber wheel stopper x2 Bollard x 1
Ling Duon Kwan | 01. Installation Completed | 7.605 | Residential | Astronergy 585Wp | 13 | Huawei SUN2000-6KTL | Tiles |  |  | 34 | 13 |  |  |  | 4 | 16 | 20 | 8 | 5 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Lim Kok Teong | 01. Installation Completed | 17.55 | Residential | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | Metal (screw) |  | 84 |  | 30 |  |  |  | 26 | 50 | 20 | 25 | 5 |  |  | 80 |  | 2 | 2 | 1 |  | 1 |  | dongle
Wong Wai Kwong | 01. Installation Completed | 8.19 | Residential | Astronergy 585Wp | 14 | Huawei SUN2000-6KTL | Tiles |  |  | 37 | 14 |  |  |  | 8 | 22 | 12 | 11 | 3 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Jimmy Kok Aik Lim | 01. Installation Completed | 7.02 | Residential | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Tiles |  |  | 34 | 12 |  |  |  | 8 | 16 | 16 | 8 | 4 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Chan Po Kok | 01. Installation Completed | 8.19 | Residential | Astronergy 585Wp | 14 | Huawei SUN2000-6KTL | Tiles |  |  | 40 | 14 |  |  |  | 8 | 20 | 16 | 10 | 4 |  |  | 80 |  | 2 | 2 | 1 |  | 1
Cheong Sau Ling | 01. Installation Completed | 8.775 | Residential | Astronergy 585Wp | 15 | Huawei SUN2000-8KTL | Tiles |  |  | 42 | 15 |  |  |  | 8 | 20 | 20 | 10 | 5 |  |  | 80 |  | 2 | 2 | 1
Yap Been Im (Marienne) | 01. Installation Completed | 8.775 | Residential | Astronergy 585Wp | 15 | Huawei SUN2000-8KTL | Tiles |  |  | 42 | 15 |  |  |  | 8 | 22 | 16 | 11 | 4 |  |  | 80 |  | 2 | 2 | 1
Sim Keng Chor | 01. Installation Completed | 17.55 | Residential | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | Klip-lok | 70 | [7 empty] | 50 | 20 | 25 | 5 |  |  | 80 |  | 2 | 2 | 1 |  |  |  | dongle
Nor Hana | 01. Installation Completed | 6.435 | Residential | Astronergy 585Wp | 11 | Huawei SUN2000-5KTL-M1 | RC |  |  | 31 | 11 |  |  |  | 14 | 14 | 16 | 7 | 4 |  |  | 80 |  | 2 | 2 | 1
Ng Lay Ping | 01. Installation Completed | 14.625 | Residential | Astronergy 585Wp | 25 | Huawei SUN2000-12KTL | Tiles |  |  | 70 | 25 |  |  |  | 20 | 42 | 16 | 21 | 4 |  |  | 80 |  | 2 | 2 | 1 |  |  |  | dongle
Nor Fadillah | 01. Installation Completed | 17.55 | Residential | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | Tiles |  |  | 84 | 30 |  |  |  | 15 | 40 | 38 | 21 | 11 |  |  | 80 |  | 2 | 2 | 1 |  |  |  | dongle
Billy Teoh Wee Wei | 01. Installation Completed | 17.55 | Residential | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | RC |  |  | 84 | 30 |  |  |  | 44 | 42 | 40 | 21 | 11
Teo En Chie | 01. Installation Completed | 15.795 | Residential | Astronergy 585Wp | 27 | Huawei SUN2000-12KTL | Tiles |  |  | 76 | 27 |  |  |  | 24 | 50 | 8 | 25 | 2 |  |  | 80 |  | 2 | 2 | 1 |  |  |  | dongle
Budi Jelas Sdn Bhd | 01. Installation Completed | 26.91 | C&I | Astronergy 585Wp | 46 | Huawei SUN2000-20KTL | Metal (screw) |  | 116 | 6 | 2 |  |  |  | 0 | 68 | 48 | 46 | 15 | [10 empty] | dongle
CHL Foam Sdn Bhd | 01. Installation Completed | 345.15 | C&I | Astronergy 585Wp | 590 | Huawei SUN2000-115KTL x 2 Huawei SUN2000-30KTL x 1 | Klip-lok | 1326 |  | 0 | [5 empty] | 1118 | 124 | 1118 | 34 | [10 empty] | SmartLogger
Datin Tai Bee Choon | 01. Installation Completed | 17.55 | Residential | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | Klip-lok |  |  | 84 | 30 |  |  |  | 24 | 54 | 12 | 27 | 4
Chua Boon Seng | 01. Installation Completed | 12.285 | Residential | Astronergy 585Wp | 21 | Huawei SUN2000-8KTL | Tiles |  |  | 56 | 20 |  |  |  | 12 | 28 | 16 | 14 | 5
Ong Pui Fen | 01. Installation Completed | 7.605 | Residential | Astronergy 585Wp | 13 | Huawei SUN2000-6KTL |  |  |  | 59 | 21 |  |  |  | 8 | 14 | 24 | 7 | 7
Goh Wee Bang | 01. Installation Completed | 13.455 | Residential | Astronergy 585Wp | 23 | Huawei SUN2000-10KTL | Tiles |  |  | 82 | 29 |  |  |  | 14 | 28 | 48 | 15 | 9 |  |  | 80 |  | 8 | 8 | 1
Chan Hui Li | 01. Installation Completed | 9.36 | Residential | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL |  |  |  | 45 | 16 |  |  |  | 8 | 24 | 16 | 12 | 5
Teoh Kah Ming | 01. Installation Completed | 9.36 | Residential | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL |  |  |  | 0
Gan Wei Kuan | 01. Installation Completed | 7.02 | Residential | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 |  |  |  | 0
Haiu Chan Lai | 01. Installation Completed | 8.775 | Residential | Astronergy 585Wp | 15 | Huawei SUN2000-8KTL | Tiles |  |  | 56 | 20 |  |  |  | 10 | 20 | 22 | 10 | 6
Shreeram | 01. Installation Completed | 8.19 | Residential | Astronergy 585Wp | 14 | Huawei SUN2000-6KTL | Tiles |  |  | 45 | 16 |  |  |  | 10 | 22 | 12 | 11 | 4
Yeap Say Woei | 01. Installation Completed | 13.455 | Residential | Astronergy 585Wp | 23 | Huawei SUN2000-10KTL |  |  |  | 0
Tan Zhi Cheng | 01. Installation Completed | 7.02 | Residential | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Tiles |  |  | 45 | 16 |  |  |  | 9 | 20 | 12 | 11 | 5
Teh Siew Eng | 01. Installation Completed | 12.285 | Residential | Astronergy 585Wp | 21 | Huawei SUN2000-10KTL | Tiles |  |  | 0
Lai Chun Wai | 01. Installation Completed | 8.775 | Residential | Astronergy 585Wp | 14 | Solinteg MHT-8K-25 hybrid | Tiles |  |  | 0
Tay Poh Chai | 01. Installation Completed | 14.04 | Residential | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL | Klip-lok | 68 |  | 0 | [5 empty] | 28 | 40 | 14 | 10 |  |  | 80 |  | 8 | 8 | 1 |  |  |  | dongle
Alex How Chee Keong | 01. Installation Completed | 11.7 | Residential | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL | Tiles |  |  | 0
How Mei Cheng | 01. Installation Completed | 7.02 | Residential | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Tiles |  |  | 34 | 12 |  |  |  | 6 | 18 | 12 | 9 | 4
Windy Ng | 01. Installation Completed | 9.36 | Residential | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL | Klip-lok | 62 |  | 0 | 22 |  |  |  | 16 | 26 | 12 | 13 | 4
Zainuddin Zin | 01. Installation Completed | 12.285 | Residential | Astronergy 585Wp | 21 | Huawei SUN2000-10KTL | Metal (screw) |  | 62 | 0 | 22 |  |  |  | 0 | 20 | 44 | 10 | 12
Kwan Li Shan | 01. Installation Completed | 9.36 | Residential | Astronergy 585Wp | 16 | Huawei SUN2000-8KTL | Tiles |  |  | 56 | 20 |  |  |  | 12 | 24 | 16 | 12 | 5
Liau Hui Kiem | 01. Installation Completed | 14.04 | Residential | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL | Klip-lok | 70 |  | 0 | 24 |  |  |  | 16 | 40 | 16 | 20 | 5
Mohd Nasir Man | 01. Installation Completed | 8.19 | Residential | Astronergy 585Wp | 14 | Huawei SUN2000-6KTL | Tiles |  |  | 45 | 16 |  |  |  | 8 | 20 | 16 | 10 | 5
Tan Ger Ber | 01. Installation Completed | 14.04 | Residential | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL | Tiles |  |  | 68 | 24 |  |  |  | 18 | 40 | 16 | 20 | 5
Ng Boon Kiat (Daniel) | 01. Installation Completed | 5.265 | Residential | Astronergy 585Wp | 9 | Solinteg MHS-5K-30 hybrid | Tiles |  |  | 34 | 12 |  |  |  | 6 | 12 | 12 | 6 | 4
How Yee Seun | 01. Installation Completed | 12.87 | Residential | Astronergy 585Wp | 22 | Huawei SUN2000-10KTL | Tiles |  |  | 62 | 22 |  |  |  | 10 | 32 | 24 | 16 | 7
Lau Ah Leng | 01. Installation Completed | 12.285 | Residential | Astronergy 585Wp | 21 | Huawei SUN2000-10KTL | Tiles |  |  | 79 | 28 |  |  |  | 13 | 30 | 30 | 16 | 6
Leong Tack Ming | 01. Installation Completed | 8.775 | Residential | Astronergy 585Wp | 15 | Huawei SUN2000-8KTL | Klip-lok | 56 |  | 28 | 10 |  |  |  | 5 | 20 | 20 | 10 | 6
Charles Lew Chow Leng | 01. Installation Completed | 14.04 | Residential | Astronergy 585Wp | 24 | Huawei SUN2000-12KTL | Tiles |  |  | 68 | 24 |  |  |  | 18 | 40 | 16 | 20 | 5
Loh Fook Khew | 01. Installation Completed | 12.285 | Residential | Astronergy 585Wp | 21 | Huawei SUN2000-10KTL | Metal (screw) |  |  | 68 | 24 |  |  |  | 14 | 32 | 20 | 16 | 5
Cheong Chin Meng | 01. Installation Completed | 15.21 | Residential | Astronergy 585Wp | 26 | Solinteg MHT-12K-25 hybrid | Metal (screw) |  | 79 | 0 | 28 |  |  |  | 20 | 44 | 16 | 12 | 5
Chua Ling Ling | 01. Installation Completed | 11.7 | Residential | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL | Tiles |  |  | 79 | 28 |  |  |  | 8 | 20 | 40 | 10 | 10
Yeo Chen Kok | 01. Installation Completed | 12.285 | Residential | Astronergy 585Wp | 21 | Huawei SUN2000-10KTL | Tiles |  |  | 68 | 24 |  |  |  | 16 | 34 | 16 | 18 | 5
Ong Gin Chin | 01. Installation Completed | 7.02 | Residential | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Tiles |  |  | 45 | 16 |  |  |  | 6 | 14 | 20 | 10 | 6
Amirludin Bin Awang | 01. Installation Completed | 12.285 | Residential | Astronergy 585Wp | 21 | Solinteg MHT-10K-25 hybrid | Metal (screw) |  | 68 | 0 | 24 |  |  |  | 18 | 36 | 12 | 6 | 4
Ng Siew Fong | 01. Installation Completed | 7.02 | Residential | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Tiles |  |  | 34 | 12 |  |  |  | 6 | 18 | 12 | 9 | 4
Chuah Teah Soo | 01. Installation Completed | 10.53 | Residential | Astronergy 585Wp | 18 | Huawei SUN2000-8KTL | Tiles |  |  | 45 | 16 |  |  |  | 8 | 28 | 16 | 14 | 5
Ecila Sim Jun-Inn | 01. Installation Completed | 11.7 | Residential | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL | Klip-lok | 75 |  | 0 | 24 |  |  |  | 6 | 24 | 36 | 16 | 10
Wong Yoke Chon | 01. Installation Completed | 7.02 | Residential | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Metal (screw) |  | 34 | 0 | 12 |  |  |  | 0 | 12 | 24 | 6 | 7
Foo Su Hoong | 01. Installation Completed | 15.21 | Residential | Astronergy 585Wp | 26 | Huawei SUN2000-12KTL | Tiles |  |  | 79 | 28 |  |  |  | 20 | 44 | 16 | 22 | 5
Teoh Eng Siong | 01. Installation Completed | 10.53 | Residential | Astronergy 585Wp | 18 | Huawei SUN2000-8KTL | Tiles |  |  | 56 | 20 |  |  |  | 12 | 28 | 16 | 14 | 5
Wan Johan Bin Rahim | 01. Installation Completed | 17.55 | Residential | Astronergy 585Wp | 30 | Huawei SUN2000-12KTL | Shingle |  |  | 56 | 20 |  |  |  | 20 | 50 | 20 | 25 | 6
Koo Woon Kee | 01. Installation Completed | 10.53 | Residential | Astronergy 585Wp | 18 | Huawei SUN2000-8KTL | Tiles |  |  | 62 | 22 |  |  |  | 11 | 28 | 18 | 14 | 6
Nor Aini | 01. Installation Completed | 7.02 | Residential | Astronergy 585Wp | 12 | Huawei SUN2000-5KTL-L1 | Metal (screw) |  | 34 | 0 | 12 |  |  |  | 4 | 16 | 16 | 8 | 5
Teo Kai Yun | 01. Installation Completed | 15.21 | Residential | Astronergy 585Wp | 26 | Huawei SUN2000-12KTL | Metal (screw) |  | 79 | 0 | 28 |  |  |  | 14 | 38 | 28 | 20 | 8
Chua Teng Teng | 01. Installation Completed | 11.7 | Residential | Astronergy 585Wp | 20 | Huawei SUN2000-10KTL | Tiles |  |  | 79 | 28 |  |  |  | 8 | 20 | 40 | 10 | 10
Tiong Nguong Kiong | 01. Installation Completed | R-PV | Residential | NEM | 10.53 | Astronergy 585Wp | Tiles Roof | 0 | 0 | 70 | 24 | 0 | 0 | 0 | 2 | 14 | 44 | 24 | 11 |  | 0
Kwong Wui Ee | 01. Installation Completed | R-PV | Residential | NEM | 9.36 | Astronergy 585Wp | Tiles Roof | 0 | 0 | 40 | 16 | 0 | 0 | 0 | 8 | 24 | 16 | 16 | 4 |  | 0
Econframe Marketing Sdn Bhd (Kilang 20) | 01. Installation Completed | C&I-PV | C&I | NEM | 67.275 | Yingli Solar 585Wp | Metal Deck | 0 | 260 | 0 | 6 | 4 | 44 | 8 | 46 | 214 | 32 | 120 | 8 |  | 0
Kim Chong Mechanical Services Sdn Bhd | 01. Installation Completed | C&I-PV | C&I | NEM | 26.55 | Astronergy 590Wp | Metal Deck | 0 | 112 | 0 | 0 | 0 | 0 | 30 | 8 | 68 | 44 | 52 | 11 |  | 0
Econframe Marketing Sdn Bhd (Kilang 1 & 3) | 01. Installation Completed | C&I-PV | C&I | NEM | 109.395 | Yingli Solar 585Wp | Metal Deck | 0 | 412 | 0 | 2 | 32 | 46 | 14 | 72 | 352 | 44 | 194 | 11 |  | 0
Econframe Marketing Sdn Bhd (Kilang 4) | 01. Installation Completed | C&I-PV | C&I | NEM | 26.91 | Yingli Solar 585Wp | Metal Deck | 0 | 104 | 0 | 0 | 0 | 20 | 4 | 16 | 84 | 16 | 48 | 4 |  | 0
Chua Tong Hin Hardware Sdn Bhd | 01. Installation Completed | C&I-PV | C&I | NEM | 37.44 | Astronergy 585Wp | Metal Deck | 0 | 144 | 0 | 0 | 0 | 32 | 0 | 16 | 112 | 32 | 64 | 8 |  | 0
Pelita Hijrah Sdn Bhd | 01. Installation Completed | C&I-PV | C&I | NEM | 107.64 | Astronergy 585Wp | Metal Deck | 0 | 418 | 0 | 0 | 0 | 92 | 0 | 42 | 318 | 100 | 184 | 25 |  | 0
Unilink Machinery Sdn Bhd | 01. Installation Completed | C&I-PV | C&I | NEM | 26.55 | Astronergy 590Wp | Metal Deck | 0 | 100 | 0 | 0 | 20 | 0 | 0 | 10 | 80 | 20 | 50 | 5 |  | 0
Chareon Phromsuwan | 01. Installation Completed | R-PV | Residential | NEM | 12.98 | Astronergy 590Wp | Tiles Roof | 0 | 0 | 60 | 24 | 0 | 0 | 0 | 16 | 36 | 16 | 24 | 4 |  | 0
Christopher A De Souza | 01. Installation Completed | R-PV | Residential | NEM | 15.34 | Astronergy 590Wp | Tiles Roof | 0 | 0 | 60 | 24 | 0 | 0 | 0 | 16 | 44 | 16 | 28 | 4 |  | 0
Teng Lee Xung | 01. Installation Completed | R-PV | Residential | NEM | 14.16 | Astronergy 590Wp | Tiles Roof | 0 | 0 | 98 | 36 | 0 | 0 | 0 | 16 | 28 | 40 | 34 | 10 |  | 0
Razman Bin Samsudin | 01. Installation Completed | R-PV | Residential | NEM | 13.8 | Astronergy 575Wp | Tiles Roof | 0 | 0 | 72 | 28 | 0 | 0 | 0 | 20 | 40 | 16 | 28 | 4 |  | 0
Lee Chiou Horng | 01. Installation Completed | R-PV | Residential | NEM | 9.44 | Astronergy 590Wp | Metal Deck | 0 | 80 | 0 | 32 | 0 | 0 | 0 | 24 | 24 | 16 | 16 | 4 |  | 0
Teo Boon Ling | 01. Installation Completed | R-PV | Residential | NEM | 11.7 | Astronergy 585Wp | Metal Deck | 0 | 48 | 0 | 20 | 0 | 0 | 0 | 16 | 36 | 8 | 20 | 2 |  | 0
Gan Tek Chuan | 01. Installation Completed | R-PV | Residential | NEM | 17.7 | Astronergy 590Wp | Tiles Roof | 0 | 0 | 70 | 28 | 0 | 0 | 0 | 22 | 50 | 12 | 28 | 3 |  | 0
Amirul Hakim bin Omar | 01. Installation Completed | R-PV | Residential | NEM | 7.02 | Astronergy 585Wp | Tiles Roof | 0 | 0 | 56 | 20 | 0 | 0 | 0 | 4 | 8 | 32 | 20 | 8 |  | 0
Tan Kheng Guan | 01. Installation Completed | R-PV | Residential | NEM | 17.55 | Astronergy 585Wp | Metal Deck | 0 | 148 | 0 | 60 | 0 | 0 | 0 | 48 | 48 | 24 | 36 | 6 |  | 0
Phang Kar Teck | 01. Installation Completed | R-PV | Residential | NEM | 7.02 | Astronergy 585Wp | Tiles Roof | 0 | 0 | 40 | 16 | 0 | 0 | 0 | 8 | 16 | 16 | 16 | 4 |  | 0
Pang Chong Han | 01. Installation Completed | R-PV | Residential | NEM | 8.26 | Astronergy 590Wp | Tiles Roof | 0 | 0 | 50 | 20 | 0 | 0 | 0 | 10 | 18 | 20 | 18 | 5 |  | 0
Prasert Phromsuwan | 01. Installation Completed | R-PV | Residential | NEM | 9.44 | Astronergy 590Wp | Tiles Roof | 0 | 0 | 40 | 16 | 0 | 0 | 0 | 8 | 24 | 16 | 16 | 4 |  | 0
Low Yi Chin |  | C&I-PV | C&I | NEM | 14.16 | Astronergy 590Wp | Metal Deck | 0 | 68 | 0 | 0 | 8 | 6 | 0 | 6 | 40 | 16 | 24 | 4 |  | 0
Great Beauty Furniture Sdn Bhd |  | NEM | C&I | 26.55 | 26.55 | 20 | Tiles Roof | 0 | 0 | 120 | 0 | 0 | 0 | 30 | 0 | 60 | 60 | 60 | 15 |  | 0
Chara Sdn Bhd |  |  | C&I |  |  |  | Metal Deck | 0 | 368 | 0 | 16 | 32 | 16 | 24 | 4 | 256 | 104 | 172 | 26 |  | 0
Jowee Trading Sdn Bhd |  |  | C&I |  |  |  | Metal Deck | 0 | 224 | 0 | 4 | 20 | 20 | 4 | 24 | 156 | 48 | 92 | 12 |  | 0
Zimandy Construction |  |  | C&I |  |  |  | Metal Deck | 0 | 448 | 0 | 0 | 68 | 24 | 0 | 60 | 356 | 64 | 204 | 16 |  | 0
Weller Aircond |  |  | C&I |  |  |  | Metal Deck | 0 | 396 | 0 | 36 | 20 | 0 | 56 | 56 | 264 | 112 | 188 | 28 |  | 0
Mei Shun Fang |  |  | C&I |  |  |  | Klip Lok Roof | 1676 | 0 | 0 | 0 | 0 | 0 | 0 | -112 | 1452 | 224 | 836 | 56 |  | 0
Sleep Matics |  |  | C&I |  |  |  | Klip Lok Roof | 1360 | 0 | 0 | 0 | 0 | 0 | 0 | -152 | 1056 | 304 | 608 | 76 |  | 0
Berjayapak (System 1) |  |  | C&I |  |  |  | Klip Lok Roof | 362 | 0 | 0 | 0 | 0 | 82 | 2 | 56 | 306 | 56 | 168 | 14 |  | 0
Berjayapak (System 2) |  |  | C&I |  |  |  | Klip Lok Roof | 358 | 0 | 0 | 22 | 6 | 66 | 0 | 70 | 310 | 48 | 168 | 12 |  | 0
Gereja Baptis |  |  | C&I |  |  |  | Metal Deck | 0 | 194 | 0 | 8 | 26 | 0 | 12 | 8 | 118 | 76 | 84 | 19 |  | 0
Insultec Duragate |  |  | C&I |  |  |  | Metal Deck | 0 | 242 | 0 | 2 | 24 | 0 | 30 | 28 | 162 | 56 | 108 | 14 |  | 0
Insultec Duragate |  |  | C&I |  |  |  | Metal Deck | 0 | 230 | 0 | 0 | 0 | 28 | 10 | 36 | 150 | 80 | 114 | 20 |  | 0

## Warehouse Stock (hidden)
Material | Total Amount | Delivered | Current Need | Dec Module Count
Astronergy 575Wp |  |  |  | 0
Astronergy 585Wp |  |  |  | 346
Astronergy 590Wp |  |  |  | 45
Huawei 5KTL-L1
Huawei 5KTL-M1
Huawei 6KTL-M1
Huawei 8KTL-M1
Huawei 10KTL-M1
Huawei 12KTL-M5
Tile Hook | 4592 | 4472 | 120
L-Foot | 6440 | 4270 | 2170
Klip Lok Clamp | 5633 | 1877 | 3756
2.6m rail | 2139 | 2051 | 88
5.3m rail | 260 | 56 | 204
4.7m rail | 476 | 234 | 242
3.6m rail | 224 | 56 | 168
Splicer | 1794 | 1710 | 84
Mid Clamp | 11350 | 6664 | 4686
End Clamp | 4078 | 2830 | 1248
Grounding Clip | 7036 | 4210 | 2826
Grounding Lug | 1085 | 773 | 312
Precast Concrete Block | 0 | 0 | 0