1.0: 	EPCC

| Flow Chart | Description | Resp. |
| --- | --- | --- |
| Client Enquiry Contact client to understand Client’s requirement Prepare a preliminary design based on Client requirement Prepare a business proposal for Client Submission of business proposal to Client Proposal Acceptance No Yes Client to sign proposal or to issue Letter of Award 1st Invoice Issuance & Payment Conduct site study NEM application submission to SEDA Project Planning for execution NEM Approval by SEDA & ST License Application 2nd Invoice Issuance & Payment Material Procurement & Subcon Appointment Material Delivery & Site Mobilization ST License Approval System Testing & Commissioning (T&C) NEM Meter Change & Last Invoice Issuance & Payment System Energize Obtain NEMCD from SEDA System Training & Project Handover to Client Project Closure & Handover to O&M personnel | Client Enquiry: When receiving an enquiry from a potential client, the Business Development (BD) team will contact the client to find out more about the client’s requirement. Preparation of Proposal: - After understanding the client requirement, the Engineering team will prepare a preliminary design and the BD team will prepare the business proposal for the client. The proposal will then be submitted and presented to client for client’s review and consideration. If the client does not accept the proposal, the proposal will be reviewed and revised to meet client’s requirement. Proposal Acceptance: - When the proposal is accepted by the client, the client will sign the proposal as an acceptance of the proposal, or alternatively the client can issue a Letter of Award. Upon the acceptance of the proposal by the client, the 1st invoice will be issued to the client. Site Study: - The Engineering team will conduct a site study to collect more information for the engineering design and authority submission. The site study is carried out to determine the site feasibility for the installation of solar system. Information collected on site will be communicated to the client. Authority Application: - The Authority team will prepare the documents for the NEM quota application submission to SEDA and other necessary authority application. While waiting for the NEM Quota approval, the Project team will plan for the project execution and the Engineering team will complete the detailed engineering design for the system installation. Upon receiving the NEM Quota approval, the 2nd invoice will be issued to the client and ST License application will start. Proposal Execution: - Upon receiving payment from the client, the material for the project will be procured and the subcon for the installation works will be appointed. When the material arrived, the site installation works will begin. Upon receiving the ST License approval and the completion of the installation of the system, a testing and commission will be conducted on site. The Authority team will trigger the NEM meter change process with TNB and arrange for the meter change on site. After the completion of the meter change on site, the last invoice will be issued to client and the Project team will energize the system. Proposal Completion & Handover: - Once the system is energized, a system training will be conducted to the client. The project will then be handed over to the client as project closure. The project will be handed over to the Operation & Maintenance (O&M) personnel for the start of the O&M services. | BDT ET / BDT BDT BDT/ET BDT/ Finance ET AT PT/ET Finance SC/ PT/ET SC/PT PT AT PT/Finance PT PT PT/O&M |

2.0: 	Operation & Maintenance

| Flow Chart | Description | Resp. |
| --- | --- | --- |
| Project Handover Conduct site study Prepare O&M schedule and plan Regular System Monitoring System Troubleshoot & Repair System Healthy No Yes Preventive Maintenance & System Cleaning Submission of report to client O&M Services Continues Ends Project Closure | Project Handover: When the system is energized, the project will be handed over to the O&M personnel. The O&M personnel will conduct a site study with the Project team to understand the system installed. After the site study, the O&M personnel will prepare a schedule and plan for the system maintenance. System Monitoring: - The system will be monitored daily for its performance. If the system is not performing as per the intended result, the O&M personnel will troubleshoot the problem and repair the system as necessary. If the system is performing as per the intended result, the preventive maintenance and system cleaning will be performed as per scheduled. Preventive maintenance: - After every preventive maintenance and system cleaning activities, the O&M personnel will prepare a report to list the activities done to submit to the client and obtain the client’s acknowledgement of the work done. Continuous O&M Services: - The O&M personnel will check the validity of the O&M services provided to the client. If the O&M services is coming to an end, the O&M personnel will inform the client on the end date and offer the client the option of extension of the services provided. If the client accepts, the regular monitoring of the system and services shall continue. If the client does not accept the extension, the O&M services will cease after the end date of O&M agreed period. | PT/O&M PT/O&M O&M O&M O&M O&M O&M O&M O&M O&M O&M |

3.0	Glossary of abbreviation & definition of terms used:

| Abbreviation/ Term | Description |
| --- | --- |
| BDT | Business Development Team |
| ET | Engineering Team |
| NEM | Net Energy Metering |
| O&M | Operation & Maintenance |
| PT | Project Team |
| SEDA | Sustainable Energy Development Authority |
| ST | Suruhanjaya Tenaga |